## Control
TALON ROBOTICS -- PAYLOAD DELIVERY READINESS
Control panel. Every sheet reads its parameters from the cells below.
PARAMETER | VALUE | WHAT IT CONTROLS
Reporting date | 2026-09-30 | The as-of date for RAID ageing and overdue.
Release candidate | 88 | The build readiness is assessed against. Readiness is always about ONE build, never "the latest of everything".
Extract folder | C:\Users\inouf\OneDrive\Documents\Portfolio Projects\project-4-talon-robotics\erp_extracts | Where Power Query looks for the CSV extracts. Edit if you move the repo, then Data > Refresh All.
Rig hours per week | 180 | Bookable hardware-in-the-loop hours in a week. Six rigs at 30 hours. This is what bounds the queue.
Queue rows shown | 30 | How many ranked requirements the Verification Queue sheet displays.
DATA DISCLOSURE
Talon Robotics is a fictional mechatronics company. All data in this workbook is synthetic and generated by the scripts in the sql\ folder. No confidential data is used and no claim is made about any production system.

## Data_Req
RequirementID | Title | ReqType | Priority | SubsystemCode | SubsystemName | Criticality | MinTestLevel | RequiresIndependentTester | TotalCases | CasesWithRuns | PassingCases | BlockedCases | LastPassBuild | LastGoodBuild | PassingButUnderLevelled | PassingButSelfVerified | HasEvidence | MeetsPolicy | StaleByCode | StaleByRequirement | IsCurrent | VerificationState | InterveningBuilds | AsOfBuild
REQ-0001 | The subsystem shall complete, within budget, command & telemetry link behaviour case 1 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0002 | The payload shall inhibit release when payload release mechanism behaviour case 2 | Safety | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 2 | 0 | 88 |  | 0 | 2 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0003 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 3 | Interface | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0004 | The system shall provide power management behaviour case 4 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0005 | The subsystem shall complete, within budget, command & telemetry link behaviour case 5 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0006 | The interface shall exchange, without loss, structural interface behaviour case 6 | Interface | MustShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0007 | The subsystem shall complete, within budget, ground control software behaviour case 7 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0008 | The system shall provide command & telemetry link behaviour case 8 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0009 | The interface shall exchange, without loss, payload release mechanism behaviour case 9 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0010 | The system shall provide ground control software behaviour case 10 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0011 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 11 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 4 | 4 | 2 | 1 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0012 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 12 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 39 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 9 | 88
REQ-0013 | The interface shall exchange, without loss, power management behaviour case 13 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0014 | The payload shall inhibit release when structural interface behaviour case 14 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 28 | 28 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 10 | 88
REQ-0015 | The interface shall exchange, without loss, power management behaviour case 15 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0016 | The system shall provide ground control software behaviour case 16 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0017 | The interface shall exchange, without loss, diagnostics & logging behaviour case 17 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0018 | The subsystem shall complete, within budget, structural interface behaviour case 18 | Performance | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0019 | The payload shall inhibit release when navigation & sensor fusion behaviour case 19 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0020 | The system shall provide flight control interface behaviour case 20 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0021 | The system shall provide power management behaviour case 21 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0022 | The system shall provide payload release mechanism behaviour case 22 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0023 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 23 | Interface | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0024 | The system shall provide ground control software behaviour case 24 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0025 | The interface shall exchange, without loss, flight control interface behaviour case 25 | Interface | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0026 | The payload shall inhibit release when payload release mechanism behaviour case 26 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0027 | The payload shall inhibit release when command & telemetry link behaviour case 27 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 33 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 13 | 88
REQ-0028 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 28 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0029 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 29 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0030 | The system shall record, for certification, command & telemetry link behaviour case 30 | Regulatory | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Field | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0031 | The subsystem shall complete, within budget, payload release mechanism behaviour case 31 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 4 | 4 | 4 | 0 | 88 |  | 4 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0032 | The subsystem shall complete, within budget, command & telemetry link behaviour case 32 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 2 | 2 | 1 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0033 | The system shall provide ground control software behaviour case 33 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0034 | The system shall record, for certification, flight control interface behaviour case 34 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 3 | 3 | 3 | 0 | 71 | 69 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 14 | 88
REQ-0035 | The payload shall inhibit release when flight control interface behaviour case 35 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 52 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0036 | The system shall provide flight control interface behaviour case 36 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 66 | 66 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 16 | 88
REQ-0037 | The subsystem shall complete, within budget, payload release mechanism behaviour case 37 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 62 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 19 | 88
REQ-0038 | The system shall provide navigation & sensor fusion behaviour case 38 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0039 | The system shall provide ground control software behaviour case 39 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0040 | The system shall provide navigation & sensor fusion behaviour case 40 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0041 | The system shall provide diagnostics & logging behaviour case 41 | Functional | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0042 | The system shall record, for certification, command & telemetry link behaviour case 42 | Regulatory | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Field | 1 | 3 | 3 | 2 | 1 | 88 |  | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0043 | The payload shall inhibit release when flight control interface behaviour case 43 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 39 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0044 | The payload shall inhibit release when power management behaviour case 44 | Safety | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0045 | The interface shall exchange, without loss, command & telemetry link behaviour case 45 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 64 | 64 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 1 | 88
REQ-0046 | The system shall provide ground control software behaviour case 46 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0047 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 47 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0048 | The subsystem shall complete, within budget, command & telemetry link behaviour case 48 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0049 | The subsystem shall complete, within budget, command & telemetry link behaviour case 49 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0050 | The interface shall exchange, without loss, power management behaviour case 50 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0051 | The system shall provide command & telemetry link behaviour case 51 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0052 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 52 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0053 | The payload shall inhibit release when payload release mechanism behaviour case 53 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 63 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0054 | The system shall provide navigation & sensor fusion behaviour case 54 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0056 | The system shall provide payload release mechanism behaviour case 56 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0057 | The interface shall exchange, without loss, flight control interface behaviour case 57 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 43 | 43 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 27 | 88
REQ-0058 | The subsystem shall complete, within budget, flight control interface behaviour case 58 | Performance | Nice | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0059 | The interface shall exchange, without loss, power management behaviour case 59 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0060 | The payload shall inhibit release when flight control interface behaviour case 60 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 53 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0061 | The subsystem shall complete, within budget, power management behaviour case 61 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 4 | 4 | 3 | 1 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0062 | The interface shall exchange, without loss, payload release mechanism behaviour case 62 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0063 | The system shall provide ground control software behaviour case 63 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0064 | The interface shall exchange, without loss, flight control interface behaviour case 64 | Interface | Nice | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0065 | The system shall provide diagnostics & logging behaviour case 65 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0066 | The subsystem shall complete, within budget, power management behaviour case 66 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0067 | The system shall provide ground control software behaviour case 67 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0068 | The interface shall exchange, without loss, payload release mechanism behaviour case 68 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0069 | The payload shall inhibit release when flight control interface behaviour case 69 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 3 | 1 | 59 | 59 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 21 | 88
REQ-0070 | The system shall provide command & telemetry link behaviour case 70 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0071 | The subsystem shall complete, within budget, command & telemetry link behaviour case 71 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0072 | The interface shall exchange, without loss, payload release mechanism behaviour case 72 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0073 | The interface shall exchange, without loss, command & telemetry link behaviour case 73 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0074 | The system shall provide structural interface behaviour case 74 | Functional | MustShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 2 | 2 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0075 | The interface shall exchange, without loss, power management behaviour case 75 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0076 | The subsystem shall complete, within budget, ground control software behaviour case 76 | Performance | Nice | GND-CTRL | Ground Control Software | Support | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0077 | The system shall provide payload release mechanism behaviour case 77 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 69 | 69 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 14 | 88
REQ-0078 | The payload shall inhibit release when power management behaviour case 78 | Safety | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0079 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 79 | Performance | Nice | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 1 | 1 | 1 | 0 | 69 | 69 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0080 | The payload shall inhibit release when flight control interface behaviour case 80 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 |  | 2 | 2 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0081 | The interface shall exchange, without loss, power management behaviour case 81 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0082 | The system shall provide navigation & sensor fusion behaviour case 82 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0083 | The system shall record, for certification, payload release mechanism behaviour case 83 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0085 | The interface shall exchange, without loss, payload release mechanism behaviour case 85 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 59 | 59 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 21 | 88
REQ-0086 | The interface shall exchange, without loss, power management behaviour case 86 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0087 | The system shall provide ground control software behaviour case 87 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0088 | The subsystem shall complete, within budget, command & telemetry link behaviour case 88 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 3 | 3 | 2 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0089 | The system shall record, for certification, payload release mechanism behaviour case 89 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 4 | 4 | 4 | 0 | 51 |  | 4 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0090 | The interface shall exchange, without loss, flight control interface behaviour case 90 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0091 | The interface shall exchange, without loss, structural interface behaviour case 91 | Interface | ShouldShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0092 | The payload shall inhibit release when structural interface behaviour case 92 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 31 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 9 | 88
REQ-0093 | The subsystem shall complete, within budget, power management behaviour case 93 | Performance | MustShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 2 | 2 | 1 | 1 | 39 | 39 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 4 | 88
REQ-0094 | The payload shall inhibit release when structural interface behaviour case 94 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0095 | The system shall provide command & telemetry link behaviour case 95 | Functional | Nice | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0097 | The system shall provide navigation & sensor fusion behaviour case 97 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0098 | The system shall record, for certification, payload release mechanism behaviour case 98 | Regulatory | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0099 | The system shall provide command & telemetry link behaviour case 99 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0100 | The system shall provide power management behaviour case 100 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0101 | The subsystem shall complete, within budget, command & telemetry link behaviour case 101 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0102 | The interface shall exchange, without loss, power management behaviour case 102 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0103 | The interface shall exchange, without loss, command & telemetry link behaviour case 103 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0104 | The system shall provide structural interface behaviour case 104 | Functional | ShouldShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0105 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 105 | Performance | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0106 | The payload shall inhibit release when flight control interface behaviour case 106 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 42 | 42 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 27 | 88
REQ-0107 | The subsystem shall complete, within budget, ground control software behaviour case 107 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 3 | 3 | 3 | 0 | 69 | 69 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0108 | The subsystem shall complete, within budget, structural interface behaviour case 108 | Performance | Nice | STRUCT-I | Structural Interface | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0109 | The payload shall inhibit release when payload release mechanism behaviour case 109 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 39 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0110 | The system shall provide command & telemetry link behaviour case 110 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0111 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 111 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0112 | The system shall provide diagnostics & logging behaviour case 112 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0113 | The system shall record, for certification, payload release mechanism behaviour case 113 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 3 | 3 | 2 | 1 | 88 | 31 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 29 | 88
REQ-0114 | The system shall provide navigation & sensor fusion behaviour case 114 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 67 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0115 | The system shall provide flight control interface behaviour case 115 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0116 | The payload shall inhibit release when command & telemetry link behaviour case 116 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 4 | 4 | 3 | 0 | 88 |  | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0117 | The subsystem shall complete, within budget, ground control software behaviour case 117 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 3 | 3 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0118 | The system shall provide payload release mechanism behaviour case 118 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0119 | The subsystem shall complete, within budget, power management behaviour case 119 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 2 | 1 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0120 | The subsystem shall complete, within budget, flight control interface behaviour case 120 | Performance | Nice | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 63 | 63 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 18 | 88
REQ-0121 | The interface shall exchange, without loss, ground control software behaviour case 121 | Interface | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0122 | The payload shall inhibit release when command & telemetry link behaviour case 122 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0123 | The interface shall exchange, without loss, flight control interface behaviour case 123 | Interface | Nice | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0124 | The payload shall inhibit release when power management behaviour case 124 | Safety | MustShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0125 | The interface shall exchange, without loss, flight control interface behaviour case 125 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0126 | The subsystem shall complete, within budget, command & telemetry link behaviour case 126 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0127 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 127 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0128 | The system shall provide payload release mechanism behaviour case 128 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 49 | 49 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0129 | The subsystem shall complete, within budget, flight control interface behaviour case 129 | Performance | Nice | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0130 | The system shall provide ground control software behaviour case 130 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0131 | The interface shall exchange, without loss, power management behaviour case 131 | Interface | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 46 | 46 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0132 | The payload shall inhibit release when flight control interface behaviour case 132 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 71 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0133 | The interface shall exchange, without loss, flight control interface behaviour case 133 | Interface | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0134 | The subsystem shall complete, within budget, ground control software behaviour case 134 | Performance | MustShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0137 | The system shall provide structural interface behaviour case 137 | Functional | MustShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0138 | The interface shall exchange, without loss, flight control interface behaviour case 138 | Interface | Nice | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 3 | 0 | 65 | 65 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 17 | 88
REQ-0139 | The subsystem shall complete, within budget, structural interface behaviour case 139 | Performance | ShouldShip | STRUCT-I | Structural Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0140 | The subsystem shall complete, within budget, power management behaviour case 140 | Performance | MustShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0141 | The interface shall exchange, without loss, payload release mechanism behaviour case 141 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 59 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0142 | The system shall provide ground control software behaviour case 142 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0143 | The system shall provide payload release mechanism behaviour case 143 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0144 | The system shall provide diagnostics & logging behaviour case 144 | Functional | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0145 | The system shall provide diagnostics & logging behaviour case 145 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0146 | The payload shall inhibit release when structural interface behaviour case 146 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0147 | The interface shall exchange, without loss, payload release mechanism behaviour case 147 | Interface | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 61 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 20 | 88
REQ-0148 | The payload shall inhibit release when flight control interface behaviour case 148 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 70 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 13 | 88
REQ-0149 | The payload shall inhibit release when payload release mechanism behaviour case 149 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 46 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0150 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 150 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0151 | The system shall provide power management behaviour case 151 | Functional | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0152 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 152 | Performance | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 58 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 5 | 88
REQ-0153 | The payload shall inhibit release when payload release mechanism behaviour case 153 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0154 | The system shall record, for certification, payload release mechanism behaviour case 154 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 4 | 4 | 4 | 0 | 65 | 65 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 16 | 88
REQ-0155 | The system shall provide power management behaviour case 155 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0156 | The system shall provide ground control software behaviour case 156 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0157 | The payload shall inhibit release when payload release mechanism behaviour case 157 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 68 | 68 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 14 | 88
REQ-0158 | The payload shall inhibit release when structural interface behaviour case 158 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0159 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 159 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0160 | The system shall provide navigation & sensor fusion behaviour case 160 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 63 | 63 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0161 | The system shall record, for certification, power management behaviour case 161 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 4 | 4 | 2 | 1 | 69 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0162 | The subsystem shall complete, within budget, power management behaviour case 162 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0163 | The system shall provide diagnostics & logging behaviour case 163 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0164 | The subsystem shall complete, within budget, payload release mechanism behaviour case 164 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0165 | The system shall provide payload release mechanism behaviour case 165 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 71 | 71 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 12 | 88
REQ-0166 | The payload shall inhibit release when payload release mechanism behaviour case 166 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 2 | 0 | 54 | 54 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0167 | The payload shall inhibit release when payload release mechanism behaviour case 167 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 2 | 2 | 1 | 1 | 65 | 65 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 16 | 88
REQ-0168 | The system shall provide ground control software behaviour case 168 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0169 | The subsystem shall complete, within budget, payload release mechanism behaviour case 169 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 1 | 1 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0170 | The system shall provide ground control software behaviour case 170 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0171 | The subsystem shall complete, within budget, power management behaviour case 171 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 2 | 1 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0172 | The payload shall inhibit release when navigation & sensor fusion behaviour case 172 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 3 | 3 | 3 | 0 | 88 |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0173 | The system shall provide command & telemetry link behaviour case 173 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0175 | The subsystem shall complete, within budget, command & telemetry link behaviour case 175 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0176 | The system shall record, for certification, payload release mechanism behaviour case 176 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0177 | The system shall provide command & telemetry link behaviour case 177 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0178 | The system shall provide flight control interface behaviour case 178 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 47 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0180 | The interface shall exchange, without loss, ground control software behaviour case 180 | Interface | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0181 | The payload shall inhibit release when payload release mechanism behaviour case 181 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0182 | The subsystem shall complete, within budget, structural interface behaviour case 182 | Performance | Nice | STRUCT-I | Structural Interface | Safety | HIL | 0 | 4 | 4 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0184 | The subsystem shall complete, within budget, power management behaviour case 184 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 48 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0185 | The system shall provide ground control software behaviour case 185 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0186 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 186 | Interface | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0187 | The system shall record, for certification, flight control interface behaviour case 187 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 1 | 1 | 1 | 0 | 55 | 55 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0188 | The system shall provide structural interface behaviour case 188 | Functional | ShouldShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 3 | 3 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0189 | The payload shall inhibit release when flight control interface behaviour case 189 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 59 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0190 | The system shall provide command & telemetry link behaviour case 190 | Functional | Nice | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0191 | The payload shall inhibit release when payload release mechanism behaviour case 191 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 65 | 65 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 16 | 88
REQ-0193 | The system shall provide command & telemetry link behaviour case 193 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0194 | The system shall record, for certification, power management behaviour case 194 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 2 | 2 | 2 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0195 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 195 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0196 | The payload shall inhibit release when command & telemetry link behaviour case 196 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0197 | The system shall provide navigation & sensor fusion behaviour case 197 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 2 | 1 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0198 | The system shall record, for certification, payload release mechanism behaviour case 198 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 4 | 4 | 4 | 0 | 69 | 60 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 20 | 88
REQ-0199 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 199 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0200 | The system shall provide navigation & sensor fusion behaviour case 200 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0201 | The interface shall exchange, without loss, diagnostics & logging behaviour case 201 | Interface | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0203 | The payload shall inhibit release when flight control interface behaviour case 203 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0204 | The system shall provide navigation & sensor fusion behaviour case 204 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0205 | The subsystem shall complete, within budget, power management behaviour case 205 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 2 | 2 | 1 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0206 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 206 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0207 | The interface shall exchange, without loss, diagnostics & logging behaviour case 207 | Interface | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0208 | The interface shall exchange, without loss, flight control interface behaviour case 208 | Interface | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 67 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0209 | The system shall provide navigation & sensor fusion behaviour case 209 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0210 | The payload shall inhibit release when flight control interface behaviour case 210 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0211 | The interface shall exchange, without loss, payload release mechanism behaviour case 211 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0212 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 212 | Performance | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0213 | The interface shall exchange, without loss, command & telemetry link behaviour case 213 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0214 | The system shall provide ground control software behaviour case 214 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0215 | The system shall provide navigation & sensor fusion behaviour case 215 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0216 | The interface shall exchange, without loss, command & telemetry link behaviour case 216 | Interface | Nice | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 49 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 6 | 88
REQ-0217 | The payload shall inhibit release when payload release mechanism behaviour case 217 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 40 | 40 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 25 | 88
REQ-0218 | The interface shall exchange, without loss, power management behaviour case 218 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0219 | The system shall provide ground control software behaviour case 219 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0220 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 220 | Performance | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0221 | The payload shall inhibit release when command & telemetry link behaviour case 221 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0222 | The system shall provide payload release mechanism behaviour case 222 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0223 | The subsystem shall complete, within budget, ground control software behaviour case 223 | Performance | MustShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0224 | The payload shall inhibit release when command & telemetry link behaviour case 224 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 3 | 3 | 2 | 1 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0225 | The payload shall inhibit release when flight control interface behaviour case 225 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 51 | 51 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 23 | 88
REQ-0226 | The payload shall inhibit release when structural interface behaviour case 226 | Safety | ShouldShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0227 | The interface shall exchange, without loss, power management behaviour case 227 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0228 | The system shall record, for certification, command & telemetry link behaviour case 228 | Regulatory | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Field | 1 | 2 | 2 | 1 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0229 | The interface shall exchange, without loss, power management behaviour case 229 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0230 | The system shall provide flight control interface behaviour case 230 | Functional | Nice | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0231 | The interface shall exchange, without loss, command & telemetry link behaviour case 231 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0232 | The payload shall inhibit release when payload release mechanism behaviour case 232 | Safety | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0233 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 233 | Interface | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 1 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0234 | The system shall provide ground control software behaviour case 234 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0235 | The system shall record, for certification, flight control interface behaviour case 235 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 3 | 3 | 3 | 0 | 68 | 37 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 29 | 88
REQ-0236 | The subsystem shall complete, within budget, ground control software behaviour case 236 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0237 | The subsystem shall complete, within budget, power management behaviour case 237 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0239 | The interface shall exchange, without loss, power management behaviour case 239 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0240 | The system shall provide payload release mechanism behaviour case 240 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0241 | The system shall provide ground control software behaviour case 241 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0242 | The payload shall inhibit release when command & telemetry link behaviour case 242 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0243 | The payload shall inhibit release when flight control interface behaviour case 243 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 1 | 0 | 45 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0244 | The interface shall exchange, without loss, command & telemetry link behaviour case 244 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0245 | The subsystem shall complete, within budget, flight control interface behaviour case 245 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0246 | The payload shall inhibit release when payload release mechanism behaviour case 246 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0247 | The subsystem shall complete, within budget, command & telemetry link behaviour case 247 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0248 | The subsystem shall complete, within budget, power management behaviour case 248 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0249 | The subsystem shall complete, within budget, command & telemetry link behaviour case 249 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 2 | 2 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0250 | The interface shall exchange, without loss, diagnostics & logging behaviour case 250 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0251 | The system shall provide ground control software behaviour case 251 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0252 | The payload shall inhibit release when payload release mechanism behaviour case 252 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 4 | 4 | 3 | 0 | 88 | 49 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0253 | The system shall record, for certification, flight control interface behaviour case 253 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 3 | 0 | 69 | 50 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 24 | 88
REQ-0254 | The interface shall exchange, without loss, command & telemetry link behaviour case 254 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0255 | The payload shall inhibit release when flight control interface behaviour case 255 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0256 | The subsystem shall complete, within budget, power management behaviour case 256 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0257 | The interface shall exchange, without loss, power management behaviour case 257 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0258 | The payload shall inhibit release when payload release mechanism behaviour case 258 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 36 | 36 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 28 | 88
REQ-0259 | The system shall provide ground control software behaviour case 259 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0260 | The interface shall exchange, without loss, payload release mechanism behaviour case 260 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 55 | 55 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0261 | The system shall provide ground control software behaviour case 261 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0262 | The subsystem shall complete, within budget, payload release mechanism behaviour case 262 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 64 | 64 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 17 | 88
REQ-0263 | The system shall provide command & telemetry link behaviour case 263 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0264 | The system shall provide structural interface behaviour case 264 | Functional | MustShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0265 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 265 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0266 | The interface shall exchange, without loss, payload release mechanism behaviour case 266 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0267 | The interface shall exchange, without loss, power management behaviour case 267 | Interface | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0268 | The system shall provide power management behaviour case 268 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0269 | The subsystem shall complete, within budget, payload release mechanism behaviour case 269 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 1 | 0 | 51 | 51 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0271 | The system shall provide power management behaviour case 271 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0272 | The payload shall inhibit release when power management behaviour case 272 | Safety | MustShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0273 | The interface shall exchange, without loss, power management behaviour case 273 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0274 | The subsystem shall complete, within budget, flight control interface behaviour case 274 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 54 | 54 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 22 | 88
REQ-0275 | The interface shall exchange, without loss, payload release mechanism behaviour case 275 | Interface | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0276 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 276 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0277 | The subsystem shall complete, within budget, power management behaviour case 277 | Performance | MustShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0278 | The system shall record, for certification, flight control interface behaviour case 278 | Regulatory | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 4 | 0 | 70 | 49 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 24 | 88
REQ-0279 | The system shall provide ground control software behaviour case 279 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0280 | The payload shall inhibit release when flight control interface behaviour case 280 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 3 | 0 | 63 | 63 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 18 | 88
REQ-0281 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 281 | Interface | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0282 | The system shall provide ground control software behaviour case 282 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0283 | The subsystem shall complete, within budget, payload release mechanism behaviour case 283 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0284 | The subsystem shall complete, within budget, payload release mechanism behaviour case 284 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 68 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0285 | The subsystem shall complete, within budget, power management behaviour case 285 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0286 | The payload shall inhibit release when navigation & sensor fusion behaviour case 286 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 3 | 3 | 3 | 0 | 88 |  | 3 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0287 | The interface shall exchange, without loss, payload release mechanism behaviour case 287 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 2 | 0 | 69 | 69 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 14 | 88
REQ-0288 | The interface shall exchange, without loss, payload release mechanism behaviour case 288 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0289 | The system shall record, for certification, flight control interface behaviour case 289 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0290 | The system shall record, for certification, structural interface behaviour case 290 | Regulatory | ShouldShip | STRUCT-I | Structural Interface | Safety | Field | 1 | 4 | 4 | 4 | 0 | 88 | 70 | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0291 | The subsystem shall complete, within budget, structural interface behaviour case 291 | Performance | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0292 | The system shall provide navigation & sensor fusion behaviour case 292 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0293 | The interface shall exchange, without loss, ground control software behaviour case 293 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 50 | 50 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 7 | 88
REQ-0294 | The subsystem shall complete, within budget, flight control interface behaviour case 294 | Performance | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0295 | The system shall record, for certification, power management behaviour case 295 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0296 | The subsystem shall complete, within budget, power management behaviour case 296 | Performance | MustShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0297 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 297 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 33 | 33 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 12 | 88
REQ-0298 | The system shall provide payload release mechanism behaviour case 298 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0299 | The system shall provide ground control software behaviour case 299 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0300 | The payload shall inhibit release when flight control interface behaviour case 300 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 2 | 0 | 55 | 55 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0301 | The payload shall inhibit release when structural interface behaviour case 301 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 2 | 2 | 1 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0302 | The interface shall exchange, without loss, power management behaviour case 302 | Interface | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0303 | The subsystem shall complete, within budget, command & telemetry link behaviour case 303 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0304 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 304 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0305 | The interface shall exchange, without loss, diagnostics & logging behaviour case 305 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0306 | The system shall provide flight control interface behaviour case 306 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0307 | The subsystem shall complete, within budget, power management behaviour case 307 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0308 | The system shall record, for certification, flight control interface behaviour case 308 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 4 | 0 | 45 | 33 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 32 | 88
REQ-0309 | The payload shall inhibit release when flight control interface behaviour case 309 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 3 | 1 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0310 | The system shall provide power management behaviour case 310 | Functional | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0311 | The system shall provide ground control software behaviour case 311 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0312 | The system shall record, for certification, payload release mechanism behaviour case 312 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 4 | 4 | 3 | 1 | 88 | 88 | 2 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0313 | The interface shall exchange, without loss, diagnostics & logging behaviour case 313 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 |  | 4 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0314 | The system shall provide command & telemetry link behaviour case 314 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0315 | The payload shall inhibit release when payload release mechanism behaviour case 315 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0316 | The payload shall inhibit release when power management behaviour case 316 | Safety | MustShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0317 | The system shall provide diagnostics & logging behaviour case 317 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0318 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 318 | Interface | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0319 | The interface shall exchange, without loss, ground control software behaviour case 319 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0320 | The system shall provide flight control interface behaviour case 320 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 63 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 18 | 88
REQ-0321 | The payload shall inhibit release when structural interface behaviour case 321 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0322 | The system shall provide structural interface behaviour case 322 | Functional | Nice | STRUCT-I | Structural Interface | Safety | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0323 | The system shall provide ground control software behaviour case 323 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0324 | The system shall provide flight control interface behaviour case 324 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 36 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0325 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 325 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0326 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 326 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0327 | The system shall provide diagnostics & logging behaviour case 327 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0328 | The subsystem shall complete, within budget, ground control software behaviour case 328 | Performance | Nice | GND-CTRL | Ground Control Software | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0329 | The system shall provide power management behaviour case 329 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0331 | The system shall provide ground control software behaviour case 331 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0332 | The payload shall inhibit release when navigation & sensor fusion behaviour case 332 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 4 | 4 | 3 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0333 | The system shall provide navigation & sensor fusion behaviour case 333 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0334 | The system shall provide diagnostics & logging behaviour case 334 | Functional | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0335 | The system shall provide diagnostics & logging behaviour case 335 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0336 | The payload shall inhibit release when payload release mechanism behaviour case 336 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0337 | The subsystem shall complete, within budget, flight control interface behaviour case 337 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 71 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0338 | The system shall provide payload release mechanism behaviour case 338 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 67 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 15 | 88
REQ-0339 | The system shall provide command & telemetry link behaviour case 339 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0340 | The system shall provide flight control interface behaviour case 340 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 42 | 42 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 27 | 88
REQ-0341 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 341 | Interface | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0342 | The subsystem shall complete, within budget, flight control interface behaviour case 342 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0343 | The payload shall inhibit release when power management behaviour case 343 | Safety | MustShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0344 | The system shall provide ground control software behaviour case 344 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0345 | The subsystem shall complete, within budget, payload release mechanism behaviour case 345 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0346 | The system shall provide ground control software behaviour case 346 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0347 | The system shall provide ground control software behaviour case 347 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0348 | The system shall provide payload release mechanism behaviour case 348 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 64 | 64 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 17 | 88
REQ-0349 | The payload shall inhibit release when flight control interface behaviour case 349 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 34 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 31 | 88
REQ-0350 | The payload shall inhibit release when flight control interface behaviour case 350 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 30 | 30 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 33 | 88
REQ-0351 | The system shall provide ground control software behaviour case 351 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0352 | The system shall provide navigation & sensor fusion behaviour case 352 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0353 | The system shall provide flight control interface behaviour case 353 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0354 | The system shall provide ground control software behaviour case 354 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0355 | The interface shall exchange, without loss, diagnostics & logging behaviour case 355 | Interface | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 3 | 3 | 2 | 0 | 69 | 69 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0356 | The payload shall inhibit release when structural interface behaviour case 356 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0357 | The payload shall inhibit release when payload release mechanism behaviour case 357 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0358 | The subsystem shall complete, within budget, command & telemetry link behaviour case 358 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0359 | The payload shall inhibit release when flight control interface behaviour case 359 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 54 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0360 | The payload shall inhibit release when command & telemetry link behaviour case 360 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0361 | The subsystem shall complete, within budget, payload release mechanism behaviour case 361 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 31 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0362 | The subsystem shall complete, within budget, command & telemetry link behaviour case 362 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0363 | The subsystem shall complete, within budget, flight control interface behaviour case 363 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 3 | 3 | 3 | 0 | 65 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0365 | The system shall record, for certification, payload release mechanism behaviour case 365 | Regulatory | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0366 | The system shall provide ground control software behaviour case 366 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0367 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 367 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 54 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 5 | 88
REQ-0368 | The system shall record, for certification, flight control interface behaviour case 368 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 3 | 1 | 63 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0369 | The system shall provide flight control interface behaviour case 369 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0370 | The system shall provide command & telemetry link behaviour case 370 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0371 | The interface shall exchange, without loss, command & telemetry link behaviour case 371 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0372 | The payload shall inhibit release when flight control interface behaviour case 372 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 29 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 33 | 88
REQ-0373 | The system shall provide command & telemetry link behaviour case 373 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0374 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 374 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0375 | The interface shall exchange, without loss, flight control interface behaviour case 375 | Interface | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0376 | The system shall record, for certification, payload release mechanism behaviour case 376 | Regulatory | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 2 | 2 | 2 | 0 | 71 | 44 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 24 | 88
REQ-0377 | The payload shall inhibit release when flight control interface behaviour case 377 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 61 | 57 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0378 | The payload shall inhibit release when power management behaviour case 378 | Safety | MustShip | PWR-MGMT | Power Management | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0379 | The system shall provide structural interface behaviour case 379 | Functional | ShouldShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0380 | The subsystem shall complete, within budget, payload release mechanism behaviour case 380 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 45 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0382 | The payload shall inhibit release when flight control interface behaviour case 382 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 2 | 1 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0383 | The system shall provide ground control software behaviour case 383 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 30 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 11 | 88
REQ-0385 | The subsystem shall complete, within budget, command & telemetry link behaviour case 385 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0386 | The system shall provide navigation & sensor fusion behaviour case 386 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0387 | The system shall provide navigation & sensor fusion behaviour case 387 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0388 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 388 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0389 | The system shall provide ground control software behaviour case 389 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0390 | The interface shall exchange, without loss, command & telemetry link behaviour case 390 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0391 | The system shall provide power management behaviour case 391 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0392 | The system shall record, for certification, flight control interface behaviour case 392 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0393 | The system shall provide payload release mechanism behaviour case 393 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0394 | The system shall record, for certification, navigation & sensor fusion behaviour case 394 | Regulatory | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Field | 1 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0395 | The subsystem shall complete, within budget, power management behaviour case 395 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0396 | The subsystem shall complete, within budget, payload release mechanism behaviour case 396 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 71 | 71 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 12 | 88
REQ-0397 | The system shall provide payload release mechanism behaviour case 397 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 34 | 34 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 28 | 88
REQ-0398 | The subsystem shall complete, within budget, command & telemetry link behaviour case 398 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0399 | The system shall provide diagnostics & logging behaviour case 399 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0400 | The subsystem shall complete, within budget, power management behaviour case 400 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0401 | The interface shall exchange, without loss, payload release mechanism behaviour case 401 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 41 | 41 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 25 | 88
REQ-0402 | The system shall provide ground control software behaviour case 402 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0403 | The system shall provide diagnostics & logging behaviour case 403 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0404 | The system shall record, for certification, power management behaviour case 404 | Regulatory | ShouldShip | PWR-MGMT | Power Management | Mission | Field | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0405 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 405 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0406 | The subsystem shall complete, within budget, payload release mechanism behaviour case 406 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 38 | 38 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 27 | 88
REQ-0407 | The interface shall exchange, without loss, flight control interface behaviour case 407 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 57 | 57 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0408 | The system shall provide navigation & sensor fusion behaviour case 408 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 3 | 1 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0409 | The system shall provide command & telemetry link behaviour case 409 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0410 | The system shall provide command & telemetry link behaviour case 410 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0411 | The interface shall exchange, without loss, command & telemetry link behaviour case 411 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0412 | The system shall record, for certification, payload release mechanism behaviour case 412 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | Field | 1 | 2 | 2 | 2 | 0 | 66 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0413 | The interface shall exchange, without loss, command & telemetry link behaviour case 413 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0414 | The interface shall exchange, without loss, command & telemetry link behaviour case 414 | Interface | Nice | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0415 | The interface shall exchange, without loss, structural interface behaviour case 415 | Interface | MustShip | STRUCT-I | Structural Interface | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0416 | The payload shall inhibit release when command & telemetry link behaviour case 416 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 3 | 3 | 2 | 1 | 38 | 30 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 14 | 88
REQ-0417 | The system shall record, for certification, flight control interface behaviour case 417 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 3 | 3 | 3 | 0 | 68 | 54 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0418 | The system shall provide diagnostics & logging behaviour case 418 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0419 | The interface shall exchange, without loss, diagnostics & logging behaviour case 419 | Interface | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0420 | The interface shall exchange, without loss, power management behaviour case 420 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0421 | The payload shall inhibit release when navigation & sensor fusion behaviour case 421 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0423 | The payload shall inhibit release when flight control interface behaviour case 423 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0424 | The payload shall inhibit release when structural interface behaviour case 424 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0425 | The subsystem shall complete, within budget, command & telemetry link behaviour case 425 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 2 | 2 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0426 | The system shall record, for certification, structural interface behaviour case 426 | Regulatory | MustShip | STRUCT-I | Structural Interface | Safety | Field | 1 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0427 | The payload shall inhibit release when flight control interface behaviour case 427 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 45 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0428 | The interface shall exchange, without loss, ground control software behaviour case 428 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0429 | The payload shall inhibit release when payload release mechanism behaviour case 429 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 41 | 41 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 25 | 88
REQ-0431 | The subsystem shall complete, within budget, command & telemetry link behaviour case 431 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 3 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0432 | The system shall provide diagnostics & logging behaviour case 432 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0433 | The interface shall exchange, without loss, power management behaviour case 433 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 |  | 3 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0434 | The payload shall inhibit release when structural interface behaviour case 434 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 88 | 60 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 2 | 88
REQ-0435 | The system shall record, for certification, power management behaviour case 435 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 1 | 1 | 1 | 0 | 42 | 42 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 4 | 88
REQ-0436 | The interface shall exchange, without loss, power management behaviour case 436 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0437 | The subsystem shall complete, within budget, power management behaviour case 437 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0438 | The system shall provide flight control interface behaviour case 438 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0439 | The payload shall inhibit release when payload release mechanism behaviour case 439 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 2 | 1 | 53 | 51 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 22 | 88
REQ-0440 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 440 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0441 | The system shall provide power management behaviour case 441 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0442 | The payload shall inhibit release when payload release mechanism behaviour case 442 | Safety | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0443 | The system shall provide command & telemetry link behaviour case 443 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 41 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 10 | 88
REQ-0444 | The payload shall inhibit release when navigation & sensor fusion behaviour case 444 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0445 | The system shall provide power management behaviour case 445 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0446 | The interface shall exchange, without loss, payload release mechanism behaviour case 446 | Interface | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 39 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0447 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 447 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0448 | The subsystem shall complete, within budget, power management behaviour case 448 | Performance | Nice | PWR-MGMT | Power Management | Mission | HIL | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0449 | The payload shall inhibit release when payload release mechanism behaviour case 449 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 2 | 2 | 0 | 2 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0450 | The system shall provide diagnostics & logging behaviour case 450 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0451 | The system shall provide diagnostics & logging behaviour case 451 | Functional | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0452 | The system shall record, for certification, power management behaviour case 452 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 3 | 3 | 2 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0453 | The system shall provide power management behaviour case 453 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 32 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 4 | 88
REQ-0454 | The interface shall exchange, without loss, payload release mechanism behaviour case 454 | Interface | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 34 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 28 | 88
REQ-0455 | The subsystem shall complete, within budget, command & telemetry link behaviour case 455 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0456 | The subsystem shall complete, within budget, command & telemetry link behaviour case 456 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0457 | The system shall record, for certification, power management behaviour case 457 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0458 | The system shall provide navigation & sensor fusion behaviour case 458 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0459 | The system shall provide power management behaviour case 459 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0460 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 460 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0461 | The system shall provide power management behaviour case 461 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0462 | The subsystem shall complete, within budget, command & telemetry link behaviour case 462 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 65 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0463 | The payload shall inhibit release when flight control interface behaviour case 463 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 4 | 4 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0464 | The system shall record, for certification, power management behaviour case 464 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | Field | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0465 | The system shall provide navigation & sensor fusion behaviour case 465 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0466 | The system shall provide payload release mechanism behaviour case 466 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0467 | The system shall record, for certification, flight control interface behaviour case 467 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | Field | 1 | 4 | 4 | 4 | 0 | 88 | 34 | 3 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 31 | 88
REQ-0468 | The system shall provide ground control software behaviour case 468 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0469 | The payload shall inhibit release when payload release mechanism behaviour case 469 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 30 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0470 | The interface shall exchange, without loss, power management behaviour case 470 | Interface | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0471 | The system shall provide command & telemetry link behaviour case 471 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0472 | The payload shall inhibit release when flight control interface behaviour case 472 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 32 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 33 | 88
REQ-0473 | The system shall provide payload release mechanism behaviour case 473 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 59 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0474 | The interface shall exchange, without loss, diagnostics & logging behaviour case 474 | Interface | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0475 | The subsystem shall complete, within budget, payload release mechanism behaviour case 475 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0476 | The system shall provide power management behaviour case 476 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0477 | The system shall provide ground control software behaviour case 477 | Functional | Nice | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0478 | The subsystem shall complete, within budget, flight control interface behaviour case 478 | Performance | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 2 | 2 | 2 | 0 | 64 | 64 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 18 | 88
REQ-0479 | The interface shall exchange, without loss, command & telemetry link behaviour case 479 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0480 | The system shall provide power management behaviour case 480 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0481 | The system shall provide payload release mechanism behaviour case 481 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0482 | The interface shall exchange, without loss, ground control software behaviour case 482 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 31 | 31 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 10 | 88
REQ-0483 | The system shall provide command & telemetry link behaviour case 483 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0484 | The interface shall exchange, without loss, diagnostics & logging behaviour case 484 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0485 | The subsystem shall complete, within budget, flight control interface behaviour case 485 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0486 | The interface shall exchange, without loss, power management behaviour case 486 | Interface | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0487 | The subsystem shall complete, within budget, ground control software behaviour case 487 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | HIL | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0488 | The payload shall inhibit release when payload release mechanism behaviour case 488 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 57 |  | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0489 | The system shall provide navigation & sensor fusion behaviour case 489 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0490 | The system shall provide navigation & sensor fusion behaviour case 490 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0491 | The system shall provide diagnostics & logging behaviour case 491 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0492 | The system shall provide ground control software behaviour case 492 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0493 | The payload shall inhibit release when payload release mechanism behaviour case 493 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0494 | The system shall provide power management behaviour case 494 | Functional | MustShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0495 | The system shall provide payload release mechanism behaviour case 495 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 71 | 71 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 12 | 88
REQ-0496 | The payload shall inhibit release when navigation & sensor fusion behaviour case 496 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 39 | 1 | 2 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 12 | 88
REQ-0497 | The interface shall exchange, without loss, payload release mechanism behaviour case 497 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 2 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0498 | The interface shall exchange, without loss, command & telemetry link behaviour case 498 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0499 | The system shall provide payload release mechanism behaviour case 499 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0500 | The system shall provide navigation & sensor fusion behaviour case 500 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0501 | The subsystem shall complete, within budget, flight control interface behaviour case 501 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 3 | 3 | 3 | 0 | 71 | 36 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 30 | 88
REQ-0502 | The subsystem shall complete, within budget, payload release mechanism behaviour case 502 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 28 | 28 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 29 | 88
REQ-0503 | The system shall record, for certification, structural interface behaviour case 503 | Regulatory | MustShip | STRUCT-I | Structural Interface | Safety | Field | 1 | 2 | 2 | 1 | 1 | 36 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0504 | The system shall provide command & telemetry link behaviour case 504 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0505 | The system shall provide flight control interface behaviour case 505 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 1 | 1 | 1 | 0 | 30 | 30 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 33 | 88
REQ-0506 | The interface shall exchange, without loss, command & telemetry link behaviour case 506 | Interface | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0507 | The interface shall exchange, without loss, ground control software behaviour case 507 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0508 | The system shall provide diagnostics & logging behaviour case 508 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 |  | 4 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0509 | The system shall provide power management behaviour case 509 | Functional | Nice | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0510 | The interface shall exchange, without loss, ground control software behaviour case 510 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 2 | 2 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0511 | The interface shall exchange, without loss, power management behaviour case 511 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0512 | The system shall provide diagnostics & logging behaviour case 512 | Functional | Nice | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0514 | The payload shall inhibit release when flight control interface behaviour case 514 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 2 | 2 | 2 | 0 | 56 |  | 2 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0515 | The payload shall inhibit release when payload release mechanism behaviour case 515 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 4 | 4 | 3 | 1 | 49 | 35 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 28 | 88
REQ-0516 | The system shall provide ground control software behaviour case 516 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0517 | The subsystem shall complete, within budget, payload release mechanism behaviour case 517 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | HIL | 0 | 1 | 1 | 0 | 1 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0518 | The system shall provide payload release mechanism behaviour case 518 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | Integration | 0 | 1 | 1 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No evidence | 0 | 88
REQ-0519 | The system shall provide ground control software behaviour case 519 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0520 | The system shall provide navigation & sensor fusion behaviour case 520 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 3 | 3 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0521 | The payload shall inhibit release when payload release mechanism behaviour case 521 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 4 | 4 | 4 | 0 | 88 |  | 4 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0522 | The subsystem shall complete, within budget, flight control interface behaviour case 522 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 0 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0523 | The payload shall inhibit release when payload release mechanism behaviour case 523 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | HIL | 1 | 3 | 3 | 3 | 0 | 88 | 88 | 0 | 1 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0524 | The system shall provide navigation & sensor fusion behaviour case 524 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0525 | The interface shall exchange, without loss, command & telemetry link behaviour case 525 | Interface | Nice | COMM-LNK | Command & Telemetry Link | Mission | Integration | 0 | 3 | 3 | 1 | 1 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0526 | The system shall provide diagnostics & logging behaviour case 526 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0527 | The system shall provide ground control software behaviour case 527 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0528 | The payload shall inhibit release when flight control interface behaviour case 528 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 3 | 3 | 2 | 1 | 59 | 44 | 1 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 26 | 88
REQ-0529 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 529 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 1 | 1 | 1 | 0 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0530 | The interface shall exchange, without loss, diagnostics & logging behaviour case 530 | Interface | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0531 | The payload shall inhibit release when flight control interface behaviour case 531 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | HIL | 1 | 1 | 1 | 1 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0532 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 532 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | HIL | 0 | 3 | 3 | 1 | 2 | 88 |  | 1 | 0 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0533 | The system shall provide navigation & sensor fusion behaviour case 533 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | Integration | 0 | 2 | 2 | 2 | 0 | 88 | 88 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0534 | The system shall provide power management behaviour case 534 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 88 | 1 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0537 | The payload shall inhibit release when command & telemetry link behaviour case 537 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | HIL | 1 | 1 | 1 | 1 | 0 | 88 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | Insufficient evidence | 0 | 88
REQ-0538 | The system shall provide diagnostics & logging behaviour case 538 | Functional | MustShip | DIAG-LOG | Diagnostics & Logging | Support | Integration | 0 | 4 | 4 | 4 | 0 | 88 | 88 | 2 | 0 | 1 | 1 | 0 | 0 | 1 | Current | 0 | 88
REQ-0539 | The interface shall exchange, without loss, ground control software behaviour case 539 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | Integration | 0 | 3 | 3 | 3 | 0 | 88 | 29 | 2 | 0 | 1 | 1 | 1 | 0 | 0 | Stale - subsystem changed | 11 | 88
REQ-0540 | The system shall provide flight control interface behaviour case 540 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | Integration | 0 | 3 | 3 | 2 | 0 | 71 | 65 | 1 | 0 | 1 | 1 | 1 | 1 | 0 | Stale - requirement changed | 17 | 88

## Data_Queue
PriorityRank | RequirementID | Title | ReqType | Priority | SubsystemCode | SubsystemName | Criticality | OwnerID | OwnerName | OwnerTeam | MinTestLevel | LastGoodBuild | InterveningBuilds | Cases | RigHours | AirframeHours | TestMinutes | CumulativeRigHours | PriorityScore | ActionCode | NeedsNewCase | IsThisWeek | RecommendedAction
1 | REQ-0287 | The interface shall exchange, without loss, payload release mechanism behaviour case 287 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | Integration | 69 | 14 | 3 | 2.5 | 0 | 292 | 2.5 | 92 | REVIEW_THEN_RERUN | 0 | 1 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
2 | REQ-0397 | The system shall provide payload release mechanism behaviour case 397 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-007 | Grace Baptiste | Integration & Test | Integration | 34 | 28 | 1 | 2.5 | 0 | 33 | 5 | 92 | REVIEW_THEN_RERUN | 0 | 1 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
3 | REQ-0253 | The system shall record, for certification, flight control interface behaviour case 253 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | Field | 50 | 24 | 4 | 0 | 24 | 443 | 5 | 92 | REVIEW_THEN_RERUN | 0 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
4 | REQ-0211 | The interface shall exchange, without loss, payload release mechanism behaviour case 211 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-021 | Ulrike Dalgleish | Avionics | Integration |  | 0 | 2 | 0 | 0 | 103 | 5 | 90 | VERIFY | 0 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
5 | REQ-0266 | The interface shall exchange, without loss, payload release mechanism behaviour case 266 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-001 | Aditi Halvorsen | Avionics | Integration |  | 0 | 1 | 0 | 0 | 195 | 5 | 90 | VERIFY | 1 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
6 | REQ-0449 | The payload shall inhibit release when payload release mechanism behaviour case 449 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-011 | Katya Fairweather | Integration & Test | HIL |  | 0 | 2 | 5 | 0 | 100 | 10 | 90 | VERIFY | 0 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
7 | REQ-0176 | The system shall record, for certification, payload release mechanism behaviour case 176 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-008 | Hiroshi Ibarra | Payload | Field |  | 0 | 1 | 0 | 8 | 187 | 10 | 90 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
8 | REQ-0085 | The interface shall exchange, without loss, payload release mechanism behaviour case 85 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | Integration | 59 | 21 | 3 | 0 | 0 | 464 | 10 | 88 | RERUN | 0 | 1 | Evidence was valid at build 59 but the subsystem has changed in 21 builds since. Re-run on the release candidate.
9 | REQ-0260 | The interface shall exchange, without loss, payload release mechanism behaviour case 260 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-017 | Quentin Zielinski | Avionics | Integration | 55 | 22 | 1 | 0 | 0 | 115 | 10 | 88 | RERUN | 0 | 1 | Evidence was valid at build 55 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
10 | REQ-0338 | The system shall provide payload release mechanism behaviour case 338 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-005 | Elena Lindqvist | Avionics | Integration | 67 | 15 | 2 | 0 | 0 | 260 | 10 | 88 | RERUN | 0 | 1 | Evidence was valid at build 67 but the subsystem has changed in 15 builds since. Re-run on the release candidate.
11 | REQ-0340 | The system shall provide flight control interface behaviour case 340 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-006 | Farid Saltzman | Ground Segment | Integration | 42 | 27 | 3 | 0 | 0 | 566 | 10 | 88 | RERUN | 0 | 1 | Evidence was valid at build 42 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
12 | REQ-0401 | The interface shall exchange, without loss, payload release mechanism behaviour case 401 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-016 | Priya Quintana | Payload | Integration | 41 | 25 | 1 | 0 | 0 | 105 | 10 | 88 | RERUN | 0 | 1 | Evidence was valid at build 41 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
13 | REQ-0036 | The system shall provide flight control interface behaviour case 36 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-005 | Elena Lindqvist | Avionics | Integration | 66 | 16 | 2 | 2.5 | 0 | 189 | 12.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 66 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
14 | REQ-0157 | The payload shall inhibit release when payload release mechanism behaviour case 157 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-001 | Aditi Halvorsen | Avionics | HIL | 68 | 14 | 4 | 2.5 | 0 | 325 | 15 | 88 | RERUN | 0 | 1 | Evidence was valid at build 68 but the subsystem has changed in 14 builds since. Re-run on the release candidate.
15 | REQ-0217 | The payload shall inhibit release when payload release mechanism behaviour case 217 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | HIL | 40 | 25 | 1 | 2.5 | 0 | 96 | 17.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 40 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
16 | REQ-0225 | The payload shall inhibit release when flight control interface behaviour case 225 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | HIL | 51 | 23 | 1 | 2.5 | 0 | 32 | 20 | 88 | RERUN | 0 | 1 | Evidence was valid at build 51 but the subsystem has changed in 23 builds since. Re-run on the release candidate.
17 | REQ-0252 | The payload shall inhibit release when payload release mechanism behaviour case 252 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-004 | Dmitri Eriksen | Payload | HIL | 49 | 22 | 4 | 2.5 | 0 | 384 | 22.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 49 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
18 | REQ-0350 | The payload shall inhibit release when flight control interface behaviour case 350 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | HIL | 30 | 33 | 1 | 2.5 | 0 | 104 | 25 | 88 | RERUN | 0 | 1 | Evidence was valid at build 30 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
19 | REQ-0359 | The payload shall inhibit release when flight control interface behaviour case 359 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-005 | Elena Lindqvist | Avionics | HIL | 54 | 22 | 4 | 2.5 | 0 | 335 | 27.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 54 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
20 | REQ-0372 | The payload shall inhibit release when flight control interface behaviour case 372 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | HIL | 29 | 33 | 4 | 2.5 | 0 | 259 | 30 | 88 | RERUN | 0 | 1 | Evidence was valid at build 29 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
21 | REQ-0429 | The payload shall inhibit release when payload release mechanism behaviour case 429 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-019 | Sana Nakamura | Integration & Test | HIL | 41 | 25 | 1 | 2.5 | 0 | 147 | 32.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 41 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
22 | REQ-0472 | The payload shall inhibit release when flight control interface behaviour case 472 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-016 | Priya Quintana | Payload | HIL | 32 | 33 | 3 | 2.5 | 0 | 247 | 35 | 88 | RERUN | 0 | 1 | Evidence was valid at build 32 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
23 | REQ-0478 | The subsystem shall complete, within budget, flight control interface behaviour case 478 | Performance | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-014 | Nils Castellan | Ground Segment | HIL | 64 | 18 | 2 | 2.5 | 0 | 342 | 37.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 64 but the subsystem has changed in 18 builds since. Re-run on the release candidate.
24 | REQ-0060 | The payload shall inhibit release when flight control interface behaviour case 60 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-018 | Rafael Grigorescu | Ground Segment | HIL | 53 | 22 | 3 | 5 | 0 | 518 | 42.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 53 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
25 | REQ-0069 | The payload shall inhibit release when flight control interface behaviour case 69 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | HIL | 59 | 21 | 4 | 5 | 0 | 331 | 47.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 59 but the subsystem has changed in 21 builds since. Re-run on the release candidate.
26 | REQ-0106 | The payload shall inhibit release when flight control interface behaviour case 106 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | HIL | 42 | 27 | 2 | 5 | 0 | 355 | 52.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 42 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
27 | REQ-0165 | The system shall provide payload release mechanism behaviour case 165 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-018 | Rafael Grigorescu | Ground Segment | Integration | 71 | 12 | 4 | 5 | 0 | 544 | 57.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 71 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
28 | REQ-0166 | The payload shall inhibit release when payload release mechanism behaviour case 166 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-005 | Elena Lindqvist | Avionics | HIL | 54 | 22 | 3 | 5 | 0 | 237 | 62.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 54 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
29 | REQ-0167 | The payload shall inhibit release when payload release mechanism behaviour case 167 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-011 | Katya Fairweather | Integration & Test | HIL | 65 | 16 | 2 | 5 | 0 | 159 | 67.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 65 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
30 | REQ-0191 | The payload shall inhibit release when payload release mechanism behaviour case 191 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | HIL | 65 | 16 | 3 | 5 | 0 | 313 | 72.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 65 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
31 | REQ-0258 | The payload shall inhibit release when payload release mechanism behaviour case 258 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-020 | Tomas Ustinov | Payload | HIL | 36 | 28 | 2 | 5 | 0 | 327 | 77.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 36 but the subsystem has changed in 28 builds since. Re-run on the release candidate.
32 | REQ-0269 | The subsystem shall complete, within budget, payload release mechanism behaviour case 269 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | HIL | 51 | 22 | 2 | 5 | 0 | 240 | 82.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 51 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
33 | REQ-0300 | The payload shall inhibit release when flight control interface behaviour case 300 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-015 | Olabisi Jindal | Integration & Test | HIL | 55 | 22 | 3 | 5 | 0 | 450 | 87.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 55 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
34 | REQ-0439 | The payload shall inhibit release when payload release mechanism behaviour case 439 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-017 | Quentin Zielinski | Avionics | HIL | 51 | 22 | 3 | 5 | 0 | 199 | 92.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 51 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
35 | REQ-0528 | The payload shall inhibit release when flight control interface behaviour case 528 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | HIL | 44 | 26 | 3 | 5 | 0 | 591 | 97.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 44 but the subsystem has changed in 26 builds since. Re-run on the release candidate.
36 | REQ-0280 | The payload shall inhibit release when flight control interface behaviour case 280 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | HIL | 63 | 18 | 4 | 7.5 | 0 | 327 | 105 | 88 | RERUN | 0 | 1 | Evidence was valid at build 63 but the subsystem has changed in 18 builds since. Re-run on the release candidate.
37 | REQ-0349 | The payload shall inhibit release when flight control interface behaviour case 349 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-017 | Quentin Zielinski | Avionics | HIL | 34 | 31 | 4 | 7.5 | 0 | 432 | 112.5 | 88 | RERUN | 0 | 1 | Evidence was valid at build 34 but the subsystem has changed in 31 builds since. Re-run on the release candidate.
38 | REQ-0515 | The payload shall inhibit release when payload release mechanism behaviour case 515 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-020 | Tomas Ustinov | Payload | HIL | 35 | 28 | 4 | 7.5 | 0 | 617 | 120 | 88 | RERUN | 0 | 1 | Evidence was valid at build 35 but the subsystem has changed in 28 builds since. Re-run on the release candidate.
39 | REQ-0034 | The system shall record, for certification, flight control interface behaviour case 34 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-018 | Rafael Grigorescu | Ground Segment | Field | 69 | 14 | 3 | 0 | 8 | 96 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 69 but the subsystem has changed in 14 builds since. Re-run on the release candidate.
40 | REQ-0187 | The system shall record, for certification, flight control interface behaviour case 187 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-003 | Camille Villalobos | Integration & Test | Field | 55 | 22 | 1 | 0 | 8 | 66 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 55 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
41 | REQ-0198 | The system shall record, for certification, payload release mechanism behaviour case 198 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-018 | Rafael Grigorescu | Ground Segment | Field | 60 | 20 | 4 | 0 | 8 | 442 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 60 but the subsystem has changed in 20 builds since. Re-run on the release candidate.
42 | REQ-0417 | The system shall record, for certification, flight control interface behaviour case 417 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | Field | 54 | 22 | 3 | 0 | 8 | 524 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 54 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
43 | REQ-0467 | The system shall record, for certification, flight control interface behaviour case 467 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-008 | Hiroshi Ibarra | Payload | Field | 34 | 31 | 4 | 0 | 8 | 469 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 34 but the subsystem has changed in 31 builds since. Re-run on the release candidate.
44 | REQ-0113 | The system shall record, for certification, payload release mechanism behaviour case 113 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | Field | 31 | 29 | 3 | 0 | 16 | 400 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 31 but the subsystem has changed in 29 builds since. Re-run on the release candidate.
45 | REQ-0154 | The system shall record, for certification, payload release mechanism behaviour case 154 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | Field | 65 | 16 | 4 | 0 | 16 | 308 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 65 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
46 | REQ-0235 | The system shall record, for certification, flight control interface behaviour case 235 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-011 | Katya Fairweather | Integration & Test | Field | 37 | 29 | 3 | 0 | 16 | 385 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 37 but the subsystem has changed in 29 builds since. Re-run on the release candidate.
47 | REQ-0308 | The system shall record, for certification, flight control interface behaviour case 308 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-005 | Elena Lindqvist | Avionics | Field | 33 | 32 | 4 | 0 | 16 | 501 | 120 | 88 | RERUN | 0 | 0 | Evidence was valid at build 33 but the subsystem has changed in 32 builds since. Re-run on the release candidate.
48 | REQ-0118 | The system shall provide payload release mechanism behaviour case 118 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-006 | Farid Saltzman | Ground Segment | Integration |  | 0 | 2 | 0 | 0 | 209 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
49 | REQ-0137 | The system shall provide structural interface behaviour case 137 | Functional | MustShip | STRUCT-I | Structural Interface | Safety | P-009 | Imani Petrovic | Avionics | Integration |  | 0 | 1 | 0 | 0 | 32 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
50 | REQ-0141 | The interface shall exchange, without loss, payload release mechanism behaviour case 141 | Interface | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-007 | Grace Baptiste | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 150 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
51 | REQ-0178 | The system shall provide flight control interface behaviour case 178 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-020 | Tomas Ustinov | Payload | Integration |  | 0 | 1 | 0 | 0 | 143 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
52 | REQ-0208 | The interface shall exchange, without loss, flight control interface behaviour case 208 | Interface | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 2 | 0 | 0 | 103 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
53 | REQ-0306 | The system shall provide flight control interface behaviour case 306 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 1 | 0 | 0 | 16 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
54 | REQ-0324 | The system shall provide flight control interface behaviour case 324 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | Integration |  | 0 | 1 | 0 | 0 | 26 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
55 | REQ-0438 | The system shall provide flight control interface behaviour case 438 | Functional | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-020 | Tomas Ustinov | Payload | Integration |  | 0 | 1 | 0 | 0 | 161 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
56 | REQ-0473 | The system shall provide payload release mechanism behaviour case 473 | Functional | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-006 | Farid Saltzman | Ground Segment | Integration |  | 0 | 1 | 0 | 0 | 93 | 120 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
57 | REQ-0026 | The payload shall inhibit release when payload release mechanism behaviour case 26 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-008 | Hiroshi Ibarra | Payload | HIL |  | 0 | 2 | 2.5 | 0 | 289 | 122.5 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
58 | REQ-0035 | The payload shall inhibit release when flight control interface behaviour case 35 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 155 | 125 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
59 | REQ-0043 | The payload shall inhibit release when flight control interface behaviour case 43 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | HIL |  | 0 | 1 | 2.5 | 0 | 201 | 127.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
60 | REQ-0053 | The payload shall inhibit release when payload release mechanism behaviour case 53 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | HIL |  | 0 | 3 | 2.5 | 0 | 431 | 130 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
61 | REQ-0080 | The payload shall inhibit release when flight control interface behaviour case 80 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-011 | Katya Fairweather | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 156 | 132.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
62 | REQ-0109 | The payload shall inhibit release when payload release mechanism behaviour case 109 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-016 | Priya Quintana | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 180 | 135 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
63 | REQ-0149 | The payload shall inhibit release when payload release mechanism behaviour case 149 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 205 | 137.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
64 | REQ-0169 | The subsystem shall complete, within budget, payload release mechanism behaviour case 169 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-015 | Olabisi Jindal | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 291 | 140 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
65 | REQ-0181 | The payload shall inhibit release when payload release mechanism behaviour case 181 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-005 | Elena Lindqvist | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 187 | 142.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
66 | REQ-0189 | The payload shall inhibit release when flight control interface behaviour case 189 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-002 | Bruno Oyelaran | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 121 | 145 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
67 | REQ-0301 | The payload shall inhibit release when structural interface behaviour case 301 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | P-006 | Farid Saltzman | Ground Segment | HIL |  | 0 | 2 | 2.5 | 0 | 56 | 147.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
68 | REQ-0336 | The payload shall inhibit release when payload release mechanism behaviour case 336 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | HIL |  | 0 | 2 | 2.5 | 0 | 122 | 150 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
69 | REQ-0382 | The payload shall inhibit release when flight control interface behaviour case 382 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | HIL |  | 0 | 3 | 2.5 | 0 | 338 | 152.5 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
70 | REQ-0427 | The payload shall inhibit release when flight control interface behaviour case 427 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | HIL |  | 0 | 2 | 2.5 | 0 | 265 | 155 | 86 | RAISE_TEST_LEVEL | 0 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
71 | REQ-0469 | The payload shall inhibit release when payload release mechanism behaviour case 469 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-008 | Hiroshi Ibarra | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 193 | 157.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
72 | REQ-0475 | The subsystem shall complete, within budget, payload release mechanism behaviour case 475 | Performance | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-008 | Hiroshi Ibarra | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 67 | 160 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
73 | REQ-0488 | The payload shall inhibit release when payload release mechanism behaviour case 488 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-017 | Quentin Zielinski | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 34 | 162.5 | 86 | INDEPENDENT_WITNESS | 0 | 1 | Verified by its own owner at build 57, and the subsystem or the requirement has changed since. Re-run it on the release candidate witnessed by a second engineer; a countersignature now would certify superseded evidence.
74 | REQ-0493 | The payload shall inhibit release when payload release mechanism behaviour case 493 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 37 | 165 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
75 | REQ-0514 | The payload shall inhibit release when flight control interface behaviour case 514 | Safety | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 263 | 167.5 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
76 | REQ-0521 | The payload shall inhibit release when payload release mechanism behaviour case 521 | Safety | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | HIL |  | 0 | 4 | 2.5 | 0 | 523 | 170 | 86 | RAISE_TEST_LEVEL | 1 | 1 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
77 | REQ-0089 | The system shall record, for certification, payload release mechanism behaviour case 89 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-011 | Katya Fairweather | Integration & Test | Field |  | 0 | 4 | 0 | 8 | 436 | 170 | 86 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
78 | REQ-0368 | The system shall record, for certification, flight control interface behaviour case 368 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-009 | Imani Petrovic | Avionics | Field |  | 0 | 4 | 0 | 8 | 630 | 170 | 86 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
79 | REQ-0392 | The system shall record, for certification, flight control interface behaviour case 392 | Regulatory | MustShip | FLT-CTRL | Flight Control Interface | Safety | P-003 | Camille Villalobos | Integration & Test | Field |  | 0 | 2 | 0 | 8 | 300 | 170 | 86 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
80 | REQ-0412 | The system shall record, for certification, payload release mechanism behaviour case 412 | Regulatory | MustShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | Field |  | 0 | 2 | 0 | 8 | 152 | 170 | 86 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
81 | REQ-0503 | The system shall record, for certification, structural interface behaviour case 503 | Regulatory | MustShip | STRUCT-I | Structural Interface | Safety | P-012 | Liam Moreau | Payload | Field |  | 0 | 2 | 0 | 8 | 263 | 170 | 86 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the airframe -- a flight slot, not rig time.
82 | REQ-0014 | The payload shall inhibit release when structural interface behaviour case 14 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | P-019 | Sana Nakamura | Integration & Test | HIL | 28 | 10 | 1 | 2.5 | 0 | 169 | 172.5 | 84 | RERUN | 0 | 1 | Evidence was valid at build 28 but the subsystem has changed in 10 builds since. Re-run on the release candidate.
83 | REQ-0092 | The payload shall inhibit release when structural interface behaviour case 92 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | P-014 | Nils Castellan | Ground Segment | HIL | 31 | 9 | 2 | 5 | 0 | 302 | 177.5 | 84 | RERUN | 0 | 1 | Evidence was valid at build 31 but the subsystem has changed in 9 builds since. Re-run on the release candidate.
84 | REQ-0434 | The payload shall inhibit release when structural interface behaviour case 434 | Safety | MustShip | STRUCT-I | Structural Interface | Safety | P-005 | Elena Lindqvist | Avionics | HIL | 60 | 2 | 2 | 2.5 | 0 | 136 | 180 | 81 | RERUN | 0 | 1 | Evidence was valid at build 60 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
85 | REQ-0099 | The system shall provide command & telemetry link behaviour case 99 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-012 | Liam Moreau | Payload | Integration |  | 0 | 1 | 0 | 0 | 203 | 180 | 79 | VERIFY | 1 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
86 | REQ-0249 | The subsystem shall complete, within budget, command & telemetry link behaviour case 249 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-008 | Hiroshi Ibarra | Payload | HIL |  | 0 | 2 | 2.5 | 0 | 349 | 182.5 | 79 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
87 | REQ-0398 | The subsystem shall complete, within budget, command & telemetry link behaviour case 398 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 114 | 185 | 79 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
88 | REQ-0444 | The payload shall inhibit release when navigation & sensor fusion behaviour case 444 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-007 | Grace Baptiste | Integration & Test | HIL |  | 0 | 1 | 2.5 | 0 | 123 | 187.5 | 79 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
89 | REQ-0027 | The payload shall inhibit release when command & telemetry link behaviour case 27 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-020 | Tomas Ustinov | Payload | HIL | 33 | 13 | 4 | 2.5 | 0 | 449 | 190 | 77 | RERUN | 0 | 0 | Evidence was valid at build 33 but the subsystem has changed in 13 builds since. Re-run on the release candidate.
90 | REQ-0416 | The payload shall inhibit release when command & telemetry link behaviour case 416 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-017 | Quentin Zielinski | Avionics | HIL | 30 | 14 | 3 | 5 | 0 | 522 | 195 | 77 | RERUN | 0 | 0 | Evidence was valid at build 30 but the subsystem has changed in 14 builds since. Re-run on the release candidate.
91 | REQ-0496 | The payload shall inhibit release when navigation & sensor fusion behaviour case 496 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-012 | Liam Moreau | Payload | HIL | 39 | 12 | 3 | 5 | 0 | 158 | 200 | 77 | RERUN | 0 | 0 | Evidence was valid at build 39 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
92 | REQ-0008 | The system shall provide command & telemetry link behaviour case 8 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-015 | Olabisi Jindal | Integration & Test | Integration |  | 0 | 3 | 0 | 0 | 297 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
93 | REQ-0124 | The payload shall inhibit release when power management behaviour case 124 | Safety | MustShip | PWR-MGMT | Power Management | Mission | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 1 | 0 | 0 | 61 | 200 | 75 | INDEPENDENT_WITNESS | 0 | 0 | Verified by its own owner against a policy requiring independence. Nothing has changed since that pass, so a second engineer reviews and countersigns it; no re-execution and no rig time.
94 | REQ-0155 | The system shall provide power management behaviour case 155 | Functional | MustShip | PWR-MGMT | Power Management | Mission | P-021 | Ulrike Dalgleish | Avionics | Integration |  | 0 | 1 | 0 | 0 | 207 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
95 | REQ-0218 | The interface shall exchange, without loss, power management behaviour case 218 | Interface | MustShip | PWR-MGMT | Power Management | Mission | P-002 | Bruno Oyelaran | Ground Segment | Integration |  | 0 | 1 | 0 | 0 | 51 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
96 | REQ-0433 | The interface shall exchange, without loss, power management behaviour case 433 | Interface | MustShip | PWR-MGMT | Power Management | Mission | P-015 | Olabisi Jindal | Integration & Test | Integration |  | 0 | 3 | 0 | 0 | 330 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
97 | REQ-0459 | The system shall provide power management behaviour case 459 | Functional | MustShip | PWR-MGMT | Power Management | Mission | P-018 | Rafael Grigorescu | Ground Segment | Integration |  | 0 | 2 | 0 | 0 | 173 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
98 | REQ-0486 | The interface shall exchange, without loss, power management behaviour case 486 | Interface | MustShip | PWR-MGMT | Power Management | Mission | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 2 | 0 | 0 | 212 | 200 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
99 | REQ-0028 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 28 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-002 | Bruno Oyelaran | Ground Segment | HIL |  | 0 | 2 | 2.5 | 0 | 231 | 202.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
100 | REQ-0049 | The subsystem shall complete, within budget, command & telemetry link behaviour case 49 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-004 | Dmitri Eriksen | Payload | HIL |  | 0 | 4 | 2.5 | 0 | 409 | 205 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
101 | REQ-0122 | The payload shall inhibit release when command & telemetry link behaviour case 122 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-001 | Aditi Halvorsen | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 194 | 207.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
102 | REQ-0172 | The payload shall inhibit release when navigation & sensor fusion behaviour case 172 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-009 | Imani Petrovic | Avionics | HIL |  | 0 | 3 | 2.5 | 0 | 394 | 210 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
103 | REQ-0196 | The payload shall inhibit release when command & telemetry link behaviour case 196 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-017 | Quentin Zielinski | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 224 | 212.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
104 | REQ-0197 | The system shall provide navigation & sensor fusion behaviour case 197 | Functional | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-010 | Jonas Weatherby | Ground Segment | Integration |  | 0 | 4 | 2.5 | 0 | 757 | 215 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
105 | REQ-0233 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 233 | Interface | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-010 | Jonas Weatherby | Ground Segment | Integration |  | 0 | 3 | 2.5 | 0 | 250 | 217.5 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
106 | REQ-0247 | The subsystem shall complete, within budget, command & telemetry link behaviour case 247 | Performance | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-016 | Priya Quintana | Payload | HIL |  | 0 | 3 | 2.5 | 0 | 239 | 220 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
107 | REQ-0272 | The payload shall inhibit release when power management behaviour case 272 | Safety | MustShip | PWR-MGMT | Power Management | Mission | P-020 | Tomas Ustinov | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 22 | 222.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
108 | REQ-0286 | The payload shall inhibit release when navigation & sensor fusion behaviour case 286 | Safety | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 3 | 2.5 | 0 | 474 | 225 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
109 | REQ-0316 | The payload shall inhibit release when power management behaviour case 316 | Safety | MustShip | PWR-MGMT | Power Management | Mission | P-005 | Elena Lindqvist | Avionics | HIL |  | 0 | 2 | 2.5 | 0 | 357 | 227.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
110 | REQ-0378 | The payload shall inhibit release when power management behaviour case 378 | Safety | MustShip | PWR-MGMT | Power Management | Mission | P-001 | Aditi Halvorsen | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 94 | 230 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
111 | REQ-0529 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 529 | Performance | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-005 | Elena Lindqvist | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 187 | 232.5 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
112 | REQ-0537 | The payload shall inhibit release when command & telemetry link behaviour case 537 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-016 | Priya Quintana | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 25 | 235 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
113 | REQ-0116 | The payload shall inhibit release when command & telemetry link behaviour case 116 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 4 | 5 | 0 | 397 | 240 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
114 | REQ-0224 | The payload shall inhibit release when command & telemetry link behaviour case 224 | Safety | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-018 | Rafael Grigorescu | Ground Segment | HIL |  | 0 | 3 | 5 | 0 | 350 | 245 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
115 | REQ-0042 | The system shall record, for certification, command & telemetry link behaviour case 42 | Regulatory | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-009 | Imani Petrovic | Avionics | Field |  | 0 | 3 | 0 | 8 | 310 | 245 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the airframe -- a flight slot, not rig time.
116 | REQ-0161 | The system shall record, for certification, power management behaviour case 161 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | P-015 | Olabisi Jindal | Integration & Test | Field |  | 0 | 4 | 0 | 8 | 714 | 245 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the airframe -- a flight slot, not rig time.
117 | REQ-0194 | The system shall record, for certification, power management behaviour case 194 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | P-015 | Olabisi Jindal | Integration & Test | Field |  | 0 | 2 | 0 | 8 | 210 | 245 | 75 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the airframe -- a flight slot, not rig time.
118 | REQ-0228 | The system shall record, for certification, command & telemetry link behaviour case 228 | Regulatory | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-018 | Rafael Grigorescu | Ground Segment | Field |  | 0 | 2 | 0 | 8 | 370 | 245 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
119 | REQ-0394 | The system shall record, for certification, navigation & sensor fusion behaviour case 394 | Regulatory | MustShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-006 | Farid Saltzman | Ground Segment | Field |  | 0 | 3 | 0 | 8 | 431 | 245 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
120 | REQ-0457 | The system shall record, for certification, power management behaviour case 457 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | P-021 | Ulrike Dalgleish | Avionics | Field |  | 0 | 1 | 0 | 8 | 80 | 245 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
121 | REQ-0464 | The system shall record, for certification, power management behaviour case 464 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | P-020 | Tomas Ustinov | Payload | Field |  | 0 | 1 | 0 | 8 | 85 | 245 | 75 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Field level this requirement type demands, and a lower-level pass is not admissible. No Field-level test exists yet: write one and run it on the airframe -- a flight slot, not rig time.
122 | REQ-0443 | The system shall provide command & telemetry link behaviour case 443 | Functional | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-010 | Jonas Weatherby | Ground Segment | Integration | 41 | 10 | 3 | 0 | 0 | 349 | 245 | 73 | RERUN | 0 | 0 | Evidence was valid at build 41 but the subsystem has changed in 10 builds since. Re-run on the release candidate.
123 | REQ-0045 | The interface shall exchange, without loss, command & telemetry link behaviour case 45 | Interface | MustShip | COMM-LNK | Command & Telemetry Link | Mission | P-004 | Dmitri Eriksen | Payload | Integration | 64 | 1 | 2 | 2.5 | 0 | 263 | 247.5 | 70 | RERUN | 0 | 0 | Evidence was valid at build 64 but the subsystem has changed in 1 builds since. Re-run on the release candidate.
124 | REQ-0093 | The subsystem shall complete, within budget, power management behaviour case 93 | Performance | MustShip | PWR-MGMT | Power Management | Mission | P-001 | Aditi Halvorsen | Avionics | HIL | 39 | 4 | 2 | 5 | 0 | 112 | 252.5 | 70 | RERUN | 0 | 0 | Evidence was valid at build 39 but the subsystem has changed in 4 builds since. Re-run on the release candidate.
125 | REQ-0435 | The system shall record, for certification, power management behaviour case 435 | Regulatory | MustShip | PWR-MGMT | Power Management | Mission | P-019 | Sana Nakamura | Integration & Test | Field | 42 | 4 | 1 | 0 | 8 | 92 | 252.5 | 70 | RERUN | 0 | 0 | Evidence was valid at build 42 but the subsystem has changed in 4 builds since. Re-run on the release candidate.
126 | REQ-0346 | The system shall provide ground control software behaviour case 346 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | P-013 | Mei Thackeray | Avionics | Integration |  | 0 | 2 | 0 | 0 | 219 | 252.5 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
127 | REQ-0354 | The system shall provide ground control software behaviour case 354 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | P-014 | Nils Castellan | Ground Segment | Integration |  | 0 | 1 | 0 | 0 | 193 | 252.5 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
128 | REQ-0402 | The system shall provide ground control software behaviour case 402 | Functional | MustShip | GND-CTRL | Ground Control Software | Support | P-014 | Nils Castellan | Ground Segment | Integration |  | 0 | 4 | 0 | 0 | 540 | 252.5 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
129 | REQ-0428 | The interface shall exchange, without loss, ground control software behaviour case 428 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 142 | 252.5 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
130 | REQ-0199 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 199 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | P-002 | Bruno Oyelaran | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 75 | 255 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
131 | REQ-0223 | The subsystem shall complete, within budget, ground control software behaviour case 223 | Performance | MustShip | GND-CTRL | Ground Control Software | Support | P-009 | Imani Petrovic | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 40 | 257.5 | 66 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
132 | REQ-0274 | The subsystem shall complete, within budget, flight control interface behaviour case 274 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-011 | Katya Fairweather | Integration & Test | HIL | 54 | 22 | 2 | 2.5 | 0 | 125 | 260 | 65 | REVIEW_THEN_RERUN | 0 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
133 | REQ-0540 | The system shall provide flight control interface behaviour case 540 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-006 | Farid Saltzman | Ground Segment | Integration | 65 | 17 | 3 | 2.5 | 0 | 348 | 262.5 | 65 | REVIEW_THEN_RERUN | 0 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
134 | REQ-0539 | The interface shall exchange, without loss, ground control software behaviour case 539 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | P-003 | Camille Villalobos | Integration & Test | Integration | 29 | 11 | 3 | 0 | 0 | 306 | 262.5 | 64 | RERUN | 0 | 0 | Evidence was valid at build 29 but the subsystem has changed in 11 builds since. Re-run on the release candidate.
135 | REQ-0012 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 12 | Performance | MustShip | DIAG-LOG | Diagnostics & Logging | Support | P-020 | Tomas Ustinov | Payload | HIL | 39 | 9 | 2 | 2.5 | 0 | 256 | 265 | 64 | RERUN | 0 | 0 | Evidence was valid at build 39 but the subsystem has changed in 9 builds since. Re-run on the release candidate.
136 | REQ-0293 | The interface shall exchange, without loss, ground control software behaviour case 293 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | P-003 | Camille Villalobos | Integration & Test | Integration | 50 | 7 | 1 | 2.5 | 0 | 125 | 267.5 | 64 | RERUN | 0 | 0 | Evidence was valid at build 50 but the subsystem has changed in 7 builds since. Re-run on the release candidate.
137 | REQ-0482 | The interface shall exchange, without loss, ground control software behaviour case 482 | Interface | MustShip | GND-CTRL | Ground Control Software | Support | P-012 | Liam Moreau | Payload | Integration | 31 | 10 | 1 | 2.5 | 0 | 177 | 270 | 64 | RERUN | 0 | 0 | Evidence was valid at build 31 but the subsystem has changed in 10 builds since. Re-run on the release candidate.
138 | REQ-0057 | The interface shall exchange, without loss, flight control interface behaviour case 57 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | Integration | 43 | 27 | 1 | 0 | 0 | 151 | 270 | 61 | RERUN | 0 | 0 | Evidence was valid at build 43 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
139 | REQ-0077 | The system shall provide payload release mechanism behaviour case 77 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-020 | Tomas Ustinov | Payload | Integration | 69 | 14 | 2 | 0 | 0 | 388 | 270 | 61 | RERUN | 0 | 0 | Evidence was valid at build 69 but the subsystem has changed in 14 builds since. Re-run on the release candidate.
140 | REQ-0320 | The system shall provide flight control interface behaviour case 320 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | Integration | 63 | 18 | 2 | 0 | 0 | 157 | 270 | 61 | RERUN | 0 | 0 | Evidence was valid at build 63 but the subsystem has changed in 18 builds since. Re-run on the release candidate.
141 | REQ-0348 | The system shall provide payload release mechanism behaviour case 348 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-016 | Priya Quintana | Payload | Integration | 64 | 17 | 1 | 0 | 0 | 175 | 270 | 61 | RERUN | 0 | 0 | Evidence was valid at build 64 but the subsystem has changed in 17 builds since. Re-run on the release candidate.
142 | REQ-0505 | The system shall provide flight control interface behaviour case 505 | Functional | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | Integration | 30 | 33 | 1 | 0 | 0 | 22 | 270 | 61 | RERUN | 0 | 0 | Evidence was valid at build 30 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
143 | REQ-0037 | The subsystem shall complete, within budget, payload release mechanism behaviour case 37 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-017 | Quentin Zielinski | Avionics | HIL | 62 | 19 | 4 | 2.5 | 0 | 490 | 272.5 | 61 | RERUN | 0 | 0 | Evidence was valid at build 62 but the subsystem has changed in 19 builds since. Re-run on the release candidate.
144 | REQ-0147 | The interface shall exchange, without loss, payload release mechanism behaviour case 147 | Interface | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | Integration | 61 | 20 | 3 | 2.5 | 0 | 405 | 275 | 61 | RERUN | 0 | 0 | Evidence was valid at build 61 but the subsystem has changed in 20 builds since. Re-run on the release candidate.
145 | REQ-0148 | The payload shall inhibit release when flight control interface behaviour case 148 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-017 | Quentin Zielinski | Avionics | HIL | 70 | 13 | 4 | 2.5 | 0 | 579 | 277.5 | 61 | RERUN | 0 | 0 | Evidence was valid at build 70 but the subsystem has changed in 13 builds since. Re-run on the release candidate.
146 | REQ-0406 | The subsystem shall complete, within budget, payload release mechanism behaviour case 406 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-010 | Jonas Weatherby | Ground Segment | HIL | 38 | 27 | 1 | 2.5 | 0 | 127 | 280 | 61 | RERUN | 0 | 0 | Evidence was valid at build 38 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
147 | REQ-0407 | The interface shall exchange, without loss, flight control interface behaviour case 407 | Interface | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-006 | Farid Saltzman | Ground Segment | Integration | 57 | 22 | 4 | 2.5 | 0 | 394 | 282.5 | 61 | RERUN | 0 | 0 | Evidence was valid at build 57 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
148 | REQ-0495 | The system shall provide payload release mechanism behaviour case 495 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | Integration | 71 | 12 | 3 | 2.5 | 0 | 436 | 285 | 61 | RERUN | 0 | 0 | Evidence was valid at build 71 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
149 | REQ-0501 | The subsystem shall complete, within budget, flight control interface behaviour case 501 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-002 | Bruno Oyelaran | Ground Segment | HIL | 36 | 30 | 3 | 2.5 | 0 | 256 | 287.5 | 61 | RERUN | 0 | 0 | Evidence was valid at build 36 but the subsystem has changed in 30 builds since. Re-run on the release candidate.
150 | REQ-0262 | The subsystem shall complete, within budget, payload release mechanism behaviour case 262 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | HIL | 64 | 17 | 2 | 5 | 0 | 241 | 292.5 | 61 | RERUN | 0 | 0 | Evidence was valid at build 64 but the subsystem has changed in 17 builds since. Re-run on the release candidate.
151 | REQ-0377 | The payload shall inhibit release when flight control interface behaviour case 377 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-012 | Liam Moreau | Payload | HIL | 57 | 22 | 3 | 7.5 | 0 | 290 | 300 | 61 | RERUN | 0 | 0 | Evidence was valid at build 57 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
152 | REQ-0376 | The system shall record, for certification, payload release mechanism behaviour case 376 | Regulatory | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-015 | Olabisi Jindal | Integration & Test | Field | 44 | 24 | 2 | 0 | 8 | 199 | 300 | 61 | RERUN | 0 | 0 | Evidence was valid at build 44 but the subsystem has changed in 24 builds since. Re-run on the release candidate.
153 | REQ-0278 | The system shall record, for certification, flight control interface behaviour case 278 | Regulatory | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-018 | Rafael Grigorescu | Ground Segment | Field | 49 | 24 | 4 | 0 | 16 | 268 | 300 | 61 | RERUN | 0 | 0 | Evidence was valid at build 49 but the subsystem has changed in 24 builds since. Re-run on the release candidate.
154 | REQ-0002 | The payload shall inhibit release when payload release mechanism behaviour case 2 | Safety | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | HIL |  | 0 | 3 | 0 | 0 | 272 | 300 | 59 | INDEPENDENT_WITNESS | 0 | 0 | Verified by its own owner against a policy requiring independence. Nothing has changed since that pass, so a second engineer reviews and countersigns it; no re-execution and no rig time.
155 | REQ-0222 | The system shall provide payload release mechanism behaviour case 222 | Functional | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-014 | Nils Castellan | Ground Segment | Integration |  | 0 | 3 | 0 | 0 | 392 | 300 | 59 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level against real neighbours; no rig time is needed.
156 | REQ-0446 | The interface shall exchange, without loss, payload release mechanism behaviour case 446 | Interface | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | Integration |  | 0 | 1 | 0 | 0 | 189 | 300 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
157 | REQ-0132 | The payload shall inhibit release when flight control interface behaviour case 132 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | HIL |  | 0 | 2 | 2.5 | 0 | 56 | 302.5 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
158 | REQ-0243 | The payload shall inhibit release when flight control interface behaviour case 243 | Safety | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 218 | 305 | 59 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
159 | REQ-0245 | The subsystem shall complete, within budget, flight control interface behaviour case 245 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-003 | Camille Villalobos | Integration & Test | HIL |  | 0 | 1 | 2.5 | 0 | 180 | 307.5 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
160 | REQ-0337 | The subsystem shall complete, within budget, flight control interface behaviour case 337 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | HIL |  | 0 | 2 | 2.5 | 0 | 242 | 310 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
161 | REQ-0342 | The subsystem shall complete, within budget, flight control interface behaviour case 342 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 2 | 2.5 | 0 | 274 | 312.5 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
162 | REQ-0345 | The subsystem shall complete, within budget, payload release mechanism behaviour case 345 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-006 | Farid Saltzman | Ground Segment | HIL |  | 0 | 2 | 2.5 | 0 | 348 | 315 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
163 | REQ-0363 | The subsystem shall complete, within budget, flight control interface behaviour case 363 | Performance | ShouldShip | FLT-CTRL | Flight Control Interface | Safety | P-020 | Tomas Ustinov | Payload | HIL |  | 0 | 3 | 2.5 | 0 | 518 | 317.5 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
164 | REQ-0380 | The subsystem shall complete, within budget, payload release mechanism behaviour case 380 | Performance | ShouldShip | REL-MECH | Payload Release Mechanism | Safety | P-016 | Priya Quintana | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 113 | 320 | 59 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
165 | REQ-0290 | The system shall record, for certification, structural interface behaviour case 290 | Regulatory | ShouldShip | STRUCT-I | Structural Interface | Safety | P-021 | Ulrike Dalgleish | Avionics | Field | 70 | 2 | 4 | 0 | 8 | 464 | 320 | 54 | RERUN | 0 | 0 | Evidence was valid at build 70 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
166 | REQ-0239 | The interface shall exchange, without loss, power management behaviour case 239 | Interface | ShouldShip | PWR-MGMT | Power Management | Mission | P-015 | Olabisi Jindal | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 24 | 320 | 52 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
167 | REQ-0480 | The system shall provide power management behaviour case 480 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 1 | 0 | 0 | 194 | 320 | 52 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
168 | REQ-0005 | The subsystem shall complete, within budget, command & telemetry link behaviour case 5 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | P-001 | Aditi Halvorsen | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 184 | 322.5 | 52 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
169 | REQ-0329 | The system shall provide power management behaviour case 329 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | P-021 | Ulrike Dalgleish | Avionics | Integration |  | 0 | 1 | 2.5 | 0 | 69 | 325 | 52 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
170 | REQ-0362 | The subsystem shall complete, within budget, command & telemetry link behaviour case 362 | Performance | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | P-007 | Grace Baptiste | Integration & Test | HIL |  | 0 | 1 | 2.5 | 0 | 15 | 327.5 | 52 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
171 | REQ-0502 | The subsystem shall complete, within budget, payload release mechanism behaviour case 502 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-011 | Katya Fairweather | Integration & Test | HIL | 28 | 29 | 1 | 2.5 | 0 | 184 | 330 | 51 | REVIEW_THEN_RERUN | 0 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
172 | REQ-0297 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 297 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-017 | Quentin Zielinski | Avionics | Integration | 33 | 12 | 1 | 0 | 0 | 170 | 330 | 50 | RERUN | 0 | 0 | Evidence was valid at build 33 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
173 | REQ-0518 | The system shall provide payload release mechanism behaviour case 518 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 47 | 330 | 49 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
174 | REQ-0517 | The subsystem shall complete, within budget, payload release mechanism behaviour case 517 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | HIL |  | 0 | 1 | 2.5 | 0 | 150 | 332.5 | 49 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
175 | REQ-0004 | The system shall provide power management behaviour case 4 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | P-009 | Imani Petrovic | Avionics | Integration |  | 0 | 1 | 0 | 0 | 64 | 332.5 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
176 | REQ-0110 | The system shall provide command & telemetry link behaviour case 110 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 1 | 0 | 0 | 130 | 332.5 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
177 | REQ-0326 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 326 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 3 | 0 | 0 | 429 | 332.5 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
178 | REQ-0373 | The system shall provide command & telemetry link behaviour case 373 | Functional | ShouldShip | COMM-LNK | Command & Telemetry Link | Mission | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 1 | 0 | 0 | 140 | 332.5 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
179 | REQ-0256 | The subsystem shall complete, within budget, power management behaviour case 256 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | P-006 | Farid Saltzman | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 126 | 335 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
180 | REQ-0437 | The subsystem shall complete, within budget, power management behaviour case 437 | Performance | ShouldShip | PWR-MGMT | Power Management | Mission | P-021 | Ulrike Dalgleish | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 49 | 337.5 | 48 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
181 | REQ-0532 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 532 | Performance | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-002 | Bruno Oyelaran | Ground Segment | HIL |  | 0 | 3 | 5 | 0 | 479 | 342.5 | 48 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level on the rig.
182 | REQ-0128 | The system shall provide payload release mechanism behaviour case 128 | Functional | Nice | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | Integration | 49 | 22 | 3 | 0 | 0 | 541 | 342.5 | 47 | RERUN | 0 | 0 | Evidence was valid at build 49 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
183 | REQ-0138 | The interface shall exchange, without loss, flight control interface behaviour case 138 | Interface | Nice | FLT-CTRL | Flight Control Interface | Safety | P-009 | Imani Petrovic | Avionics | Integration | 65 | 17 | 4 | 2.5 | 0 | 458 | 345 | 47 | RERUN | 0 | 0 | Evidence was valid at build 65 but the subsystem has changed in 17 builds since. Re-run on the release candidate.
184 | REQ-0454 | The interface shall exchange, without loss, payload release mechanism behaviour case 454 | Interface | Nice | REL-MECH | Payload Release Mechanism | Safety | P-005 | Elena Lindqvist | Avionics | Integration | 34 | 28 | 2 | 2.5 | 0 | 367 | 347.5 | 47 | RERUN | 0 | 0 | Evidence was valid at build 34 but the subsystem has changed in 28 builds since. Re-run on the release candidate.
185 | REQ-0120 | The subsystem shall complete, within budget, flight control interface behaviour case 120 | Performance | Nice | FLT-CTRL | Flight Control Interface | Safety | P-017 | Quentin Zielinski | Avionics | HIL | 63 | 18 | 2 | 5 | 0 | 131 | 352.5 | 47 | RERUN | 0 | 0 | Evidence was valid at build 63 but the subsystem has changed in 18 builds since. Re-run on the release candidate.
186 | REQ-0396 | The subsystem shall complete, within budget, payload release mechanism behaviour case 396 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-001 | Aditi Halvorsen | Avionics | HIL | 71 | 12 | 2 | 5 | 0 | 313 | 357.5 | 47 | RERUN | 0 | 0 | Evidence was valid at build 71 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
187 | REQ-0064 | The interface shall exchange, without loss, flight control interface behaviour case 64 | Interface | Nice | FLT-CTRL | Flight Control Interface | Safety | P-015 | Olabisi Jindal | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 179 | 357.5 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
188 | REQ-0031 | The subsystem shall complete, within budget, payload release mechanism behaviour case 31 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-014 | Nils Castellan | Ground Segment | HIL |  | 0 | 4 | 2.5 | 0 | 679 | 360 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
189 | REQ-0058 | The subsystem shall complete, within budget, flight control interface behaviour case 58 | Performance | Nice | FLT-CTRL | Flight Control Interface | Safety | P-017 | Quentin Zielinski | Avionics | HIL |  | 0 | 2 | 2.5 | 0 | 283 | 362.5 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
190 | REQ-0108 | The subsystem shall complete, within budget, structural interface behaviour case 108 | Performance | Nice | STRUCT-I | Structural Interface | Safety | P-021 | Ulrike Dalgleish | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 202 | 365 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
191 | REQ-0284 | The subsystem shall complete, within budget, payload release mechanism behaviour case 284 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-017 | Quentin Zielinski | Avionics | HIL |  | 0 | 1 | 2.5 | 0 | 207 | 367.5 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
192 | REQ-0361 | The subsystem shall complete, within budget, payload release mechanism behaviour case 361 | Performance | Nice | REL-MECH | Payload Release Mechanism | Safety | P-018 | Rafael Grigorescu | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 56 | 370 | 45 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
193 | REQ-0160 | The system shall provide navigation & sensor fusion behaviour case 160 | Functional | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-004 | Dmitri Eriksen | Payload | Integration | 63 | 2 | 2 | 0 | 0 | 437 | 370 | 43 | RERUN | 0 | 0 | Evidence was valid at build 63 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
194 | REQ-0311 | The system shall provide ground control software behaviour case 311 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 80 | 370 | 43 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
195 | REQ-0367 | The interface shall exchange, without loss, navigation & sensor fusion behaviour case 367 | Interface | ShouldShip | NAV-SENS | Navigation & Sensor Fusion | Mission | P-017 | Quentin Zielinski | Avionics | Integration | 54 | 5 | 2 | 0 | 0 | 154 | 370 | 43 | RERUN | 0 | 0 | Evidence was valid at build 54 but the subsystem has changed in 5 builds since. Re-run on the release candidate.
196 | REQ-0453 | The system shall provide power management behaviour case 453 | Functional | ShouldShip | PWR-MGMT | Power Management | Mission | P-006 | Farid Saltzman | Ground Segment | Integration | 32 | 4 | 2 | 0 | 0 | 206 | 370 | 43 | RERUN | 0 | 0 | Evidence was valid at build 32 but the subsystem has changed in 4 builds since. Re-run on the release candidate.
197 | REQ-0383 | The system shall provide ground control software behaviour case 383 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | P-009 | Imani Petrovic | Avionics | Integration | 30 | 11 | 2 | 2.5 | 0 | 329 | 372.5 | 41 | REVIEW_THEN_RERUN | 0 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
198 | REQ-0299 | The system shall provide ground control software behaviour case 299 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | P-012 | Liam Moreau | Payload | Integration |  | 0 | 3 | 0 | 0 | 561 | 372.5 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
199 | REQ-0335 | The system shall provide diagnostics & logging behaviour case 335 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | P-018 | Rafael Grigorescu | Ground Segment | Integration |  | 0 | 2 | 0 | 0 | 167 | 372.5 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
200 | REQ-0508 | The system shall provide diagnostics & logging behaviour case 508 | Functional | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | P-001 | Aditi Halvorsen | Avionics | Integration |  | 0 | 4 | 0 | 0 | 407 | 372.5 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
201 | REQ-0516 | The system shall provide ground control software behaviour case 516 | Functional | ShouldShip | GND-CTRL | Ground Control Software | Support | P-001 | Aditi Halvorsen | Avionics | Integration |  | 0 | 1 | 0 | 0 | 98 | 372.5 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
202 | REQ-0007 | The subsystem shall complete, within budget, ground control software behaviour case 7 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | P-018 | Rafael Grigorescu | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 130 | 375 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
203 | REQ-0117 | The subsystem shall complete, within budget, ground control software behaviour case 117 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | P-010 | Jonas Weatherby | Ground Segment | HIL |  | 0 | 3 | 2.5 | 0 | 478 | 377.5 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
204 | REQ-0212 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 212 | Performance | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | P-015 | Olabisi Jindal | Integration & Test | HIL |  | 0 | 2 | 2.5 | 0 | 407 | 380 | 39 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
205 | REQ-0448 | The subsystem shall complete, within budget, power management behaviour case 448 | Performance | Nice | PWR-MGMT | Power Management | Mission | P-018 | Rafael Grigorescu | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 173 | 382.5 | 38 | VERIFY | 0 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
206 | REQ-0095 | The system shall provide command & telemetry link behaviour case 95 | Functional | Nice | COMM-LNK | Command & Telemetry Link | Mission | P-011 | Katya Fairweather | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 163 | 382.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
207 | REQ-0151 | The system shall provide power management behaviour case 151 | Functional | Nice | PWR-MGMT | Power Management | Mission | P-017 | Quentin Zielinski | Avionics | Integration |  | 0 | 1 | 0 | 0 | 130 | 382.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
208 | REQ-0310 | The system shall provide power management behaviour case 310 | Functional | Nice | PWR-MGMT | Power Management | Mission | P-020 | Tomas Ustinov | Payload | Integration |  | 0 | 1 | 0 | 0 | 22 | 382.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
209 | REQ-0048 | The subsystem shall complete, within budget, command & telemetry link behaviour case 48 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | P-016 | Priya Quintana | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 108 | 385 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
210 | REQ-0066 | The subsystem shall complete, within budget, power management behaviour case 66 | Performance | Nice | PWR-MGMT | Power Management | Mission | P-013 | Mei Thackeray | Avionics | HIL |  | 0 | 2 | 2.5 | 0 | 105 | 387.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
211 | REQ-0152 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 152 | Performance | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | P-018 | Rafael Grigorescu | Ground Segment | HIL | 58 | 5 | 2 | 2.5 | 0 | 305 | 390 | 34 | RERUN | 0 | 0 | Evidence was valid at build 58 but the subsystem has changed in 5 builds since. Re-run on the release candidate.
212 | REQ-0220 | The subsystem shall complete, within budget, navigation & sensor fusion behaviour case 220 | Performance | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | P-020 | Tomas Ustinov | Payload | HIL |  | 0 | 2 | 2.5 | 0 | 173 | 392.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
213 | REQ-0307 | The subsystem shall complete, within budget, power management behaviour case 307 | Performance | Nice | PWR-MGMT | Power Management | Mission | P-009 | Imani Petrovic | Avionics | HIL |  | 0 | 3 | 2.5 | 0 | 330 | 395 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
214 | REQ-0462 | The subsystem shall complete, within budget, command & telemetry link behaviour case 462 | Performance | Nice | COMM-LNK | Command & Telemetry Link | Mission | P-010 | Jonas Weatherby | Ground Segment | HIL |  | 0 | 1 | 2.5 | 0 | 174 | 397.5 | 34 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
215 | REQ-0355 | The interface shall exchange, without loss, diagnostics & logging behaviour case 355 | Interface | ShouldShip | DIAG-LOG | Diagnostics & Logging | Support | P-015 | Olabisi Jindal | Integration & Test | Integration | 69 | 2 | 3 | 5 | 0 | 197 | 402.5 | 34 | RERUN | 0 | 0 | Evidence was valid at build 69 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
216 | REQ-0107 | The subsystem shall complete, within budget, ground control software behaviour case 107 | Performance | ShouldShip | GND-CTRL | Ground Control Software | Support | P-019 | Sana Nakamura | Integration & Test | HIL | 69 | 2 | 3 | 7.5 | 0 | 457 | 410 | 34 | RERUN | 0 | 0 | Evidence was valid at build 69 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
217 | REQ-0216 | The interface shall exchange, without loss, command & telemetry link behaviour case 216 | Interface | Nice | COMM-LNK | Command & Telemetry Link | Mission | P-009 | Imani Petrovic | Avionics | Integration | 49 | 6 | 4 | 5 | 0 | 531 | 415 | 32 | RERUN | 0 | 0 | Evidence was valid at build 49 but the subsystem has changed in 6 builds since. Re-run on the release candidate.
218 | REQ-0114 | The system shall provide navigation & sensor fusion behaviour case 114 | Functional | Nice | NAV-SENS | Navigation & Sensor Fusion | Mission | P-003 | Camille Villalobos | Integration & Test | Integration | 67 | 2 | 4 | 0 | 0 | 347 | 415 | 29 | RERUN | 0 | 0 | Evidence was valid at build 67 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
219 | REQ-0241 | The system shall provide ground control software behaviour case 241 | Functional | Nice | GND-CTRL | Ground Control Software | Support | P-015 | Olabisi Jindal | Integration & Test | Integration |  | 0 | 1 | 0 | 0 | 40 | 415 | 29 | VERIFY | 1 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
220 | REQ-0131 | The interface shall exchange, without loss, power management behaviour case 131 | Interface | Nice | PWR-MGMT | Power Management | Mission | P-021 | Ulrike Dalgleish | Avionics | Integration | 46 | 2 | 1 | 2.5 | 0 | 85 | 417.5 | 29 | RERUN | 0 | 0 | Evidence was valid at build 46 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
221 | REQ-0184 | The subsystem shall complete, within budget, power management behaviour case 184 | Performance | Nice | PWR-MGMT | Power Management | Mission | P-016 | Priya Quintana | Payload | HIL | 48 | 2 | 2 | 2.5 | 0 | 66 | 420 | 29 | RERUN | 0 | 0 | Evidence was valid at build 48 but the subsystem has changed in 2 builds since. Re-run on the release candidate.
222 | REQ-0313 | The interface shall exchange, without loss, diagnostics & logging behaviour case 313 | Interface | Nice | DIAG-LOG | Diagnostics & Logging | Support | P-003 | Camille Villalobos | Integration & Test | Integration |  | 0 | 4 | 0 | 0 | 707 | 420 | 25 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
223 | REQ-0323 | The system shall provide ground control software behaviour case 323 | Functional | Nice | GND-CTRL | Ground Control Software | Support | P-007 | Grace Baptiste | Integration & Test | Integration |  | 0 | 3 | 0 | 0 | 403 | 420 | 25 | RAISE_TEST_LEVEL | 0 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. Run its tests at or above that level against real neighbours; no rig time is needed.
224 | REQ-0366 | The system shall provide ground control software behaviour case 366 | Functional | Nice | GND-CTRL | Ground Control Software | Support | P-004 | Dmitri Eriksen | Payload | Integration |  | 0 | 2 | 0 | 0 | 249 | 420 | 25 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the Integration level this requirement type demands, and a lower-level pass is not admissible. No Integration-level test exists yet: write one and run it against real neighbours; no rig time is needed.
225 | REQ-0076 | The subsystem shall complete, within budget, ground control software behaviour case 76 | Performance | Nice | GND-CTRL | Ground Control Software | Support | P-020 | Tomas Ustinov | Payload | HIL |  | 0 | 1 | 2.5 | 0 | 207 | 422.5 | 25 | RAISE_TEST_LEVEL | 1 | 0 | Passing evidence sits below the HIL level this requirement type demands, and a lower-level pass is not admissible. No HIL-level test exists yet: write one and run it on the rig.
226 | REQ-0079 | The subsystem shall complete, within budget, diagnostics & logging behaviour case 79 | Performance | Nice | DIAG-LOG | Diagnostics & Logging | Support | P-013 | Mei Thackeray | Avionics | HIL | 69 | 2 | 1 | 2.5 | 0 | 116 | 425 | 20 | RERUN | 0 | 0 | Evidence was valid at build 69 but the subsystem has changed in 2 builds since. Re-run on the release candidate.

## Data_Sub
SubsystemCode | SubsystemName | Criticality | RequiresHILRig | Requirements | MustShip | CurrentAll | CurrentMustShip | NoEvidence | Insufficient | StaleByCode | StaleByReq | ReadinessPct | BuildsChanged | LinesChanged | LastChangeBuild | RigHoursOutstanding | AirframeHoursOutstanding
FLT-CTRL | Flight Control Interface | Safety | 1 | 79 | 47 | 23 | 11 | 0 | 22 | 31 | 3 | 23.4 | 45 | 22292 | 88 | 120 | 120
REL-MECH | Payload Release Mechanism | Safety | 1 | 93 | 62 | 29 | 20 | 6 | 25 | 30 | 3 | 32.26 | 42 | 21533 | 88 | 132.5 | 72
PWR-MGMT | Power Management | Mission | 1 | 78 | 37 | 49 | 22 | 4 | 20 | 5 | 0 | 59.46 | 15 | 6939 | 57 | 32.5 | 40
COMM-LNK | Command & Telemetry Link | Mission | 1 | 73 | 43 | 48 | 26 | 5 | 15 | 5 | 0 | 60.47 | 23 | 13311 | 66 | 52.5 | 16
STRUCT-I | Structural Interface | Safety | 1 | 29 | 19 | 21 | 13 | 0 | 4 | 4 | 0 | 68.42 | 15 | 6568 | 80 | 15 | 16
GND-CTRL | Ground Control Software | Support | 0 | 61 | 28 | 42 | 20 | 2 | 12 | 4 | 1 | 71.43 | 21 | 9856 | 87 | 25 | 0
NAV-SENS | Navigation & Sensor Fusion | Mission | 1 | 66 | 33 | 50 | 24 | 1 | 10 | 5 | 0 | 72.73 | 17 | 7583 | 80 | 30 | 8
DIAG-LOG | Diagnostics & Logging | Support | 0 | 40 | 12 | 31 | 10 | 0 | 5 | 4 | 0 | 83.33 | 18 | 7653 | 80 | 17.5 | 0

## Data_KPI
AsOfBuild | AsOfDate | Requirements | MustShipCount | WorkItemCompletionPct | VerificationCoveragePct | ShipReadinessPct | StaleVerificationPct | PolicyCompliancePct | NoEvidenceCount | InsufficientCount | StaleCount | CurrentCount | BlockedTestPct | CriticalRAIDOpen | OverdueRAIDPct | TotalRAIDExposure | RigHoursOutstanding | AirframeHoursOutstanding
88 | 2026-09-30 | 519 | 281 | 93.86 | 96.53 | 51.96 | 24.48 | 77.45 | 18 | 113 | 95 | 293 | 3.39 | 9 | 57.78 | 466 | 425 | 272

## Data_Trend
BuildNumber | BuildID | BuildDate | WorkItemCompletionPct | VerificationCoveragePct | ShipReadinessPct | StaleVerificationPct | ReadinessGapVsReported
40 | B-040 | 2025-10-06 | 84.11 | 27.17 | 4.63 | 69.89 | 79.48
44 | B-044 | 2025-11-03 | 87.32 | 30.06 | 2.85 | 84.62 | 84.47
48 | B-048 | 2025-12-01 | 85.86 | 33.72 | 2.85 | 78.38 | 83.01
52 | B-052 | 2025-12-29 | 86.64 | 36.8 | 6.05 | 72.58 | 80.59
56 | B-056 | 2026-01-26 | 87.39 | 39.69 | 7.47 | 72.06 | 79.92
60 | B-060 | 2026-02-23 | 87.45 | 41.43 | 1.78 | 90.71 | 85.67
64 | B-064 | 2026-03-23 | 87.7 | 43.74 | 4.27 | 84.62 | 83.43
68 | B-068 | 2026-04-20 | 87.01 | 46.05 | 3.56 | 86.83 | 83.45
72 | B-072 | 2026-05-18 | 87.98 | 54.72 | 4.63 | 83.77 | 83.35
76 | B-076 | 2026-06-15 | 89.18 | 71.68 | 19.93 | 53.17 | 69.25
80 | B-080 | 2026-07-13 | 90.01 | 71.68 | 10.68 | 75.79 | 79.33
84 | B-084 | 2026-08-10 | 93.31 | 84.39 | 25.62 | 51.32 | 67.69
88 | B-088 | 2026-09-07 | 93.86 | 96.53 | 51.96 | 24.48 | 41.9

## Data_RAID
RAIDID | RAIDType | Title | SubsystemCode | SubsystemName | Criticality | OwnerID | OwnerName | OwnerTeam | RaisedDate | DueDate | ClosedDate | Probability | Impact | ExposureScore | ExposureBand | RAIDStatus | IsOpen | IsOverdue | DaysOverdue | AgeDays | MitigationNote
RAID-041 | Issue | Issue on Power Management: rig availability is below the rate needed to clear outstanding verification | PWR-MGMT | Power Management | Mission | P-003 | Camille Villalobos | Integration & Test | 2025-06-25 | 2026-02-25 | 2025-08-28 | 5 | 5 | 25 | Critical | Closed | 0 | 0 | 0 | 462 | Closed: mitigation completed and evidence attached to the verification record.
RAID-045 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-004 | Dmitri Eriksen | Payload | 2026-04-02 | 2026-08-07 |  | 5 | 5 | 25 | Critical | Open | 1 | 1 | 54 | 181 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-055 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-014 | Nils Castellan | Ground Segment | 2025-12-16 | 2026-02-03 |  | 5 | 5 | 25 | Critical | Open | 1 | 1 | 239 | 288 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-061 | Issue | Issue on Command & Telemetry Link: rig availability is below the rate needed to clear outstanding verification | COMM-LNK | Command & Telemetry Link | Mission | P-019 | Sana Nakamura | Integration & Test | 2026-03-22 | 2026-06-20 |  | 5 | 5 | 25 | Critical | Open | 1 | 1 | 102 | 192 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-083 | Dependency | Dependency on Power Management: awaiting supplier confirmation before verification can close | PWR-MGMT | Power Management | Mission | P-008 | Hiroshi Ibarra | Payload | 2025-04-03 | 2026-01-12 | 2025-06-17 | 5 | 5 | 25 | Critical | Closed | 0 | 0 | 0 | 545 | Closed: mitigation completed and evidence attached to the verification record.
RAID-091 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-001 | Aditi Halvorsen | Avionics | 2025-07-27 | 2026-06-17 | 2025-10-21 | 5 | 5 | 25 | Critical | Closed | 0 | 0 | 0 | 430 | Closed: mitigation completed and evidence attached to the verification record.
RAID-032 | Risk | Risk on Diagnostics & Logging: late design change may invalidate completed qualification evidence | DIAG-LOG | Diagnostics & Logging | Support | P-013 | Mei Thackeray | Avionics | 2026-02-27 | 2026-10-31 |  | 4 | 5 | 24 | Critical | Mitigating | 1 | 0 | 0 | 215 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-075 | Assumption | Assumption on Command & Telemetry Link: assumed unchanged from the previous airframe, not yet confirmed | COMM-LNK | Command & Telemetry Link | Mission | P-021 | Ulrike Dalgleish | Avionics | 2026-05-09 | 2027-01-07 | 2026-07-12 | 4 | 5 | 24 | Critical | Closed | 0 | 0 | 0 | 144 | Closed: mitigation completed and evidence attached to the verification record.
RAID-086 | Dependency | Dependency on Structural Interface: awaiting supplier confirmation before verification can close | STRUCT-I | Structural Interface | Safety | P-008 | Hiroshi Ibarra | Payload | 2025-12-07 | 2026-11-30 | 2026-03-12 | 4 | 5 | 24 | Critical | Closed | 0 | 0 | 0 | 297 | Closed: mitigation completed and evidence attached to the verification record.
RAID-051 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | 2025-05-27 | 2025-07-27 | 2025-06-10 | 5 | 4 | 22 | Critical | Closed | 0 | 0 | 0 | 491 | Closed: mitigation completed and evidence attached to the verification record.
RAID-090 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-020 | Tomas Ustinov | Payload | 2026-01-11 | 2026-12-21 |  | 5 | 4 | 22 | Critical | Open | 1 | 0 | 0 | 262 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-004 | Issue | Issue on Command & Telemetry Link: rig availability is below the rate needed to clear outstanding verification | COMM-LNK | Command & Telemetry Link | Mission | P-020 | Tomas Ustinov | Payload | 2026-02-09 | 2026-10-01 |  | 3 | 5 | 20 | Critical | Mitigating | 1 | 0 | 0 | 233 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-015 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | 2026-01-19 | 2026-07-21 | 2026-03-07 | 3 | 5 | 20 | Critical | Closed | 0 | 0 | 0 | 254 | Closed: mitigation completed and evidence attached to the verification record.
RAID-018 | Dependency | Dependency on Payload Release Mechanism: awaiting supplier confirmation before verification can close | REL-MECH | Payload Release Mechanism | Safety | P-002 | Bruno Oyelaran | Ground Segment | 2026-06-20 | 2026-10-10 |  | 3 | 5 | 20 | Critical | Mitigating | 1 | 0 | 0 | 102 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-033 | Risk | Risk on Ground Control Software: late design change may invalidate completed qualification evidence | GND-CTRL | Ground Control Software | Support | P-012 | Liam Moreau | Payload | 2026-07-06 | 2027-04-22 | 2026-09-20 | 3 | 5 | 20 | Critical | Closed | 0 | 0 | 0 | 86 | Closed: mitigation completed and evidence attached to the verification record.
RAID-042 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-001 | Aditi Halvorsen | Avionics | 2025-07-25 | 2026-07-21 |  | 3 | 5 | 20 | Critical | Open | 1 | 1 | 71 | 432 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-072 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-021 | Ulrike Dalgleish | Avionics | 2026-01-26 | 2026-08-21 | 2026-03-21 | 3 | 5 | 20 | Critical | Closed | 0 | 0 | 0 | 247 | Closed: mitigation completed and evidence attached to the verification record.
RAID-073 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | 2025-01-12 | 2025-10-10 |  | 3 | 5 | 20 | Critical | Open | 1 | 1 | 355 | 626 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-043 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | 2025-10-15 | 2026-04-10 | 2025-11-30 | 4 | 4 | 18 | High | Closed | 0 | 0 | 0 | 350 | Closed: mitigation completed and evidence attached to the verification record.
RAID-048 | Issue | Issue on Power Management: rig availability is below the rate needed to clear outstanding verification | PWR-MGMT | Power Management | Mission | P-006 | Farid Saltzman | Ground Segment | 2025-09-07 | 2026-06-02 | 2025-11-17 | 4 | 4 | 18 | High | Closed | 0 | 0 | 0 | 388 | Closed: mitigation completed and evidence attached to the verification record.
RAID-005 | Assumption | Assumption on Structural Interface: assumed unchanged from the previous airframe, not yet confirmed | STRUCT-I | Structural Interface | Safety | P-014 | Nils Castellan | Ground Segment | 2025-08-12 | 2025-12-08 | 2025-09-11 | 5 | 3 | 17 | High | Closed | 0 | 0 | 0 | 414 | Closed: mitigation completed and evidence attached to the verification record.
RAID-009 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | 2026-04-09 | 2026-11-26 | 2026-06-08 | 5 | 3 | 17 | High | Closed | 0 | 0 | 0 | 174 | Closed: mitigation completed and evidence attached to the verification record.
RAID-027 | Risk | Risk on Structural Interface: late design change may invalidate completed qualification evidence | STRUCT-I | Structural Interface | Safety | P-018 | Rafael Grigorescu | Ground Segment | 2026-04-12 | 2027-03-02 |  | 5 | 3 | 17 | High | Mitigating | 1 | 0 | 0 | 171 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-068 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-014 | Nils Castellan | Ground Segment | 2026-06-16 | 2027-05-10 |  | 5 | 3 | 17 | High | Mitigating | 1 | 0 | 0 | 106 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-017 | Assumption | Assumption on Flight Control Interface: assumed unchanged from the previous airframe, not yet confirmed | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | 2026-03-30 | 2027-03-19 |  | 2 | 5 | 15 | High | Open | 1 | 0 | 0 | 184 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-021 | Issue | Issue on Navigation & Sensor Fusion: rig availability is below the rate needed to clear outstanding verification | NAV-SENS | Navigation & Sensor Fusion | Mission | P-013 | Mei Thackeray | Avionics | 2025-07-22 | 2026-02-12 |  | 3 | 4 | 14 | High | Mitigating | 1 | 1 | 230 | 435 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-028 | Risk | Risk on Ground Control Software: late design change may invalidate completed qualification evidence | GND-CTRL | Ground Control Software | Support | P-013 | Mei Thackeray | Avionics | 2026-05-09 | 2027-04-07 |  | 3 | 4 | 14 | High | Mitigating | 1 | 0 | 0 | 144 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-030 | Assumption | Assumption on Diagnostics & Logging: assumed unchanged from the previous airframe, not yet confirmed | DIAG-LOG | Diagnostics & Logging | Support | P-005 | Elena Lindqvist | Avionics | 2026-03-01 | 2026-09-22 | 2026-04-23 | 4 | 3 | 14 | High | Closed | 0 | 0 | 0 | 213 | Closed: mitigation completed and evidence attached to the verification record.
RAID-036 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-010 | Jonas Weatherby | Ground Segment | 2025-04-13 | 2026-01-30 |  | 3 | 4 | 14 | High | Open | 1 | 1 | 243 | 535 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-039 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-015 | Olabisi Jindal | Integration & Test | 2025-06-27 | 2026-02-06 |  | 3 | 4 | 14 | High | Open | 1 | 1 | 236 | 460 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-053 | Assumption | Assumption on Navigation & Sensor Fusion: assumed unchanged from the previous airframe, not yet confirmed | NAV-SENS | Navigation & Sensor Fusion | Mission | P-016 | Priya Quintana | Payload | 2025-12-08 | 2025-11-27 | 2025-12-30 | 3 | 4 | 14 | High | Closed | 0 | 0 | 0 | 296 | Closed: mitigation completed and evidence attached to the verification record.
RAID-059 | Dependency | Dependency on Flight Control Interface: awaiting supplier confirmation before verification can close | FLT-CTRL | Flight Control Interface | Safety | P-013 | Mei Thackeray | Avionics | 2026-01-23 | 2026-11-29 | 2026-04-15 | 3 | 4 | 14 | High | Closed | 0 | 0 | 0 | 250 | Closed: mitigation completed and evidence attached to the verification record.
RAID-080 | Issue | Issue on Ground Control Software: rig availability is below the rate needed to clear outstanding verification | GND-CTRL | Ground Control Software | Support | P-014 | Nils Castellan | Ground Segment | 2026-02-27 | 2027-01-08 |  | 3 | 4 | 14 | High | Mitigating | 1 | 0 | 0 | 215 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-084 | Dependency | Dependency on Payload Release Mechanism: awaiting supplier confirmation before verification can close | REL-MECH | Payload Release Mechanism | Safety | P-013 | Mei Thackeray | Avionics | 2025-11-20 | 2025-11-09 | 2026-02-02 | 4 | 3 | 14 | High | Closed | 0 | 0 | 0 | 314 | Closed: mitigation completed and evidence attached to the verification record.
RAID-001 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-015 | Olabisi Jindal | Integration & Test | 2025-10-27 | 2026-09-16 |  | 5 | 2 | 10 | Medium | Open | 1 | 1 | 14 | 338 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-011 | Dependency | Dependency on Navigation & Sensor Fusion: awaiting supplier confirmation before verification can close | NAV-SENS | Navigation & Sensor Fusion | Mission | P-016 | Priya Quintana | Payload | 2025-09-03 | 2025-12-16 | 2025-09-29 | 5 | 2 | 10 | Medium | Closed | 0 | 0 | 0 | 392 | Closed: mitigation completed and evidence attached to the verification record.
RAID-014 | Assumption | Assumption on Command & Telemetry Link: assumed unchanged from the previous airframe, not yet confirmed | COMM-LNK | Command & Telemetry Link | Mission | P-008 | Hiroshi Ibarra | Payload | 2026-05-09 | 2026-09-23 | 2026-06-13 | 2 | 4 | 10 | Medium | Closed | 0 | 0 | 0 | 144 | Closed: mitigation completed and evidence attached to the verification record.
RAID-016 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | 2026-02-26 | 2026-07-07 | 2026-03-31 | 1 | 5 | 10 | High | Closed | 0 | 0 | 0 | 216 | Closed: mitigation completed and evidence attached to the verification record.
RAID-031 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | 2026-05-27 | 2027-01-18 |  | 1 | 5 | 10 | High | Open | 1 | 0 | 0 | 126 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-034 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | 2026-06-06 | 2026-12-26 |  | 5 | 2 | 10 | Medium | Open | 1 | 0 | 0 | 116 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-044 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-019 | Sana Nakamura | Integration & Test | 2026-03-27 | 2026-09-06 | 2026-05-08 | 2 | 4 | 10 | Medium | Closed | 0 | 0 | 0 | 187 | Closed: mitigation completed and evidence attached to the verification record.
RAID-049 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-004 | Dmitri Eriksen | Payload | 2026-01-01 | 2025-12-21 |  | 5 | 2 | 10 | Medium | Open | 1 | 0 | 0 | 272 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-058 | Assumption | Assumption on Power Management: assumed unchanged from the previous airframe, not yet confirmed | PWR-MGMT | Power Management | Mission | P-010 | Jonas Weatherby | Ground Segment | 2025-09-18 | 2026-01-08 | 2025-10-16 | 5 | 2 | 10 | Medium | Closed | 0 | 0 | 0 | 377 | Closed: mitigation completed and evidence attached to the verification record.
RAID-060 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-020 | Tomas Ustinov | Payload | 2025-10-29 | 2025-12-18 |  | 1 | 5 | 10 | High | Open | 1 | 1 | 286 | 336 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-064 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-004 | Dmitri Eriksen | Payload | 2026-01-19 | 2026-11-02 | 2026-04-05 | 2 | 4 | 10 | Medium | Closed | 0 | 0 | 0 | 254 | Closed: mitigation completed and evidence attached to the verification record.
RAID-065 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-010 | Jonas Weatherby | Ground Segment | 2025-02-08 | 2025-04-20 | 2025-02-25 | 5 | 2 | 10 | Medium | Closed | 0 | 0 | 0 | 599 | Closed: mitigation completed and evidence attached to the verification record.
RAID-066 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-018 | Rafael Grigorescu | Ground Segment | 2025-06-11 | 2026-03-02 |  | 5 | 2 | 10 | Medium | Open | 1 | 1 | 212 | 476 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-071 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-013 | Mei Thackeray | Avionics | 2026-01-12 | 2026-03-21 |  | 1 | 5 | 10 | High | Open | 1 | 1 | 193 | 261 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-008 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-021 | Ulrike Dalgleish | Avionics | 2025-05-01 | 2025-07-13 |  | 3 | 3 | 9 | Medium | Open | 1 | 1 | 444 | 517 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-025 | Risk | Risk on Ground Control Software: late design change may invalidate completed qualification evidence | GND-CTRL | Ground Control Software | Support | P-003 | Camille Villalobos | Integration & Test | 2026-02-05 | 2026-04-16 | 2026-02-22 | 3 | 3 | 9 | Medium | Closed | 0 | 0 | 0 | 237 | Closed: mitigation completed and evidence attached to the verification record.
RAID-057 | Risk | Risk on Diagnostics & Logging: late design change may invalidate completed qualification evidence | DIAG-LOG | Diagnostics & Logging | Support | P-003 | Camille Villalobos | Integration & Test | 2025-10-19 | 2026-04-18 | 2025-12-05 | 3 | 3 | 9 | Medium | Closed | 0 | 0 | 0 | 346 | Closed: mitigation completed and evidence attached to the verification record.
RAID-062 | Dependency | Dependency on Power Management: awaiting supplier confirmation before verification can close | PWR-MGMT | Power Management | Mission | P-006 | Farid Saltzman | Ground Segment | 2025-04-14 | 2025-04-03 | 2025-05-12 | 3 | 3 | 9 | Medium | Closed | 0 | 0 | 0 | 534 | Closed: mitigation completed and evidence attached to the verification record.
RAID-087 | Risk | Risk on Ground Control Software: late design change may invalidate completed qualification evidence | GND-CTRL | Ground Control Software | Support | P-017 | Quentin Zielinski | Avionics | 2025-06-02 | 2026-03-22 | 2025-08-18 | 3 | 3 | 9 | Medium | Closed | 0 | 0 | 0 | 485 | Closed: mitigation completed and evidence attached to the verification record.
RAID-020 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-002 | Bruno Oyelaran | Ground Segment | 2025-03-25 | 2025-10-07 |  | 4 | 2 | 8 | Medium | Open | 1 | 1 | 358 | 554 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-056 | Assumption | Assumption on Flight Control Interface: assumed unchanged from the previous airframe, not yet confirmed | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | 2025-12-25 | 2026-10-17 | 2026-03-13 | 4 | 2 | 8 | Medium | Closed | 0 | 0 | 0 | 279 | Closed: mitigation completed and evidence attached to the verification record.
RAID-069 | Risk | Risk on Command & Telemetry Link: late design change may invalidate completed qualification evidence | COMM-LNK | Command & Telemetry Link | Mission | P-011 | Katya Fairweather | Integration & Test | 2026-03-09 | 2026-10-30 | 2026-05-09 | 4 | 2 | 8 | Medium | Closed | 0 | 0 | 0 | 205 | Closed: mitigation completed and evidence attached to the verification record.
RAID-078 | Issue | Issue on Navigation & Sensor Fusion: rig availability is below the rate needed to clear outstanding verification | NAV-SENS | Navigation & Sensor Fusion | Mission | P-014 | Nils Castellan | Ground Segment | 2026-05-28 | 2026-10-08 | 2026-07-01 | 1 | 4 | 8 | Medium | Closed | 0 | 0 | 0 | 125 | Closed: mitigation completed and evidence attached to the verification record.
RAID-092 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-012 | Liam Moreau | Payload | 2025-12-18 | 2026-07-30 | 2026-02-14 | 4 | 2 | 8 | Medium | Closed | 0 | 0 | 0 | 286 | Closed: mitigation completed and evidence attached to the verification record.
RAID-003 | Dependency | Dependency on Payload Release Mechanism: awaiting supplier confirmation before verification can close | REL-MECH | Payload Release Mechanism | Safety | P-018 | Rafael Grigorescu | Ground Segment | 2025-11-19 | 2026-11-10 |  | 3 | 2 | 6 | Medium | Open | 1 | 0 | 0 | 315 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-029 | Risk | Risk on Diagnostics & Logging: late design change may invalidate completed qualification evidence | DIAG-LOG | Diagnostics & Logging | Support | P-016 | Priya Quintana | Payload | 2025-05-26 | 2026-05-15 | 2025-08-28 | 3 | 2 | 6 | Medium | Closed | 0 | 0 | 0 | 492 | Closed: mitigation completed and evidence attached to the verification record.
RAID-052 | Issue | Issue on Command & Telemetry Link: rig availability is below the rate needed to clear outstanding verification | COMM-LNK | Command & Telemetry Link | Mission | P-008 | Hiroshi Ibarra | Payload | 2025-12-03 | 2026-03-24 | 2025-12-31 | 2 | 3 | 6 | Medium | Closed | 0 | 0 | 0 | 301 | Closed: mitigation completed and evidence attached to the verification record.
RAID-054 | Assumption | Assumption on Navigation & Sensor Fusion: assumed unchanged from the previous airframe, not yet confirmed | NAV-SENS | Navigation & Sensor Fusion | Mission | P-012 | Liam Moreau | Payload | 2025-07-20 | 2025-11-04 | 2025-08-16 | 3 | 2 | 6 | Medium | Closed | 0 | 0 | 0 | 437 | Closed: mitigation completed and evidence attached to the verification record.
RAID-070 | Issue | Issue on Command & Telemetry Link: rig availability is below the rate needed to clear outstanding verification | COMM-LNK | Command & Telemetry Link | Mission | P-008 | Hiroshi Ibarra | Payload | 2025-12-27 | 2026-12-26 |  | 2 | 3 | 6 | Medium | Mitigating | 1 | 0 | 0 | 277 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-081 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-001 | Aditi Halvorsen | Avionics | 2025-09-25 | 2025-12-07 | 2025-10-12 | 2 | 3 | 6 | Medium | Closed | 0 | 0 | 0 | 370 | Closed: mitigation completed and evidence attached to the verification record.
RAID-082 | Dependency | Dependency on Navigation & Sensor Fusion: awaiting supplier confirmation before verification can close | NAV-SENS | Navigation & Sensor Fusion | Mission | P-002 | Bruno Oyelaran | Ground Segment | 2025-04-28 | 2025-04-17 | 2025-06-19 | 2 | 3 | 6 | Medium | Closed | 0 | 0 | 0 | 520 | Closed: mitigation completed and evidence attached to the verification record.
RAID-093 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-009 | Imani Petrovic | Avionics | 2025-04-21 | 2025-06-12 |  | 3 | 2 | 6 | Medium | Open | 1 | 1 | 475 | 527 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-095 | Issue | Issue on Power Management: rig availability is below the rate needed to clear outstanding verification | PWR-MGMT | Power Management | Mission | P-009 | Imani Petrovic | Avionics | 2026-03-12 | 2027-02-06 |  | 3 | 2 | 6 | Medium | Mitigating | 1 | 0 | 0 | 202 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-035 | Issue | Issue on Flight Control Interface: rig availability is below the rate needed to clear outstanding verification | FLT-CTRL | Flight Control Interface | Safety | P-005 | Elena Lindqvist | Avionics | 2025-01-23 | 2026-01-12 | 2025-04-27 | 5 | 1 | 5 | Medium | Closed | 0 | 0 | 0 | 615 | Closed: mitigation completed and evidence attached to the verification record.
RAID-006 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-010 | Jonas Weatherby | Ground Segment | 2025-08-12 | 2026-06-02 | 2025-10-29 | 4 | 1 | 4 | Low | Closed | 0 | 0 | 0 | 414 | Closed: mitigation completed and evidence attached to the verification record.
RAID-010 | Dependency | Dependency on Payload Release Mechanism: awaiting supplier confirmation before verification can close | REL-MECH | Payload Release Mechanism | Safety | P-002 | Bruno Oyelaran | Ground Segment | 2026-06-27 | 2027-01-20 | 2026-08-20 | 2 | 2 | 4 | Low | Closed | 0 | 0 | 0 | 95 | Closed: mitigation completed and evidence attached to the verification record.
RAID-019 | Risk | Risk on Command & Telemetry Link: late design change may invalidate completed qualification evidence | COMM-LNK | Command & Telemetry Link | Mission | P-014 | Nils Castellan | Ground Segment | 2026-03-29 | 2026-10-31 | 2026-05-24 | 4 | 1 | 4 | Low | Closed | 0 | 0 | 0 | 185 | Closed: mitigation completed and evidence attached to the verification record.
RAID-094 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | 2025-12-23 | 2026-07-14 | 2026-02-14 | 4 | 1 | 4 | Low | Closed | 0 | 0 | 0 | 281 | Closed: mitigation completed and evidence attached to the verification record.
RAID-002 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-015 | Olabisi Jindal | Integration & Test | 2026-06-23 | 2027-05-10 |  | 1 | 3 | 3 | Low | Open | 1 | 0 | 0 | 99 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-012 | Issue | Issue on Payload Release Mechanism: rig availability is below the rate needed to clear outstanding verification | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | 2025-05-27 | 2026-05-14 |  | 3 | 1 | 3 | Low | Open | 1 | 1 | 139 | 491 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-022 | Risk | Risk on Ground Control Software: late design change may invalidate completed qualification evidence | GND-CTRL | Ground Control Software | Support | P-015 | Olabisi Jindal | Integration & Test | 2026-01-31 | 2026-01-20 |  | 3 | 1 | 3 | Low | Mitigating | 1 | 0 | 0 | 242 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-023 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-016 | Priya Quintana | Payload | 2025-12-08 | 2026-12-16 | 2026-03-17 | 3 | 1 | 3 | Low | Closed | 0 | 0 | 0 | 296 | Closed: mitigation completed and evidence attached to the verification record.
RAID-024 | Dependency | Dependency on Power Management: awaiting supplier confirmation before verification can close | PWR-MGMT | Power Management | Mission | P-018 | Rafael Grigorescu | Ground Segment | 2025-03-31 | 2025-06-17 |  | 3 | 1 | 3 | Low | Mitigating | 1 | 1 | 470 | 548 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-026 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | 2025-04-15 | 2025-11-09 |  | 3 | 1 | 3 | Low | Open | 1 | 1 | 325 | 533 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-037 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-017 | Quentin Zielinski | Avionics | 2025-11-17 | 2025-11-06 |  | 3 | 1 | 3 | Low | Open | 1 | 0 | 0 | 317 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-038 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-019 | Sana Nakamura | Integration & Test | 2025-08-25 | 2026-06-19 |  | 1 | 3 | 3 | Low | Open | 1 | 1 | 103 | 401 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-040 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-001 | Aditi Halvorsen | Avionics | 2025-07-07 | 2026-07-14 | 2025-10-14 | 1 | 3 | 3 | Low | Closed | 0 | 0 | 0 | 450 | Closed: mitigation completed and evidence attached to the verification record.
RAID-046 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-021 | Ulrike Dalgleish | Avionics | 2025-05-13 | 2025-11-20 | 2025-07-01 | 1 | 3 | 3 | Low | Closed | 0 | 0 | 0 | 505 | Closed: mitigation completed and evidence attached to the verification record.
RAID-079 | Assumption | Assumption on Flight Control Interface: assumed unchanged from the previous airframe, not yet confirmed | FLT-CTRL | Flight Control Interface | Safety | P-006 | Farid Saltzman | Ground Segment | 2025-06-24 | 2026-04-05 | 2025-09-07 | 3 | 1 | 3 | Low | Closed | 0 | 0 | 0 | 463 | Closed: mitigation completed and evidence attached to the verification record.
RAID-085 | Risk | Risk on Payload Release Mechanism: late design change may invalidate completed qualification evidence | REL-MECH | Payload Release Mechanism | Safety | P-003 | Camille Villalobos | Integration & Test | 2026-02-27 | 2026-06-14 |  | 3 | 1 | 3 | Low | Open | 1 | 1 | 108 | 215 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-088 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-005 | Elena Lindqvist | Avionics | 2026-03-04 | 2026-11-02 | 2026-05-07 | 3 | 1 | 3 | Low | Closed | 0 | 0 | 0 | 210 | Closed: mitigation completed and evidence attached to the verification record.
RAID-013 | Dependency | Dependency on Payload Release Mechanism: awaiting supplier confirmation before verification can close | REL-MECH | Payload Release Mechanism | Safety | P-009 | Imani Petrovic | Avionics | 2026-01-15 | 2026-07-16 |  | 2 | 1 | 2 | Low | Open | 1 | 1 | 76 | 258 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-047 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-010 | Jonas Weatherby | Ground Segment | 2025-10-03 | 2026-01-08 |  | 2 | 1 | 2 | Low | Open | 1 | 1 | 265 | 362 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-063 | Risk | Risk on Flight Control Interface: late design change may invalidate completed qualification evidence | FLT-CTRL | Flight Control Interface | Safety | P-007 | Grace Baptiste | Integration & Test | 2026-05-10 | 2026-12-02 | 2026-07-03 | 2 | 1 | 2 | Low | Closed | 0 | 0 | 0 | 143 | Closed: mitigation completed and evidence attached to the verification record.
RAID-074 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-006 | Farid Saltzman | Ground Segment | 2025-04-03 | 2025-06-06 |  | 1 | 2 | 2 | Low | Open | 1 | 1 | 481 | 545 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-076 | Assumption | Assumption on Flight Control Interface: assumed unchanged from the previous airframe, not yet confirmed | FLT-CTRL | Flight Control Interface | Safety | P-009 | Imani Petrovic | Avionics | 2026-06-18 | 2027-03-16 |  | 2 | 1 | 2 | Low | Open | 1 | 0 | 0 | 104 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-007 | Risk | Risk on Power Management: late design change may invalidate completed qualification evidence | PWR-MGMT | Power Management | Mission | P-001 | Aditi Halvorsen | Avionics | 2025-06-29 | 2025-12-05 | 2025-08-09 | 1 | 1 | 1 | Low | Closed | 0 | 0 | 0 | 458 | Closed: mitigation completed and evidence attached to the verification record.
RAID-050 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-006 | Farid Saltzman | Ground Segment | 2026-05-11 | 2026-10-23 | 2026-06-22 | 1 | 1 | 1 | Low | Closed | 0 | 0 | 0 | 142 | Closed: mitigation completed and evidence attached to the verification record.
RAID-067 | Risk | Risk on Navigation & Sensor Fusion: late design change may invalidate completed qualification evidence | NAV-SENS | Navigation & Sensor Fusion | Mission | P-011 | Katya Fairweather | Integration & Test | 2025-12-07 | 2026-03-29 |  | 1 | 1 | 1 | Low | Open | 1 | 1 | 185 | 297 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-077 | Assumption | Assumption on Payload Release Mechanism: assumed unchanged from the previous airframe, not yet confirmed | REL-MECH | Payload Release Mechanism | Safety | P-004 | Dmitri Eriksen | Payload | 2025-02-08 | 2025-11-11 |  | 1 | 1 | 1 | Low | Open | 1 | 1 | 323 | 599 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-089 | Assumption | Assumption on Flight Control Interface: assumed unchanged from the previous airframe, not yet confirmed | FLT-CTRL | Flight Control Interface | Safety | P-014 | Nils Castellan | Ground Segment | 2025-07-10 | 2025-12-27 |  | 1 | 1 | 1 | Low | Open | 1 | 1 | 277 | 447 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-096 | Dependency | Dependency on Ground Control Software: awaiting supplier confirmation before verification can close | GND-CTRL | Ground Control Software | Support | P-005 | Elena Lindqvist | Avionics | 2025-01-12 | 2025-08-05 | 2025-03-06 | 1 | 1 | 1 | Low | Closed | 0 | 0 | 0 | 626 | Closed: mitigation completed and evidence attached to the verification record.

## Data_Work
WorkItemID | RequirementID | Priority | SubsystemCode | AssignedToID | AssignedToName | OpenedDate | ClosedDate | EstimateHours | ActualHours | WorkItemStatus
WI-0001 | REQ-0001 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-01-08 | 2025-02-01 | 18.7 | 19.1 | Closed
WI-0002 | REQ-0002 | ShouldShip | REL-MECH | P-017 | Quentin Zielinski | 2026-02-04 | 2026-02-14 | 12.2 | 10.3 | Closed
WI-0003 | REQ-0002 | ShouldShip | REL-MECH | P-012 | Liam Moreau | 2025-10-23 | 2025-11-23 | 35.2 | 39 | Closed
WI-0004 | REQ-0003 | Nice | NAV-SENS | P-020 | Tomas Ustinov | 2025-09-06 | 2025-10-31 | 25.7 | 36.4 | Closed
WI-0005 | REQ-0003 | Nice | NAV-SENS | P-011 | Katya Fairweather | 2025-04-14 | 2025-04-19 | 10.3 | 8 | Closed
WI-0006 | REQ-0004 | ShouldShip | PWR-MGMT | P-003 | Camille Villalobos | 2025-04-21 | 2025-05-04 | 16.5 | 14.5 | Closed
WI-0007 | REQ-0004 | ShouldShip | PWR-MGMT | P-019 | Sana Nakamura | 2026-03-10 | 2026-04-24 | 16.1 | 20.8 | Closed
WI-0008 | REQ-0005 | ShouldShip | COMM-LNK | P-002 | Bruno Oyelaran | 2026-05-10 | 2026-06-16 | 32.6 | 38.8 | Closed
WI-0009 | REQ-0005 | ShouldShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-05-27 | 2025-06-12 | 4.8 | 4.4 | Closed
WI-0010 | REQ-0005 | ShouldShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2025-08-22 | 2025-10-16 | 28.5 | 40.6 | Closed
WI-0011 | REQ-0006 | MustShip | STRUCT-I | P-014 | Nils Castellan | 2026-06-09 | 2026-06-15 | 33.7 | 27 | Closed
WI-0012 | REQ-0006 | MustShip | STRUCT-I | P-002 | Bruno Oyelaran | 2025-03-12 |  | 4.2 |  | InProgress
WI-0013 | REQ-0007 | ShouldShip | GND-CTRL | P-011 | Katya Fairweather | 2025-03-23 | 2025-04-18 | 17.2 | 17.9 | Closed
WI-0014 | REQ-0007 | ShouldShip | GND-CTRL | P-005 | Elena Lindqvist | 2025-07-23 | 2025-07-30 | 17.9 | 14.5 | Closed
WI-0015 | REQ-0007 | ShouldShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2025-06-12 |  | 20.4 |  | InProgress
WI-0016 | REQ-0008 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2025-06-29 | 2025-07-27 | 32.5 | 35.1 | Closed
WI-0017 | REQ-0008 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2026-05-27 | 2026-06-22 | 5 | 5.2 | Closed
WI-0018 | REQ-0008 | MustShip | COMM-LNK | P-015 | Olabisi Jindal | 2025-07-26 |  | 10 |  | Open
WI-0019 | REQ-0009 | MustShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-07-23 | 2025-07-26 | 22 | 16.5 | Closed
WI-0020 | REQ-0009 | MustShip | REL-MECH | P-013 | Mei Thackeray | 2026-01-18 | 2026-03-11 | 35.8 | 49.2 | Closed
WI-0021 | REQ-0009 | MustShip | REL-MECH | P-007 | Grace Baptiste | 2025-06-30 | 2025-07-22 | 4.2 | 4.2 | Closed
WI-0022 | REQ-0010 | MustShip | GND-CTRL | P-017 | Quentin Zielinski | 2026-04-10 | 2026-05-15 | 22.3 | 25.9 | Closed
WI-0023 | REQ-0011 | ShouldShip | NAV-SENS | P-011 | Katya Fairweather | 2025-01-06 | 2025-02-11 | 8.6 | 10.1 | Closed
WI-0024 | REQ-0011 | ShouldShip | NAV-SENS | P-002 | Bruno Oyelaran | 2025-09-18 | 2025-10-15 | 29.4 | 31.2 | Closed
WI-0025 | REQ-0012 | MustShip | DIAG-LOG | P-009 | Imani Petrovic | 2025-09-26 | 2025-10-09 | 10.1 | 8.9 | Closed
WI-0026 | REQ-0012 | MustShip | DIAG-LOG | P-018 | Rafael Grigorescu | 2026-02-15 | 2026-03-27 | 8.5 | 10.4 | Closed
WI-0027 | REQ-0013 | ShouldShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2026-01-20 | 2026-01-28 | 27 | 22.2 | Closed
WI-0028 | REQ-0014 | MustShip | STRUCT-I | P-018 | Rafael Grigorescu | 2026-05-17 | 2026-05-26 | 21.5 | 18 | Closed
WI-0029 | REQ-0014 | MustShip | STRUCT-I | P-003 | Camille Villalobos | 2026-05-08 | 2026-07-04 | 4.1 | 6 | Closed
WI-0030 | REQ-0015 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-12-08 | 2026-01-14 | 28.1 | 33.6 | Closed
WI-0031 | REQ-0015 | MustShip | PWR-MGMT | P-017 | Quentin Zielinski | 2026-04-10 | 2026-05-07 | 3 | 3.2 | Closed
WI-0032 | REQ-0015 | MustShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-05-13 | 2025-05-16 | 6.8 | 5.2 | Closed
WI-0033 | REQ-0015 | MustShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2025-03-15 | 2025-03-09 | 32.4 | 40.6 | Closed
WI-0034 | REQ-0016 | MustShip | GND-CTRL | P-006 | Farid Saltzman | 2025-03-21 | 2025-04-11 | 2 | 2 | Closed
WI-0035 | REQ-0017 | Nice | DIAG-LOG | P-006 | Farid Saltzman | 2025-09-19 | 2025-10-04 | 18.2 | 16.5 | Closed
WI-0036 | REQ-0018 | MustShip | STRUCT-I | P-002 | Bruno Oyelaran | 2026-01-05 |  | 23 |  | InProgress
WI-0037 | REQ-0019 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2025-05-10 | 2025-07-06 | 17.5 | 25.2 | Closed
WI-0038 | REQ-0020 | ShouldShip | FLT-CTRL | P-016 | Priya Quintana | 2025-09-01 | 2025-10-26 | 9.8 | 13.9 | Closed
WI-0039 | REQ-0020 | ShouldShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2026-04-18 | 2026-06-05 | 8.1 | 10.8 | Closed
WI-0040 | REQ-0020 | ShouldShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-09-16 | 2025-09-24 | 5.5 | 4.5 | Closed
WI-0041 | REQ-0021 | ShouldShip | PWR-MGMT | P-007 | Grace Baptiste | 2025-01-28 | 2025-02-15 | 32 | 30.4 | Closed
WI-0042 | REQ-0021 | ShouldShip | PWR-MGMT | P-018 | Rafael Grigorescu | 2025-10-04 | 2025-11-06 | 15 | 17.1 | Closed
WI-0043 | REQ-0022 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2026-04-19 | 2026-06-08 | 28.8 | 39 | Closed
WI-0044 | REQ-0023 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2025-08-07 | 2025-09-06 | 23.3 | 25.7 | Closed
WI-0045 | REQ-0024 | Nice | GND-CTRL | P-008 | Hiroshi Ibarra | 2025-08-19 | 2025-08-27 | 24.8 | 20.4 | Closed
WI-0046 | REQ-0024 | Nice | GND-CTRL | P-009 | Imani Petrovic | 2025-08-11 | 2025-09-06 | 24.3 | 25.6 | Closed
WI-0047 | REQ-0024 | Nice | GND-CTRL | P-018 | Rafael Grigorescu | 2025-05-27 | 2025-07-21 | 30.3 | 43.2 | Closed
WI-0048 | REQ-0025 | MustShip | FLT-CTRL | P-015 | Olabisi Jindal | 2025-12-06 | 2026-01-19 | 11.8 | 15 | Closed
WI-0049 | REQ-0026 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2026-01-15 | 2026-02-17 | 3.8 | 4.4 | Closed
WI-0050 | REQ-0027 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-06-18 | 2025-06-12 | 10.5 | 12.6 | Closed
WI-0051 | REQ-0028 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2026-03-05 | 2026-04-28 | 33.5 | 47.2 | Closed
WI-0052 | REQ-0029 | MustShip | NAV-SENS | P-004 | Dmitri Eriksen | 2025-08-02 | 2025-09-23 | 31.7 | 43.8 | Closed
WI-0053 | REQ-0030 | ShouldShip | COMM-LNK | P-005 | Elena Lindqvist | 2025-10-21 | 2025-12-17 | 2.3 | 3.3 | Closed
WI-0054 | REQ-0030 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-05-12 | 2025-05-29 | 11.2 | 10.5 | Closed
WI-0055 | REQ-0030 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2026-04-29 | 2026-05-24 | 32.8 | 33.8 | Closed
WI-0056 | REQ-0031 | Nice | REL-MECH | P-010 | Jonas Weatherby | 2025-10-22 | 2025-11-01 | 5.2 | 4.4 | Closed
WI-0057 | REQ-0031 | Nice | REL-MECH | P-002 | Bruno Oyelaran | 2025-09-12 | 2025-10-14 | 2.7 | 3.1 | Closed
WI-0058 | REQ-0031 | Nice | REL-MECH | P-016 | Priya Quintana | 2025-10-20 | 2025-11-18 | 11.7 | 12.7 | Closed
WI-0059 | REQ-0031 | Nice | REL-MECH | P-020 | Tomas Ustinov | 2025-08-13 | 2025-09-16 | 29.3 | 33.6 | Closed
WI-0060 | REQ-0032 | ShouldShip | COMM-LNK | P-020 | Tomas Ustinov | 2026-05-29 | 2026-06-15 | 30.6 | 28.4 | Closed
WI-0061 | REQ-0032 | ShouldShip | COMM-LNK | P-007 | Grace Baptiste | 2026-02-28 | 2026-03-31 | 13.5 | 15.1 | Closed
WI-0062 | REQ-0033 | MustShip | GND-CTRL | P-021 | Ulrike Dalgleish | 2025-07-12 | 2025-09-02 | 14.5 | 20.1 | Closed
WI-0063 | REQ-0034 | MustShip | FLT-CTRL | P-007 | Grace Baptiste | 2025-11-04 | 2025-12-27 | 17.6 | 24.6 | Closed
WI-0064 | REQ-0034 | MustShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2026-06-29 | 2026-07-13 | 21.2 | 19.1 | Closed
WI-0065 | REQ-0035 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-05-24 | 2026-07-17 | 29.3 | 41.3 | Closed
WI-0066 | REQ-0036 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-08-12 | 2025-09-17 | 8.9 | 10.5 | Closed
WI-0067 | REQ-0036 | MustShip | FLT-CTRL | P-008 | Hiroshi Ibarra | 2026-06-24 | 2026-08-07 | 27.4 | 35.1 | Closed
WI-0068 | REQ-0037 | ShouldShip | REL-MECH | P-009 | Imani Petrovic | 2026-01-28 | 2026-02-06 | 34.9 | 29.1 | Closed
WI-0069 | REQ-0037 | ShouldShip | REL-MECH | P-007 | Grace Baptiste | 2025-03-10 | 2025-04-10 | 2.6 | 2.9 | Closed
WI-0070 | REQ-0037 | ShouldShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-05-06 | 2025-05-31 | 23.3 | 24.2 | Closed
WI-0071 | REQ-0038 | MustShip | NAV-SENS | P-020 | Tomas Ustinov | 2025-04-24 | 2025-05-01 | 19.8 | 16 | Closed
WI-0072 | REQ-0038 | MustShip | NAV-SENS | P-002 | Bruno Oyelaran | 2025-08-26 | 2025-10-22 | 23.7 | 34.1 | Closed
WI-0073 | REQ-0038 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2025-01-24 | 2025-02-09 | 17.5 | 16.2 | Closed
WI-0074 | REQ-0039 | ShouldShip | GND-CTRL | P-011 | Katya Fairweather | 2025-01-21 | 2025-03-08 | 33.1 | 43.1 | Closed
WI-0075 | REQ-0039 | ShouldShip | GND-CTRL | P-001 | Aditi Halvorsen | 2026-01-17 | 2026-03-04 | 28.3 | 36.8 | Closed
WI-0076 | REQ-0039 | ShouldShip | GND-CTRL | P-007 | Grace Baptiste | 2025-02-02 | 2025-03-31 | 19.9 | 28.9 | Closed
WI-0077 | REQ-0040 | ShouldShip | NAV-SENS | P-015 | Olabisi Jindal | 2025-05-12 | 2025-05-25 | 13.1 | 11.5 | Closed
WI-0078 | REQ-0041 | MustShip | DIAG-LOG | P-021 | Ulrike Dalgleish | 2025-12-08 | 2026-01-21 | 8.5 | 10.9 | Closed
WI-0079 | REQ-0042 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2026-03-25 | 2026-04-06 | 17.6 | 15.4 | Closed
WI-0080 | REQ-0042 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2026-03-09 | 2026-03-12 | 25 | 18.9 | Closed
WI-0081 | REQ-0042 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2026-06-15 | 2026-07-22 | 31.8 | 37.8 | Closed
WI-0082 | REQ-0043 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2026-02-17 | 2026-03-08 | 35.3 | 34 | Closed
WI-0083 | REQ-0044 | ShouldShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2025-02-27 | 2025-04-24 | 14.5 | 20.6 | Closed
WI-0084 | REQ-0044 | ShouldShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-10-28 | 2025-11-25 | 24.7 | 26.6 | Closed
WI-0085 | REQ-0044 | ShouldShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-12-24 | 2026-01-06 | 20.8 | 18.3 | Closed
WI-0086 | REQ-0045 | MustShip | COMM-LNK | P-013 | Mei Thackeray | 2026-02-15 | 2026-04-03 | 31.5 | 41.3 | Closed
WI-0087 | REQ-0045 | MustShip | COMM-LNK | P-019 | Sana Nakamura | 2025-03-27 | 2025-05-21 | 3.8 | 5.3 | Closed
WI-0088 | REQ-0045 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2026-05-04 | 2026-05-30 | 28.1 | 29.3 | Closed
WI-0089 | REQ-0046 | MustShip | GND-CTRL | P-020 | Tomas Ustinov | 2026-04-09 | 2026-04-20 | 32.1 | 27.6 | Closed
WI-0090 | REQ-0046 | MustShip | GND-CTRL | P-011 | Katya Fairweather | 2025-07-16 |  | 34 |  | InProgress
WI-0091 | REQ-0046 | MustShip | GND-CTRL | P-004 | Dmitri Eriksen | 2025-05-10 | 2025-06-02 | 32.8 | 33.1 | Closed
WI-0092 | REQ-0047 | ShouldShip | NAV-SENS | P-005 | Elena Lindqvist | 2026-06-23 | 2026-07-18 | 13.7 | 14.1 | Closed
WI-0093 | REQ-0048 | Nice | COMM-LNK | P-002 | Bruno Oyelaran | 2025-11-24 | 2026-01-15 | 15.6 | 21.5 | Closed
WI-0094 | REQ-0048 | Nice | COMM-LNK | P-006 | Farid Saltzman | 2025-11-04 | 2025-12-04 | 30.5 | 33.7 | Closed
WI-0095 | REQ-0048 | Nice | COMM-LNK | P-010 | Jonas Weatherby | 2025-12-01 | 2025-12-17 | 16.4 | 15.2 | Closed
WI-0096 | REQ-0049 | MustShip | COMM-LNK | P-002 | Bruno Oyelaran | 2026-05-21 | 2026-05-28 | 9.8 | 8 | Closed
WI-0097 | REQ-0049 | MustShip | COMM-LNK | P-006 | Farid Saltzman | 2025-12-06 | 2026-01-15 | 12 | 14.8 | Closed
WI-0098 | REQ-0050 | MustShip | PWR-MGMT | P-010 | Jonas Weatherby | 2025-07-03 | 2025-07-17 | 4 | 3.6 | Closed
WI-0099 | REQ-0050 | MustShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-12-15 | 2026-01-24 | 35 | 42.9 | Closed
WI-0100 | REQ-0051 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2026-05-10 | 2026-06-04 | 19.1 | 19.8 | Closed
WI-0101 | REQ-0051 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2026-03-13 | 2026-04-08 | 3.8 | 3.9 | Closed
WI-0102 | REQ-0051 | MustShip | COMM-LNK | P-013 | Mei Thackeray | 2026-01-30 | 2026-03-18 | 20.8 | 27.4 | Closed
WI-0103 | REQ-0052 | ShouldShip | NAV-SENS | P-020 | Tomas Ustinov | 2025-08-09 | 2025-09-26 | 20.9 | 27.8 | Closed
WI-0104 | REQ-0052 | ShouldShip | NAV-SENS | P-011 | Katya Fairweather | 2026-06-17 | 2026-08-13 | 15.5 | 22.3 | Closed
WI-0105 | REQ-0052 | ShouldShip | NAV-SENS | P-019 | Sana Nakamura | 2025-07-22 | 2025-08-26 | 9.4 | 11 | Closed
WI-0106 | REQ-0053 | MustShip | REL-MECH | P-015 | Olabisi Jindal | 2025-05-27 | 2025-07-07 | 18.1 | 22.3 | Closed
WI-0107 | REQ-0053 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-10-11 | 2025-12-01 | 27.3 | 37.3 | Closed
WI-0108 | REQ-0053 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-12-14 | 2026-01-07 | 9.7 | 9.9 | Closed
WI-0109 | REQ-0054 | MustShip | NAV-SENS | P-015 | Olabisi Jindal | 2025-11-07 | 2025-12-13 | 12.7 | 14.9 | Closed
WI-0110 | REQ-0054 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2025-12-14 | 2026-01-09 | 19 | 19.9 | Closed
WI-0111 | REQ-0056 | Nice | REL-MECH | P-005 | Elena Lindqvist | 2025-04-22 | 2025-05-01 | 8.9 | 7.4 | Closed
WI-0112 | REQ-0056 | Nice | REL-MECH | P-021 | Ulrike Dalgleish | 2026-01-20 |  | 10.8 |  | InProgress
WI-0113 | REQ-0056 | Nice | REL-MECH | P-020 | Tomas Ustinov | 2026-05-03 |  | 31.3 |  | InProgress
WI-0114 | REQ-0056 | Nice | REL-MECH | P-013 | Mei Thackeray | 2025-03-19 | 2025-03-22 | 31.4 | 23.6 | Closed
WI-0115 | REQ-0057 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-05-13 | 2025-05-25 | 23.4 | 20.3 | Closed
WI-0116 | REQ-0057 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-04-09 | 2025-06-03 | 31.1 | 44 | Closed
WI-0117 | REQ-0058 | Nice | FLT-CTRL | P-010 | Jonas Weatherby | 2025-07-31 | 2025-09-05 | 20.4 | 23.9 | Closed
WI-0118 | REQ-0058 | Nice | FLT-CTRL | P-004 | Dmitri Eriksen | 2026-06-28 |  | 23 |  | Open
WI-0119 | REQ-0059 | MustShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-02-20 | 2025-04-17 | 28.8 | 41.3 | Closed
WI-0120 | REQ-0059 | MustShip | PWR-MGMT | P-007 | Grace Baptiste | 2025-11-23 | 2025-12-30 | 8.5 | 10.1 | Closed
WI-0121 | REQ-0060 | MustShip | FLT-CTRL | P-009 | Imani Petrovic | 2025-05-18 | 2025-06-04 | 34.7 | 32.5 | Closed
WI-0122 | REQ-0060 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2026-02-22 | 2026-04-03 | 3.7 | 4.5 | Closed
WI-0123 | REQ-0061 | Nice | PWR-MGMT | P-019 | Sana Nakamura | 2026-05-05 | 2026-05-17 | 27.9 | 24.1 | Closed
WI-0124 | REQ-0061 | Nice | PWR-MGMT | P-005 | Elena Lindqvist | 2026-03-01 | 2026-03-08 | 13.4 | 10.9 | Closed
WI-0125 | REQ-0061 | Nice | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-07-13 | 2025-08-05 | 18.9 | 19.2 | Closed
WI-0126 | REQ-0062 | MustShip | REL-MECH | P-002 | Bruno Oyelaran | 2025-07-02 | 2025-08-27 | 14.8 | 21.2 | Closed
WI-0127 | REQ-0062 | MustShip | REL-MECH | P-018 | Rafael Grigorescu | 2026-04-12 | 2026-06-06 | 27.9 | 39.8 | Closed
WI-0128 | REQ-0063 | MustShip | GND-CTRL | P-017 | Quentin Zielinski | 2026-02-27 | 2026-03-10 | 15.4 | 13.3 | Closed
WI-0129 | REQ-0063 | MustShip | GND-CTRL | P-002 | Bruno Oyelaran | 2025-07-27 | 2025-08-10 | 12.4 | 11 | Closed
WI-0130 | REQ-0063 | MustShip | GND-CTRL | P-018 | Rafael Grigorescu | 2025-01-25 | 2025-03-23 | 35.8 | 51.4 | Closed
WI-0131 | REQ-0064 | Nice | FLT-CTRL | P-010 | Jonas Weatherby | 2025-10-24 |  | 8.9 |  | InProgress
WI-0132 | REQ-0064 | Nice | FLT-CTRL | P-007 | Grace Baptiste | 2025-12-29 |  | 13.1 |  | Open
WI-0133 | REQ-0064 | Nice | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-09-26 | 2025-10-08 | 2.1 | 1.8 | Closed
WI-0134 | REQ-0065 | Nice | DIAG-LOG | P-005 | Elena Lindqvist | 2026-01-23 | 2026-03-11 | 31.2 | 41.3 | Closed
WI-0135 | REQ-0065 | Nice | DIAG-LOG | P-012 | Liam Moreau | 2026-05-22 | 2026-05-31 | 13.9 | 11.5 | Closed
WI-0136 | REQ-0065 | Nice | DIAG-LOG | P-005 | Elena Lindqvist | 2026-06-12 | 2026-06-18 | 2.5 | 2 | Closed
WI-0137 | REQ-0066 | Nice | PWR-MGMT | P-020 | Tomas Ustinov | 2025-06-22 | 2025-08-06 | 9 | 11.7 | Closed
WI-0138 | REQ-0066 | Nice | PWR-MGMT | P-012 | Liam Moreau | 2025-07-06 | 2025-07-22 | 2.7 | 2.5 | Closed
WI-0139 | REQ-0066 | Nice | PWR-MGMT | P-017 | Quentin Zielinski | 2025-08-04 | 2025-09-01 | 10.5 | 11.3 | Closed
WI-0140 | REQ-0067 | MustShip | GND-CTRL | P-014 | Nils Castellan | 2026-05-23 | 2026-06-05 | 33.9 | 29.8 | Closed
WI-0141 | REQ-0068 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-03-27 | 2025-04-10 | 9.1 | 8.2 | Closed
WI-0142 | REQ-0068 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2025-01-15 | 2025-03-08 | 17.2 | 23.7 | Closed
WI-0143 | REQ-0069 | MustShip | FLT-CTRL | P-013 | Mei Thackeray | 2025-02-01 |  | 15.9 |  | Open
WI-0144 | REQ-0069 | MustShip | FLT-CTRL | P-005 | Elena Lindqvist | 2025-06-12 | 2025-06-06 | 19.3 | 18.2 | Closed
WI-0145 | REQ-0070 | ShouldShip | COMM-LNK | P-002 | Bruno Oyelaran | 2025-11-30 | 2026-01-21 | 24.5 | 33.7 | Closed
WI-0146 | REQ-0070 | ShouldShip | COMM-LNK | P-007 | Grace Baptiste | 2025-04-15 | 2025-05-04 | 35.7 | 34.4 | Closed
WI-0147 | REQ-0071 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2026-06-01 | 2026-07-17 | 23.9 | 31.2 | Closed
WI-0148 | REQ-0072 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2025-06-25 | 2025-08-12 | 8 | 10.7 | Closed
WI-0149 | REQ-0072 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2025-12-08 | 2025-12-17 | 18.9 | 15.9 | Closed
WI-0150 | REQ-0073 | ShouldShip | COMM-LNK | P-002 | Bruno Oyelaran | 2025-04-24 | 2025-06-19 | 15.9 | 22.7 | Closed
WI-0151 | REQ-0073 | ShouldShip | COMM-LNK | P-005 | Elena Lindqvist | 2025-05-08 | 2025-05-20 | 19 | 16.6 | Closed
WI-0152 | REQ-0074 | MustShip | STRUCT-I | P-005 | Elena Lindqvist | 2025-11-18 | 2026-01-01 | 6 | 7.7 | Closed
WI-0153 | REQ-0074 | MustShip | STRUCT-I | P-018 | Rafael Grigorescu | 2025-10-08 | 2025-10-21 | 4.3 | 3.8 | Closed
WI-0154 | REQ-0075 | MustShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-07-13 | 2025-08-07 | 6.1 | 6.3 | Closed
WI-0155 | REQ-0075 | MustShip | PWR-MGMT | P-007 | Grace Baptiste | 2025-05-28 | 2025-06-05 | 10.6 | 8.7 | Closed
WI-0156 | REQ-0076 | Nice | GND-CTRL | P-009 | Imani Petrovic | 2026-05-03 | 2026-06-05 | 16.5 | 18.7 | Closed
WI-0157 | REQ-0076 | Nice | GND-CTRL | P-019 | Sana Nakamura | 2026-06-21 | 2026-07-14 | 14.4 | 14.6 | Closed
WI-0158 | REQ-0077 | ShouldShip | REL-MECH | P-012 | Liam Moreau | 2026-06-03 | 2026-07-30 | 22.6 | 32.5 | Closed
WI-0159 | REQ-0077 | ShouldShip | REL-MECH | P-012 | Liam Moreau | 2025-05-20 | 2025-06-07 | 14.4 | 13.7 | Closed
WI-0160 | REQ-0077 | ShouldShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-07-01 | 2025-08-19 | 35.2 | 47.4 | Closed
WI-0161 | REQ-0078 | ShouldShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-07-30 | 2025-09-04 | 21.9 | 25.7 | Closed
WI-0162 | REQ-0078 | ShouldShip | PWR-MGMT | P-005 | Elena Lindqvist | 2026-03-07 | 2026-03-21 | 13.5 | 12.1 | Closed
WI-0163 | REQ-0078 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2026-02-16 | 2026-03-12 | 2.8 | 2.9 | Closed
WI-0164 | REQ-0078 | ShouldShip | PWR-MGMT | P-015 | Olabisi Jindal | 2025-12-20 | 2025-12-23 | 16.8 | 12.7 | Closed
WI-0165 | REQ-0079 | Nice | DIAG-LOG | P-019 | Sana Nakamura | 2025-08-02 | 2025-09-26 | 17.4 | 24.7 | Closed
WI-0166 | REQ-0080 | MustShip | FLT-CTRL | P-005 | Elena Lindqvist | 2025-11-29 |  | 15.2 |  | Open
WI-0167 | REQ-0081 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-10-06 | 2025-11-03 | 35.5 | 38.1 | Closed
WI-0168 | REQ-0081 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-11-22 | 2026-01-07 | 12.7 | 16.5 | Closed
WI-0169 | REQ-0082 | ShouldShip | NAV-SENS | P-010 | Jonas Weatherby | 2026-03-02 | 2026-03-15 | 28.8 | 25.6 | Closed
WI-0170 | REQ-0083 | MustShip | REL-MECH | P-006 | Farid Saltzman | 2025-05-23 | 2025-07-04 | 33.6 | 42 | Closed
WI-0171 | REQ-0083 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2025-05-05 | 2025-05-12 | 17 | 13.7 | Closed
WI-0172 | REQ-0083 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2025-01-25 | 2025-03-17 | 9.3 | 12.7 | Closed
WI-0173 | REQ-0085 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2026-04-04 | 2026-05-24 | 31.1 | 42.2 | Closed
WI-0174 | REQ-0085 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2026-02-27 | 2026-03-04 | 17.2 | 13.5 | Closed
WI-0175 | REQ-0086 | ShouldShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2026-02-09 | 2026-03-01 | 11.1 | 10.7 | Closed
WI-0176 | REQ-0087 | ShouldShip | GND-CTRL | P-011 | Katya Fairweather | 2025-01-13 | 2025-03-08 | 32.6 | 46 | Closed
WI-0177 | REQ-0088 | ShouldShip | COMM-LNK | P-016 | Priya Quintana | 2025-12-21 | 2025-12-27 | 18.7 | 14.7 | Closed
WI-0178 | REQ-0088 | ShouldShip | COMM-LNK | P-018 | Rafael Grigorescu | 2025-06-18 | 2025-06-27 | 13 | 10.9 | Closed
WI-0179 | REQ-0088 | ShouldShip | COMM-LNK | P-012 | Liam Moreau | 2025-04-26 |  | 3.8 |  | InProgress
WI-0180 | REQ-0089 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2025-10-23 | 2025-11-04 | 25.5 | 22.3 | Closed
WI-0181 | REQ-0089 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-06-17 | 2025-08-09 | 24.8 | 34.7 | Closed
WI-0182 | REQ-0089 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2026-05-30 |  | 13.4 |  | Open
WI-0183 | REQ-0090 | ShouldShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-10-29 |  | 28.6 |  | Open
WI-0184 | REQ-0090 | ShouldShip | FLT-CTRL | P-014 | Nils Castellan | 2025-06-08 | 2025-08-02 | 5.7 | 8.1 | Closed
WI-0185 | REQ-0091 | ShouldShip | STRUCT-I | P-003 | Camille Villalobos | 2025-06-24 | 2025-07-20 | 10.3 | 10.8 | Closed
WI-0186 | REQ-0091 | ShouldShip | STRUCT-I | P-004 | Dmitri Eriksen | 2026-04-30 | 2026-05-17 | 14 | 13.1 | Closed
WI-0187 | REQ-0091 | ShouldShip | STRUCT-I | P-008 | Hiroshi Ibarra | 2025-05-25 | 2025-07-04 | 20.7 | 25.3 | Closed
WI-0188 | REQ-0092 | MustShip | STRUCT-I | P-011 | Katya Fairweather | 2025-03-20 | 2025-05-09 | 8.2 | 11.1 | Closed
WI-0189 | REQ-0092 | MustShip | STRUCT-I | P-014 | Nils Castellan | 2025-07-06 | 2025-07-15 | 31 | 25.8 | Closed
WI-0190 | REQ-0093 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-02-02 | 2025-03-20 | 20.7 | 26.9 | Closed
WI-0191 | REQ-0093 | MustShip | PWR-MGMT | P-014 | Nils Castellan | 2025-09-19 | 2025-10-28 | 14 | 16.9 | Closed
WI-0192 | REQ-0093 | MustShip | PWR-MGMT | P-012 | Liam Moreau | 2025-06-24 | 2025-08-03 | 5.4 | 6.6 | Closed
WI-0193 | REQ-0094 | MustShip | STRUCT-I | P-016 | Priya Quintana | 2025-06-29 | 2025-07-31 | 27.2 | 30.5 | Closed
WI-0194 | REQ-0094 | MustShip | STRUCT-I | P-011 | Katya Fairweather | 2025-05-25 | 2025-07-21 | 9.7 | 14 | Closed
WI-0195 | REQ-0094 | MustShip | STRUCT-I | P-016 | Priya Quintana | 2026-06-24 | 2026-07-21 | 33.1 | 35 | Closed
WI-0196 | REQ-0095 | Nice | COMM-LNK | P-020 | Tomas Ustinov | 2025-05-25 | 2025-07-14 | 17.7 | 23.9 | Closed
WI-0197 | REQ-0095 | Nice | COMM-LNK | P-015 | Olabisi Jindal | 2026-03-06 | 2026-03-31 | 9 | 9.3 | Closed
WI-0198 | REQ-0097 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-09-23 | 2025-09-26 | 35.7 | 27.1 | Closed
WI-0199 | REQ-0098 | ShouldShip | REL-MECH | P-009 | Imani Petrovic | 2026-03-16 | 2026-04-19 | 10.9 | 12.6 | Closed
WI-0200 | REQ-0099 | MustShip | COMM-LNK | P-005 | Elena Lindqvist | 2025-10-17 | 2025-11-27 | 8.8 | 10.9 | Closed
WI-0201 | REQ-0099 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-10-09 | 2025-11-09 | 26.2 | 29.1 | Closed
WI-0202 | REQ-0100 | MustShip | PWR-MGMT | P-017 | Quentin Zielinski | 2025-12-31 | 2026-02-05 | 21.2 | 24.9 | Closed
WI-0203 | REQ-0100 | MustShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2025-10-10 | 2025-10-18 | 27.7 | 22.8 | Closed
WI-0204 | REQ-0101 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-03-14 |  | 28.8 |  | Open
WI-0205 | REQ-0101 | ShouldShip | COMM-LNK | P-007 | Grace Baptiste | 2025-11-16 | 2026-01-05 | 17.1 | 23.1 | Closed
WI-0206 | REQ-0102 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2025-09-05 | 2025-10-23 | 15.4 | 20.5 | Closed
WI-0207 | REQ-0103 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2025-08-09 | 2025-09-01 | 5.4 | 5.5 | Closed
WI-0208 | REQ-0103 | ShouldShip | COMM-LNK | P-015 | Olabisi Jindal | 2025-07-14 | 2025-08-16 | 26.5 | 30.1 | Closed
WI-0209 | REQ-0104 | ShouldShip | STRUCT-I | P-021 | Ulrike Dalgleish | 2026-02-02 | 2026-03-14 | 33.3 | 41.1 | Closed
WI-0210 | REQ-0104 | ShouldShip | STRUCT-I | P-017 | Quentin Zielinski | 2025-05-16 | 2025-05-22 | 31.2 | 24.8 | Closed
WI-0211 | REQ-0105 | ShouldShip | DIAG-LOG | P-003 | Camille Villalobos | 2025-12-25 | 2026-02-06 | 6 | 7.7 | Closed
WI-0212 | REQ-0105 | ShouldShip | DIAG-LOG | P-008 | Hiroshi Ibarra | 2025-11-30 | 2026-01-05 | 34.5 | 40.7 | Closed
WI-0213 | REQ-0106 | MustShip | FLT-CTRL | P-003 | Camille Villalobos | 2026-05-24 | 2026-06-12 | 31.7 | 30.6 | Closed
WI-0214 | REQ-0106 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-06-21 | 2025-08-11 | 18.5 | 25.3 | Closed
WI-0215 | REQ-0106 | MustShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2026-02-20 | 2026-03-24 | 27.2 | 30.6 | Closed
WI-0216 | REQ-0107 | ShouldShip | GND-CTRL | P-018 | Rafael Grigorescu | 2026-06-17 | 2026-07-01 | 21.9 | 19.5 | Closed
WI-0217 | REQ-0108 | Nice | STRUCT-I | P-002 | Bruno Oyelaran | 2025-08-05 | 2025-09-15 | 29.8 | 36.9 | Closed
WI-0218 | REQ-0109 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-07-30 |  | 31.6 |  | InProgress
WI-0219 | REQ-0110 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2025-09-09 | 2025-10-24 | 3.6 | 4.7 | Closed
WI-0220 | REQ-0111 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2026-01-19 | 2026-02-25 | 34.5 | 41.2 | Closed
WI-0221 | REQ-0111 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2026-04-21 | 2026-05-07 | 8.4 | 7.7 | Closed
WI-0222 | REQ-0111 | ShouldShip | NAV-SENS | P-001 | Aditi Halvorsen | 2025-08-19 | 2025-08-24 | 28.2 | 21.9 | Closed
WI-0223 | REQ-0112 | ShouldShip | DIAG-LOG | P-020 | Tomas Ustinov | 2025-01-13 | 2025-03-07 | 26.4 | 36.7 | Closed
WI-0224 | REQ-0112 | ShouldShip | DIAG-LOG | P-018 | Rafael Grigorescu | 2025-11-22 | 2026-01-04 | 2.1 | 2.6 | Closed
WI-0225 | REQ-0113 | MustShip | REL-MECH | P-015 | Olabisi Jindal | 2025-02-06 | 2025-03-08 | 20.3 | 22.5 | Closed
WI-0226 | REQ-0114 | Nice | NAV-SENS | P-003 | Camille Villalobos | 2025-01-15 | 2025-01-26 | 28 | 24 | Closed
WI-0227 | REQ-0114 | Nice | NAV-SENS | P-007 | Grace Baptiste | 2025-10-25 | 2025-11-10 | 19.9 | 18.2 | Closed
WI-0228 | REQ-0114 | Nice | NAV-SENS | P-003 | Camille Villalobos | 2025-11-02 | 2025-12-18 | 14.4 | 18.8 | Closed
WI-0229 | REQ-0115 | MustShip | FLT-CTRL | P-008 | Hiroshi Ibarra | 2025-12-23 | 2026-01-07 | 9.7 | 8.9 | Closed
WI-0230 | REQ-0115 | MustShip | FLT-CTRL | P-017 | Quentin Zielinski | 2026-01-07 | 2026-01-21 | 15.9 | 14.3 | Closed
WI-0231 | REQ-0116 | MustShip | COMM-LNK | P-005 | Elena Lindqvist | 2025-06-09 | 2025-07-19 | 26.1 | 32.1 | Closed
WI-0232 | REQ-0117 | ShouldShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2026-01-16 | 2026-03-05 | 9.5 | 12.7 | Closed
WI-0233 | REQ-0117 | ShouldShip | GND-CTRL | P-010 | Jonas Weatherby | 2026-01-21 | 2026-02-01 | 9.3 | 8 | Closed
WI-0234 | REQ-0117 | ShouldShip | GND-CTRL | P-019 | Sana Nakamura | 2025-03-15 | 2025-04-25 | 3.6 | 4.4 | Closed
WI-0235 | REQ-0118 | MustShip | REL-MECH | P-014 | Nils Castellan | 2026-03-30 | 2026-04-23 | 34.9 | 35.7 | Closed
WI-0236 | REQ-0119 | Nice | PWR-MGMT | P-014 | Nils Castellan | 2025-04-09 | 2025-05-10 | 19.6 | 21.8 | Closed
WI-0237 | REQ-0120 | Nice | FLT-CTRL | P-015 | Olabisi Jindal | 2025-02-16 | 2025-03-27 | 15.3 | 18.6 | Closed
WI-0238 | REQ-0120 | Nice | FLT-CTRL | P-011 | Katya Fairweather | 2025-04-30 | 2025-06-08 | 4.5 | 5.4 | Closed
WI-0239 | REQ-0121 | ShouldShip | GND-CTRL | P-001 | Aditi Halvorsen | 2025-01-15 |  | 8.8 |  | InProgress
WI-0240 | REQ-0121 | ShouldShip | GND-CTRL | P-012 | Liam Moreau | 2026-04-13 | 2026-05-04 | 29.9 | 29.6 | Closed
WI-0241 | REQ-0121 | ShouldShip | GND-CTRL | P-005 | Elena Lindqvist | 2025-12-07 |  | 16.8 |  | InProgress
WI-0242 | REQ-0121 | ShouldShip | GND-CTRL | P-006 | Farid Saltzman | 2025-06-10 | 2025-07-02 | 3 | 3 | Closed
WI-0243 | REQ-0122 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2025-08-07 | 2025-09-28 | 19.9 | 27.4 | Closed
WI-0244 | REQ-0122 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2026-03-31 | 2026-04-12 | 8.1 | 7 | Closed
WI-0245 | REQ-0122 | MustShip | COMM-LNK | P-006 | Farid Saltzman | 2025-05-19 | 2025-07-04 | 23.5 | 30.7 | Closed
WI-0246 | REQ-0123 | Nice | FLT-CTRL | P-010 | Jonas Weatherby | 2026-05-15 | 2026-07-09 | 21 | 29.7 | Closed
WI-0247 | REQ-0123 | Nice | FLT-CTRL | P-009 | Imani Petrovic | 2025-12-26 | 2026-02-06 | 35.8 | 44.7 | Closed
WI-0248 | REQ-0123 | Nice | FLT-CTRL | P-009 | Imani Petrovic | 2026-01-19 | 2026-02-23 | 35.3 | 40.9 | Closed
WI-0249 | REQ-0124 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2025-06-13 | 2025-08-09 | 32.5 | 46.8 | Closed
WI-0250 | REQ-0124 | MustShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-08-31 | 2025-09-22 | 6.3 | 6.3 | Closed
WI-0251 | REQ-0125 | ShouldShip | FLT-CTRL | P-013 | Mei Thackeray | 2026-02-12 | 2026-04-01 | 8 | 10.6 | Closed
WI-0252 | REQ-0125 | ShouldShip | FLT-CTRL | P-005 | Elena Lindqvist | 2025-08-19 | 2025-09-29 | 29.6 | 36.6 | Closed
WI-0253 | REQ-0126 | Nice | COMM-LNK | P-012 | Liam Moreau | 2026-01-26 | 2026-03-24 | 17.5 | 25.2 | Closed
WI-0254 | REQ-0126 | Nice | COMM-LNK | P-018 | Rafael Grigorescu | 2025-03-20 | 2025-04-18 | 6.9 | 7.5 | Closed
WI-0255 | REQ-0127 | MustShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2026-04-24 | 2026-05-04 | 6.4 | 5.4 | Closed
WI-0256 | REQ-0128 | Nice | REL-MECH | P-015 | Olabisi Jindal | 2026-06-05 | 2026-07-16 | 12.9 | 16 | Closed
WI-0257 | REQ-0128 | Nice | REL-MECH | P-005 | Elena Lindqvist | 2026-01-28 | 2026-03-24 | 20 | 28.3 | Closed
WI-0258 | REQ-0128 | Nice | REL-MECH | P-008 | Hiroshi Ibarra | 2025-11-01 |  | 2.1 |  | InProgress
WI-0259 | REQ-0129 | Nice | FLT-CTRL | P-003 | Camille Villalobos | 2025-09-14 | 2025-11-02 | 10.2 | 13.7 | Closed
WI-0260 | REQ-0130 | ShouldShip | GND-CTRL | P-016 | Priya Quintana | 2025-11-23 | 2025-12-18 | 25.5 | 26.3 | Closed
WI-0261 | REQ-0130 | ShouldShip | GND-CTRL | P-010 | Jonas Weatherby | 2025-10-05 | 2025-10-19 | 23.4 | 21 | Closed
WI-0262 | REQ-0130 | ShouldShip | GND-CTRL | P-015 | Olabisi Jindal | 2025-12-07 | 2025-12-21 | 34.4 | 31.1 | Closed
WI-0263 | REQ-0131 | Nice | PWR-MGMT | P-009 | Imani Petrovic | 2025-06-27 | 2025-07-09 | 14.9 | 13 | Closed
WI-0264 | REQ-0131 | Nice | PWR-MGMT | P-018 | Rafael Grigorescu | 2026-04-20 | 2026-04-23 | 24.2 | 18.4 | Closed
WI-0265 | REQ-0132 | ShouldShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-11-08 | 2025-12-29 | 17.5 | 23.9 | Closed
WI-0266 | REQ-0132 | ShouldShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2025-01-08 | 2025-02-15 | 31.5 | 37.9 | Closed
WI-0267 | REQ-0132 | ShouldShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-04-05 | 2025-05-17 | 15.6 | 19.5 | Closed
WI-0268 | REQ-0133 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2026-04-15 | 2026-06-04 | 14 | 19 | Closed
WI-0269 | REQ-0134 | MustShip | GND-CTRL | P-013 | Mei Thackeray | 2026-01-16 |  | 6.6 |  | InProgress
WI-0270 | REQ-0134 | MustShip | GND-CTRL | P-021 | Ulrike Dalgleish | 2026-04-15 | 2026-06-01 | 26.6 | 34.8 | Closed
WI-0271 | REQ-0137 | MustShip | STRUCT-I | P-001 | Aditi Halvorsen | 2025-05-07 | 2025-05-01 | 12.9 | 14 | Closed
WI-0272 | REQ-0138 | Nice | FLT-CTRL | P-010 | Jonas Weatherby | 2025-11-27 | 2025-12-01 | 35.7 | 27.3 | Closed
WI-0273 | REQ-0138 | Nice | FLT-CTRL | P-012 | Liam Moreau | 2025-01-12 | 2025-01-23 | 14 | 12.1 | Closed
WI-0274 | REQ-0139 | ShouldShip | STRUCT-I | P-014 | Nils Castellan | 2025-02-21 | 2025-03-03 | 32.1 | 27.3 | Closed
WI-0275 | REQ-0140 | MustShip | PWR-MGMT | P-005 | Elena Lindqvist | 2025-05-23 | 2025-06-23 | 25.3 | 28.2 | Closed
WI-0276 | REQ-0141 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2026-03-23 | 2026-04-02 | 8.3 | 7 | Closed
WI-0277 | REQ-0141 | MustShip | REL-MECH | P-004 | Dmitri Eriksen | 2025-03-01 | 2025-03-09 | 21.7 | 17.9 | Closed
WI-0278 | REQ-0142 | MustShip | GND-CTRL | P-014 | Nils Castellan | 2026-03-14 |  | 3.5 |  | InProgress
WI-0279 | REQ-0143 | ShouldShip | REL-MECH | P-001 | Aditi Halvorsen | 2026-06-15 | 2026-07-04 | 15.3 | 14.7 | Closed
WI-0280 | REQ-0143 | ShouldShip | REL-MECH | P-015 | Olabisi Jindal | 2025-01-26 | 2025-02-09 | 21.7 | 19.4 | Closed
WI-0281 | REQ-0143 | ShouldShip | REL-MECH | P-021 | Ulrike Dalgleish | 2025-03-20 | 2025-04-20 | 13.1 | 14.6 | Closed
WI-0282 | REQ-0144 | MustShip | DIAG-LOG | P-002 | Bruno Oyelaran | 2025-04-19 | 2025-05-22 | 31 | 35.4 | Closed
WI-0283 | REQ-0144 | MustShip | DIAG-LOG | P-018 | Rafael Grigorescu | 2025-02-16 | 2025-04-14 | 5.5 | 7.9 | Closed
WI-0284 | REQ-0145 | Nice | DIAG-LOG | P-003 | Camille Villalobos | 2025-05-28 | 2025-07-06 | 9.8 | 11.8 | Closed
WI-0285 | REQ-0145 | Nice | DIAG-LOG | P-019 | Sana Nakamura | 2025-06-24 | 2025-08-06 | 14.8 | 18.7 | Closed
WI-0286 | REQ-0145 | Nice | DIAG-LOG | P-001 | Aditi Halvorsen | 2025-09-06 | 2025-10-14 | 12.3 | 14.8 | Closed
WI-0287 | REQ-0146 | MustShip | STRUCT-I | P-005 | Elena Lindqvist | 2025-02-04 | 2025-03-08 | 16.4 | 18.6 | Closed
WI-0288 | REQ-0146 | MustShip | STRUCT-I | P-018 | Rafael Grigorescu | 2025-07-15 | 2025-08-08 | 33.1 | 33.9 | Closed
WI-0289 | REQ-0147 | ShouldShip | REL-MECH | P-018 | Rafael Grigorescu | 2026-03-11 | 2026-04-23 | 7.8 | 9.9 | Closed
WI-0290 | REQ-0148 | ShouldShip | FLT-CTRL | P-014 | Nils Castellan | 2025-08-06 | 2025-08-14 | 4 | 3.3 | Closed
WI-0291 | REQ-0148 | ShouldShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2026-04-02 | 2026-04-11 | 20.8 | 17.3 | Closed
WI-0292 | REQ-0149 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-10-19 | 2025-11-08 | 12.9 | 12.5 | Closed
WI-0293 | REQ-0149 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-06-07 | 2025-07-08 | 35.9 | 39.9 | Closed
WI-0294 | REQ-0149 | MustShip | REL-MECH | P-021 | Ulrike Dalgleish | 2026-03-06 | 2026-04-12 | 20.1 | 24 | Closed
WI-0295 | REQ-0150 | ShouldShip | NAV-SENS | P-004 | Dmitri Eriksen | 2025-07-12 | 2025-08-19 | 17.9 | 21.6 | Closed
WI-0296 | REQ-0151 | Nice | PWR-MGMT | P-015 | Olabisi Jindal | 2025-05-23 | 2025-06-23 | 8 | 9 | Closed
WI-0297 | REQ-0152 | ShouldShip | DIAG-LOG | P-009 | Imani Petrovic | 2026-03-13 | 2026-04-18 | 9 | 10.6 | Closed
WI-0298 | REQ-0152 | ShouldShip | DIAG-LOG | P-020 | Tomas Ustinov | 2025-01-13 | 2025-02-13 | 16.5 | 18.4 | Closed
WI-0299 | REQ-0153 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-05-10 | 2025-06-13 | 20.5 | 23.5 | Closed
WI-0300 | REQ-0154 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-06-22 | 2025-08-11 | 17.8 | 24 | Closed
WI-0301 | REQ-0155 | MustShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2026-05-13 | 2026-05-29 | 27.1 | 24.9 | Closed
WI-0302 | REQ-0155 | MustShip | PWR-MGMT | P-018 | Rafael Grigorescu | 2026-01-21 | 2026-02-04 | 7.1 | 6.4 | Closed
WI-0303 | REQ-0156 | ShouldShip | GND-CTRL | P-019 | Sana Nakamura | 2025-09-10 | 2025-10-25 | 8.8 | 11.4 | Closed
WI-0304 | REQ-0157 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2026-05-09 | 2026-07-04 | 31.8 | 45.6 | Closed
WI-0305 | REQ-0157 | MustShip | REL-MECH | P-004 | Dmitri Eriksen | 2026-04-26 | 2026-06-05 | 32.1 | 39.4 | Closed
WI-0306 | REQ-0157 | MustShip | REL-MECH | P-021 | Ulrike Dalgleish | 2025-12-11 | 2025-12-20 | 21.5 | 18 | Closed
WI-0307 | REQ-0158 | MustShip | STRUCT-I | P-012 | Liam Moreau | 2025-03-25 | 2025-05-20 | 11.2 | 16 | Closed
WI-0308 | REQ-0158 | MustShip | STRUCT-I | P-001 | Aditi Halvorsen | 2025-12-05 | 2025-12-15 | 10.1 | 8.5 | Closed
WI-0309 | REQ-0159 | ShouldShip | NAV-SENS | P-001 | Aditi Halvorsen | 2025-02-28 | 2025-04-10 | 4.9 | 6 | Closed
WI-0310 | REQ-0159 | ShouldShip | NAV-SENS | P-020 | Tomas Ustinov | 2025-08-24 | 2025-10-18 | 12 | 17.1 | Closed
WI-0311 | REQ-0159 | ShouldShip | NAV-SENS | P-016 | Priya Quintana | 2025-10-27 | 2025-12-13 | 21.1 | 27.8 | Closed
WI-0312 | REQ-0160 | ShouldShip | NAV-SENS | P-006 | Farid Saltzman | 2026-06-24 | 2026-08-12 | 30.7 | 41 | Closed
WI-0313 | REQ-0160 | ShouldShip | NAV-SENS | P-020 | Tomas Ustinov | 2025-12-25 | 2026-01-08 | 21 | 18.9 | Closed
WI-0314 | REQ-0160 | ShouldShip | NAV-SENS | P-014 | Nils Castellan | 2026-06-09 | 2026-06-13 | 33.8 | 26.2 | Closed
WI-0315 | REQ-0161 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2026-04-14 | 2026-05-29 | 9.1 | 11.8 | Closed
WI-0316 | REQ-0161 | MustShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-10-11 | 2025-10-19 | 22.9 | 18.8 | Closed
WI-0317 | REQ-0161 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-12-17 | 2025-12-29 | 25.2 | 21.9 | Closed
WI-0318 | REQ-0161 | MustShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-03-18 |  | 19.4 |  | InProgress
WI-0319 | REQ-0162 | ShouldShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2026-04-07 | 2026-04-13 | 34.4 | 27.3 | Closed
WI-0320 | REQ-0163 | Nice | DIAG-LOG | P-003 | Camille Villalobos | 2025-04-18 | 2025-05-16 | 20.2 | 21.7 | Closed
WI-0321 | REQ-0164 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2026-03-20 | 2026-04-23 | 27.1 | 31.2 | Closed
WI-0322 | REQ-0164 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2025-11-02 |  | 20.1 |  | InProgress
WI-0323 | REQ-0164 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2026-04-27 | 2026-06-15 | 19.7 | 26.5 | Closed
WI-0324 | REQ-0165 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2026-06-06 | 2026-06-26 | 19.7 | 19.1 | Closed
WI-0325 | REQ-0165 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2025-07-28 | 2025-08-05 | 20.2 | 16.7 | Closed
WI-0326 | REQ-0165 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2026-03-22 | 2026-04-23 | 30.5 | 34.3 | Closed
WI-0327 | REQ-0166 | MustShip | REL-MECH | P-004 | Dmitri Eriksen | 2025-01-18 | 2025-02-14 | 14.3 | 15.2 | Closed
WI-0328 | REQ-0166 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-02-28 | 2025-04-12 | 2.1 | 2.7 | Closed
WI-0329 | REQ-0167 | MustShip | REL-MECH | P-016 | Priya Quintana | 2025-05-15 | 2025-05-27 | 4.8 | 4.2 | Closed
WI-0330 | REQ-0168 | MustShip | GND-CTRL | P-002 | Bruno Oyelaran | 2026-04-28 | 2026-06-03 | 27 | 31.8 | Closed
WI-0331 | REQ-0169 | MustShip | REL-MECH | P-016 | Priya Quintana | 2026-01-20 | 2026-02-18 | 2.5 | 2.7 | Closed
WI-0332 | REQ-0169 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-08-12 | 2025-09-03 | 7.7 | 7.7 | Closed
WI-0333 | REQ-0169 | MustShip | REL-MECH | P-013 | Mei Thackeray | 2025-02-28 | 2025-04-16 | 29.4 | 38.7 | Closed
WI-0334 | REQ-0170 | Nice | GND-CTRL | P-013 | Mei Thackeray | 2025-11-20 | 2025-12-21 | 5.8 | 6.5 | Closed
WI-0335 | REQ-0170 | Nice | GND-CTRL | P-001 | Aditi Halvorsen | 2025-05-13 | 2025-06-19 | 33.1 | 39.5 | Closed
WI-0336 | REQ-0171 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2025-08-20 | 2025-09-19 | 9.1 | 10 | Closed
WI-0337 | REQ-0171 | ShouldShip | PWR-MGMT | P-014 | Nils Castellan | 2025-05-13 | 2025-06-15 | 24.9 | 28.2 | Closed
WI-0338 | REQ-0171 | ShouldShip | PWR-MGMT | P-013 | Mei Thackeray | 2026-06-29 | 2026-07-20 | 18 | 17.7 | Closed
WI-0339 | REQ-0172 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-01-23 | 2025-02-04 | 32.9 | 28.4 | Closed
WI-0340 | REQ-0173 | MustShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2026-06-17 | 2026-08-08 | 13.2 | 18.2 | Closed
WI-0341 | REQ-0173 | MustShip | COMM-LNK | P-009 | Imani Petrovic | 2025-04-09 | 2025-05-11 | 28.1 | 31.7 | Closed
WI-0342 | REQ-0175 | MustShip | COMM-LNK | P-019 | Sana Nakamura | 2025-05-07 | 2025-05-18 | 10.9 | 9.3 | Closed
WI-0343 | REQ-0176 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2025-11-13 |  | 34.7 |  | Open
WI-0344 | REQ-0176 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2026-03-23 | 2026-04-21 | 9.7 | 10.5 | Closed
WI-0345 | REQ-0177 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-09-16 | 2025-11-02 | 20.6 | 27.2 | Closed
WI-0346 | REQ-0177 | MustShip | COMM-LNK | P-018 | Rafael Grigorescu | 2026-05-25 | 2026-06-09 | 10.2 | 9.3 | Closed
WI-0347 | REQ-0177 | MustShip | COMM-LNK | P-019 | Sana Nakamura | 2026-01-23 | 2026-02-03 | 19.8 | 17 | Closed
WI-0348 | REQ-0178 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-04-23 | 2025-05-10 | 17.3 | 16.2 | Closed
WI-0349 | REQ-0180 | Nice | GND-CTRL | P-005 | Elena Lindqvist | 2026-04-11 | 2026-05-18 | 27 | 32.2 | Closed
WI-0350 | REQ-0180 | Nice | GND-CTRL | P-011 | Katya Fairweather | 2026-02-12 | 2026-03-11 | 25.7 | 27.4 | Closed
WI-0351 | REQ-0181 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2026-03-15 |  | 24.1 |  | Open
WI-0352 | REQ-0181 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2025-09-14 | 2025-09-21 | 8.9 | 7.2 | Closed
WI-0353 | REQ-0182 | Nice | STRUCT-I | P-008 | Hiroshi Ibarra | 2025-05-14 | 2025-06-15 | 32.6 | 36.5 | Closed
WI-0354 | REQ-0182 | Nice | STRUCT-I | P-006 | Farid Saltzman | 2025-11-20 | 2025-12-23 | 24.9 | 28.2 | Closed
WI-0355 | REQ-0182 | Nice | STRUCT-I | P-017 | Quentin Zielinski | 2026-04-15 | 2026-05-28 | 35 | 44.3 | Closed
WI-0356 | REQ-0184 | Nice | PWR-MGMT | P-017 | Quentin Zielinski | 2026-04-01 | 2026-04-23 | 2.5 | 2.5 | Closed
WI-0357 | REQ-0185 | MustShip | GND-CTRL | P-019 | Sana Nakamura | 2025-09-06 | 2025-09-18 | 24.1 | 21 | Closed
WI-0358 | REQ-0185 | MustShip | GND-CTRL | P-011 | Katya Fairweather | 2025-08-15 | 2025-08-23 | 2.6 | 2.1 | Closed
WI-0359 | REQ-0186 | MustShip | NAV-SENS | P-014 | Nils Castellan | 2026-01-13 | 2026-03-05 | 14.7 | 20.1 | Closed
WI-0360 | REQ-0186 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2025-12-03 | 2025-12-23 | 25.7 | 24.9 | Closed
WI-0361 | REQ-0187 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-03-18 | 2025-04-10 | 25.7 | 25.9 | Closed
WI-0362 | REQ-0188 | ShouldShip | STRUCT-I | P-012 | Liam Moreau | 2025-08-20 | 2025-09-06 | 34.7 | 32.7 | Closed
WI-0363 | REQ-0189 | MustShip | FLT-CTRL | P-016 | Priya Quintana | 2025-07-13 | 2025-08-21 | 30.9 | 37.4 | Closed
WI-0364 | REQ-0190 | Nice | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-12-23 | 2026-01-08 | 29.6 | 27.2 | Closed
WI-0365 | REQ-0190 | Nice | COMM-LNK | P-017 | Quentin Zielinski | 2025-09-24 | 2025-11-20 | 21 | 30.4 | Closed
WI-0366 | REQ-0190 | Nice | COMM-LNK | P-012 | Liam Moreau | 2025-08-05 | 2025-09-19 | 21.9 | 28.2 | Closed
WI-0367 | REQ-0191 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-07-02 | 2025-07-27 | 31.6 | 32.9 | Closed
WI-0368 | REQ-0191 | MustShip | REL-MECH | P-006 | Farid Saltzman | 2025-10-03 | 2025-10-25 | 34.1 | 34.2 | Closed
WI-0369 | REQ-0191 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-11-18 | 2025-11-25 | 15.5 | 12.6 | Closed
WI-0370 | REQ-0193 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-04-07 | 2025-04-12 | 31.9 | 25 | Closed
WI-0371 | REQ-0193 | MustShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-01-28 | 2025-02-06 | 33.3 | 27.9 | Closed
WI-0372 | REQ-0193 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2025-08-18 | 2025-09-14 | 9.9 | 10.5 | Closed
WI-0373 | REQ-0194 | MustShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-09-07 | 2025-09-10 | 17.8 | 13.6 | Closed
WI-0374 | REQ-0194 | MustShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-02-22 | 2025-03-07 | 18.4 | 16.3 | Closed
WI-0375 | REQ-0195 | MustShip | NAV-SENS | P-011 | Katya Fairweather | 2025-03-06 | 2025-03-24 | 22.4 | 21.2 | Closed
WI-0376 | REQ-0195 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-04-29 | 2025-06-22 | 24.3 | 34.2 | Closed
WI-0377 | REQ-0195 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2026-03-05 | 2026-04-18 | 10.1 | 13 | Closed
WI-0378 | REQ-0196 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-06-28 | 2025-07-12 | 2.4 | 2.1 | Closed
WI-0379 | REQ-0196 | MustShip | COMM-LNK | P-002 | Bruno Oyelaran | 2026-05-12 | 2026-06-22 | 9 | 11.2 | Closed
WI-0380 | REQ-0196 | MustShip | COMM-LNK | P-006 | Farid Saltzman | 2025-06-14 | 2025-07-03 | 23.4 | 22.3 | Closed
WI-0381 | REQ-0196 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2025-08-18 | 2025-09-05 | 27.6 | 26.3 | Closed
WI-0382 | REQ-0197 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2026-06-07 | 2026-07-04 | 16.8 | 17.8 | Closed
WI-0383 | REQ-0197 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2026-06-01 | 2026-07-21 | 28.9 | 39.3 | Closed
WI-0384 | REQ-0197 | MustShip | NAV-SENS | P-006 | Farid Saltzman | 2026-04-01 | 2026-04-29 | 16.7 | 17.9 | Closed
WI-0385 | REQ-0198 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2026-04-24 | 2026-06-16 | 3.8 | 5.2 | Closed
WI-0386 | REQ-0198 | MustShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-10-01 |  | 22.7 |  | Open
WI-0387 | REQ-0198 | MustShip | REL-MECH | P-008 | Hiroshi Ibarra | 2026-04-13 | 2026-05-24 | 3 | 3.7 | Closed
WI-0388 | REQ-0199 | MustShip | DIAG-LOG | P-004 | Dmitri Eriksen | 2025-09-05 | 2025-10-01 | 33.6 | 35.1 | Closed
WI-0389 | REQ-0200 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2026-03-22 | 2026-04-25 | 12.3 | 14.2 | Closed
WI-0390 | REQ-0201 | ShouldShip | DIAG-LOG | P-003 | Camille Villalobos | 2025-03-06 | 2025-04-08 | 34.5 | 39.4 | Closed
WI-0391 | REQ-0201 | ShouldShip | DIAG-LOG | P-019 | Sana Nakamura | 2026-04-10 |  | 23.3 |  | Open
WI-0392 | REQ-0203 | MustShip | FLT-CTRL | P-019 | Sana Nakamura | 2025-12-11 | 2026-01-17 | 24 | 28.5 | Closed
WI-0393 | REQ-0204 | ShouldShip | NAV-SENS | P-010 | Jonas Weatherby | 2025-11-04 | 2025-12-12 | 16.4 | 19.7 | Closed
WI-0394 | REQ-0204 | ShouldShip | NAV-SENS | P-016 | Priya Quintana | 2025-01-23 | 2025-02-13 | 12.6 | 12.5 | Closed
WI-0395 | REQ-0205 | ShouldShip | PWR-MGMT | P-020 | Tomas Ustinov | 2026-03-03 | 2026-03-07 | 23.4 | 18 | Closed
WI-0396 | REQ-0206 | ShouldShip | NAV-SENS | P-014 | Nils Castellan | 2025-05-19 | 2025-06-08 | 12.1 | 11.7 | Closed
WI-0397 | REQ-0206 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2025-09-01 | 2025-09-27 | 29.2 | 30.7 | Closed
WI-0398 | REQ-0206 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2025-08-15 | 2025-08-20 | 31.9 | 24.9 | Closed
WI-0399 | REQ-0207 | ShouldShip | DIAG-LOG | P-018 | Rafael Grigorescu | 2025-02-10 | 2025-03-21 | 25.1 | 30.5 | Closed
WI-0400 | REQ-0207 | ShouldShip | DIAG-LOG | P-009 | Imani Petrovic | 2026-01-21 | 2026-02-14 | 34.6 | 35.5 | Closed
WI-0401 | REQ-0207 | ShouldShip | DIAG-LOG | P-021 | Ulrike Dalgleish | 2025-12-23 | 2026-01-23 | 18.6 | 20.7 | Closed
WI-0402 | REQ-0207 | ShouldShip | DIAG-LOG | P-005 | Elena Lindqvist | 2025-11-25 | 2026-01-15 | 22.9 | 31.4 | Closed
WI-0403 | REQ-0208 | MustShip | FLT-CTRL | P-016 | Priya Quintana | 2025-11-26 | 2025-12-17 | 31.5 | 30.8 | Closed
WI-0404 | REQ-0209 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2025-03-11 | 2025-04-23 | 6.4 | 8.1 | Closed
WI-0405 | REQ-0210 | MustShip | FLT-CTRL | P-019 | Sana Nakamura | 2026-03-29 | 2026-05-16 | 28.2 | 37.6 | Closed
WI-0406 | REQ-0210 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2025-07-31 | 2025-09-14 | 25.6 | 33 | Closed
WI-0407 | REQ-0210 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-11-28 | 2025-12-24 | 29.8 | 31.4 | Closed
WI-0408 | REQ-0211 | MustShip | REL-MECH | P-007 | Grace Baptiste | 2025-03-20 | 2025-04-24 | 4.4 | 5.1 | Closed
WI-0409 | REQ-0211 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-02-04 | 2025-02-16 | 13.9 | 12.1 | Closed
WI-0410 | REQ-0211 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-01-10 | 2025-02-08 | 27.6 | 30.1 | Closed
WI-0411 | REQ-0212 | ShouldShip | DIAG-LOG | P-013 | Mei Thackeray | 2025-03-08 | 2025-03-02 | 8.5 | 9.2 | Closed
WI-0412 | REQ-0212 | ShouldShip | DIAG-LOG | P-010 | Jonas Weatherby | 2026-04-29 | 2026-05-09 | 29.2 | 24.6 | Closed
WI-0413 | REQ-0212 | ShouldShip | DIAG-LOG | P-019 | Sana Nakamura | 2025-01-11 | 2025-01-30 | 30.9 | 29.6 | Closed
WI-0414 | REQ-0213 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2026-03-08 | 2026-03-30 | 12.8 | 12.8 | Closed
WI-0415 | REQ-0213 | ShouldShip | COMM-LNK | P-012 | Liam Moreau | 2026-03-22 | 2026-04-07 | 29.3 | 26.8 | Closed
WI-0416 | REQ-0213 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2026-05-28 |  | 7.4 |  | Open
WI-0417 | REQ-0214 | Nice | GND-CTRL | P-005 | Elena Lindqvist | 2026-04-11 |  | 32.8 |  | Open
WI-0418 | REQ-0214 | Nice | GND-CTRL | P-009 | Imani Petrovic | 2025-03-01 | 2025-04-06 | 13.6 | 16 | Closed
WI-0419 | REQ-0215 | Nice | NAV-SENS | P-009 | Imani Petrovic | 2025-07-23 | 2025-09-17 | 28.6 | 40.8 | Closed
WI-0420 | REQ-0215 | Nice | NAV-SENS | P-019 | Sana Nakamura | 2025-03-17 | 2025-03-25 | 35.5 | 29 | Closed
WI-0421 | REQ-0215 | Nice | NAV-SENS | P-020 | Tomas Ustinov | 2025-11-19 | 2026-01-04 | 35.1 | 45.9 | Closed
WI-0422 | REQ-0216 | Nice | COMM-LNK | P-020 | Tomas Ustinov | 2026-06-01 | 2026-06-23 | 27.3 | 27.2 | Closed
WI-0423 | REQ-0216 | Nice | COMM-LNK | P-018 | Rafael Grigorescu | 2025-03-12 | 2025-04-13 | 10.2 | 11.5 | Closed
WI-0424 | REQ-0216 | Nice | COMM-LNK | P-002 | Bruno Oyelaran | 2025-06-07 | 2025-07-19 | 34.4 | 43.2 | Closed
WI-0425 | REQ-0217 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2026-05-26 | 2026-07-21 | 6.6 | 9.4 | Closed
WI-0426 | REQ-0218 | MustShip | PWR-MGMT | P-003 | Camille Villalobos | 2025-09-19 | 2025-10-24 | 23.2 | 27 | Closed
WI-0427 | REQ-0218 | MustShip | PWR-MGMT | P-006 | Farid Saltzman | 2026-06-13 |  | 15.5 |  | InProgress
WI-0428 | REQ-0218 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-02-22 |  | 34.2 |  | InProgress
WI-0429 | REQ-0219 | MustShip | GND-CTRL | P-009 | Imani Petrovic | 2026-06-03 | 2026-07-06 | 13.2 | 15.1 | Closed
WI-0430 | REQ-0219 | MustShip | GND-CTRL | P-001 | Aditi Halvorsen | 2025-06-08 | 2025-06-20 | 34.4 | 29.9 | Closed
WI-0431 | REQ-0219 | MustShip | GND-CTRL | P-013 | Mei Thackeray | 2025-08-05 | 2025-08-19 | 19.1 | 17.2 | Closed
WI-0432 | REQ-0220 | Nice | NAV-SENS | P-013 | Mei Thackeray | 2025-04-28 | 2025-06-19 | 29.2 | 40.4 | Closed
WI-0433 | REQ-0221 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2026-04-29 | 2026-05-23 | 19.1 | 19.5 | Closed
WI-0434 | REQ-0222 | ShouldShip | REL-MECH | P-015 | Olabisi Jindal | 2026-06-22 | 2026-08-07 | 20.8 | 27.1 | Closed
WI-0435 | REQ-0223 | MustShip | GND-CTRL | P-010 | Jonas Weatherby | 2025-12-08 | 2026-01-18 | 31.4 | 39.2 | Closed
WI-0436 | REQ-0223 | MustShip | GND-CTRL | P-020 | Tomas Ustinov | 2026-06-15 | 2026-07-19 | 35.9 | 41.5 | Closed
WI-0437 | REQ-0224 | MustShip | COMM-LNK | P-006 | Farid Saltzman | 2025-01-31 | 2025-03-10 | 5.6 | 6.7 | Closed
WI-0438 | REQ-0224 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2025-05-05 | 2025-06-30 | 29.8 | 42.5 | Closed
WI-0439 | REQ-0224 | MustShip | COMM-LNK | P-013 | Mei Thackeray | 2026-05-14 | 2026-07-07 | 32.9 | 46.5 | Closed
WI-0440 | REQ-0225 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-02-26 | 2025-03-28 | 5.3 | 5.9 | Closed
WI-0441 | REQ-0225 | MustShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-12-22 | 2026-02-11 | 28.5 | 39.1 | Closed
WI-0442 | REQ-0225 | MustShip | FLT-CTRL | P-014 | Nils Castellan | 2025-04-06 | 2025-05-03 | 8.1 | 8.6 | Closed
WI-0443 | REQ-0226 | ShouldShip | STRUCT-I | P-011 | Katya Fairweather | 2025-07-24 | 2025-09-04 | 27.1 | 33.8 | Closed
WI-0444 | REQ-0227 | ShouldShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-11-04 | 2025-12-28 | 17.5 | 24.5 | Closed
WI-0445 | REQ-0228 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2026-06-17 | 2026-06-30 | 10.1 | 8.9 | Closed
WI-0446 | REQ-0228 | MustShip | COMM-LNK | P-007 | Grace Baptiste | 2025-10-27 |  | 8.4 |  | InProgress
WI-0447 | REQ-0229 | MustShip | PWR-MGMT | P-016 | Priya Quintana | 2025-06-27 | 2025-08-08 | 2.8 | 3.5 | Closed
WI-0448 | REQ-0230 | Nice | FLT-CTRL | P-016 | Priya Quintana | 2025-04-02 | 2025-05-03 | 13.1 | 14.6 | Closed
WI-0449 | REQ-0230 | Nice | FLT-CTRL | P-012 | Liam Moreau | 2025-12-09 |  | 20.4 |  | Open
WI-0450 | REQ-0231 | ShouldShip | COMM-LNK | P-017 | Quentin Zielinski | 2025-01-28 | 2025-03-19 | 13 | 17.7 | Closed
WI-0451 | REQ-0231 | ShouldShip | COMM-LNK | P-010 | Jonas Weatherby | 2025-03-29 | 2025-05-25 | 20 | 28.9 | Closed
WI-0452 | REQ-0232 | ShouldShip | REL-MECH | P-020 | Tomas Ustinov | 2025-02-18 | 2025-02-21 | 28.7 | 21.6 | Closed
WI-0453 | REQ-0233 | MustShip | NAV-SENS | P-006 | Farid Saltzman | 2026-03-14 | 2026-04-10 | 16.7 | 17.8 | Closed
WI-0454 | REQ-0233 | MustShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2025-01-16 | 2025-03-13 | 12.4 | 17.7 | Closed
WI-0455 | REQ-0234 | ShouldShip | GND-CTRL | P-002 | Bruno Oyelaran | 2025-12-26 | 2026-01-12 | 19 | 17.7 | Closed
WI-0456 | REQ-0234 | ShouldShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2026-04-11 | 2026-05-22 | 35.9 | 44.5 | Closed
WI-0457 | REQ-0234 | ShouldShip | GND-CTRL | P-016 | Priya Quintana | 2025-03-02 | 2025-03-06 | 2.5 | 2 | Closed
WI-0458 | REQ-0235 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-02-01 | 2025-03-18 | 33.4 | 43.3 | Closed
WI-0459 | REQ-0235 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2025-09-07 | 2025-11-02 | 27.8 | 39.7 | Closed
WI-0460 | REQ-0235 | MustShip | FLT-CTRL | P-014 | Nils Castellan | 2025-02-17 | 2025-02-25 | 21.7 | 17.8 | Closed
WI-0461 | REQ-0236 | ShouldShip | GND-CTRL | P-017 | Quentin Zielinski | 2025-09-07 | 2025-10-18 | 9.5 | 11.8 | Closed
WI-0462 | REQ-0236 | ShouldShip | GND-CTRL | P-017 | Quentin Zielinski | 2025-08-25 | 2025-09-11 | 18.7 | 17.5 | Closed
WI-0463 | REQ-0237 | ShouldShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-09-16 | 2025-10-04 | 10.6 | 10 | Closed
WI-0464 | REQ-0237 | ShouldShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-02-10 | 2025-03-25 | 15 | 19.1 | Closed
WI-0465 | REQ-0239 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2026-02-13 | 2026-02-28 | 20.3 | 18.5 | Closed
WI-0466 | REQ-0239 | ShouldShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-05-11 | 2025-05-23 | 32 | 27.8 | Closed
WI-0467 | REQ-0240 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2025-05-29 | 2025-06-05 | 18.6 | 15 | Closed
WI-0468 | REQ-0241 | Nice | GND-CTRL | P-011 | Katya Fairweather | 2025-03-12 | 2025-03-23 | 19.4 | 16.7 | Closed
WI-0469 | REQ-0241 | Nice | GND-CTRL | P-013 | Mei Thackeray | 2026-06-21 | 2026-07-15 | 14.7 | 15.1 | Closed
WI-0470 | REQ-0241 | Nice | GND-CTRL | P-007 | Grace Baptiste | 2025-08-18 | 2025-09-05 | 28.8 | 27.4 | Closed
WI-0471 | REQ-0242 | MustShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-07-09 | 2025-07-23 | 30.2 | 27.1 | Closed
WI-0472 | REQ-0242 | MustShip | COMM-LNK | P-015 | Olabisi Jindal | 2026-01-14 | 2026-02-12 | 18.9 | 20.5 | Closed
WI-0473 | REQ-0243 | ShouldShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-11-23 | 2025-12-31 | 31.3 | 37.6 | Closed
WI-0474 | REQ-0243 | ShouldShip | FLT-CTRL | P-015 | Olabisi Jindal | 2026-06-12 | 2026-08-07 | 10.5 | 15.1 | Closed
WI-0475 | REQ-0244 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2025-02-09 | 2025-03-12 | 35.9 | 39.9 | Closed
WI-0476 | REQ-0244 | ShouldShip | COMM-LNK | P-006 | Farid Saltzman | 2025-09-17 | 2025-11-10 | 27.3 | 38.5 | Closed
WI-0477 | REQ-0244 | ShouldShip | COMM-LNK | P-014 | Nils Castellan | 2025-06-12 | 2025-07-21 | 33.3 | 40.5 | Closed
WI-0478 | REQ-0245 | ShouldShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-04-14 | 2026-05-26 | 32.7 | 40.8 | Closed
WI-0479 | REQ-0245 | ShouldShip | FLT-CTRL | P-016 | Priya Quintana | 2026-04-07 | 2026-05-22 | 26.9 | 34.7 | Closed
WI-0480 | REQ-0246 | MustShip | REL-MECH | P-012 | Liam Moreau | 2026-03-12 | 2026-04-14 | 29.3 | 33.4 | Closed
WI-0481 | REQ-0247 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-02-23 | 2025-03-29 | 26.1 | 29.9 | Closed
WI-0482 | REQ-0248 | ShouldShip | PWR-MGMT | P-012 | Liam Moreau | 2025-02-18 | 2025-02-28 | 32.7 | 27.6 | Closed
WI-0483 | REQ-0248 | ShouldShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-01-20 | 2025-03-03 | 4 | 5 | Closed
WI-0484 | REQ-0249 | MustShip | COMM-LNK | P-017 | Quentin Zielinski | 2026-02-17 | 2026-03-09 | 29.4 | 28.5 | Closed
WI-0485 | REQ-0249 | MustShip | COMM-LNK | P-005 | Elena Lindqvist | 2026-05-01 | 2026-05-16 | 29.9 | 27.2 | Closed
WI-0486 | REQ-0249 | MustShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-01-13 | 2025-03-09 | 15.6 | 22.2 | Closed
WI-0487 | REQ-0250 | Nice | DIAG-LOG | P-005 | Elena Lindqvist | 2025-06-02 | 2025-07-16 | 17.5 | 22.3 | Closed
WI-0488 | REQ-0250 | Nice | DIAG-LOG | P-005 | Elena Lindqvist | 2026-05-09 | 2026-05-30 | 32.5 | 32.1 | Closed
WI-0489 | REQ-0250 | Nice | DIAG-LOG | P-007 | Grace Baptiste | 2025-03-14 | 2025-04-17 | 7.6 | 8.8 | Closed
WI-0490 | REQ-0251 | MustShip | GND-CTRL | P-002 | Bruno Oyelaran | 2025-10-08 | 2025-11-18 | 8.3 | 10.3 | Closed
WI-0491 | REQ-0251 | MustShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2026-01-21 | 2026-03-11 | 33.6 | 45.3 | Closed
WI-0492 | REQ-0252 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2025-08-01 | 2025-08-28 | 19.4 | 20.5 | Closed
WI-0493 | REQ-0253 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-03-04 | 2025-04-20 | 26.6 | 35.1 | Closed
WI-0494 | REQ-0254 | ShouldShip | COMM-LNK | P-018 | Rafael Grigorescu | 2025-11-03 | 2025-11-08 | 9.6 | 7.5 | Closed
WI-0495 | REQ-0254 | ShouldShip | COMM-LNK | P-016 | Priya Quintana | 2025-05-23 | 2025-05-27 | 8.5 | 6.5 | Closed
WI-0496 | REQ-0254 | ShouldShip | COMM-LNK | P-014 | Nils Castellan | 2025-07-24 | 2025-08-20 | 12.5 | 13.2 | Closed
WI-0497 | REQ-0255 | ShouldShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2026-02-21 | 2026-03-31 | 4 | 4.8 | Closed
WI-0498 | REQ-0255 | ShouldShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-08-31 | 2025-09-12 | 7.3 | 6.3 | Closed
WI-0499 | REQ-0255 | ShouldShip | FLT-CTRL | P-009 | Imani Petrovic | 2025-10-27 | 2025-11-07 | 19.1 | 16.3 | Closed
WI-0500 | REQ-0256 | ShouldShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-11-09 | 2025-12-06 | 4.6 | 4.8 | Closed
WI-0501 | REQ-0256 | ShouldShip | PWR-MGMT | P-012 | Liam Moreau | 2025-06-08 | 2025-06-02 | 35.8 | 33 | Closed
WI-0502 | REQ-0256 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2026-04-21 | 2026-06-02 | 18.2 | 22.7 | Closed
WI-0503 | REQ-0257 | MustShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2025-02-23 | 2025-03-08 | 15.1 | 13.3 | Closed
WI-0504 | REQ-0258 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2026-06-09 | 2026-07-01 | 22 | 21.9 | Closed
WI-0505 | REQ-0259 | ShouldShip | GND-CTRL | P-020 | Tomas Ustinov | 2025-01-16 | 2025-02-16 | 28.9 | 32 | Closed
WI-0506 | REQ-0259 | ShouldShip | GND-CTRL | P-006 | Farid Saltzman | 2025-09-11 | 2025-10-09 | 29.7 | 31.7 | Closed
WI-0507 | REQ-0260 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2026-05-29 | 2026-06-06 | 18.6 | 15.2 | Closed
WI-0508 | REQ-0261 | ShouldShip | GND-CTRL | P-006 | Farid Saltzman | 2026-04-02 | 2026-05-26 | 11.1 | 15.6 | Closed
WI-0509 | REQ-0262 | ShouldShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-11-16 | 2025-12-24 | 5.8 | 7 | Closed
WI-0510 | REQ-0262 | ShouldShip | REL-MECH | P-017 | Quentin Zielinski | 2025-09-09 | 2025-09-25 | 30.1 | 27.7 | Closed
WI-0511 | REQ-0262 | ShouldShip | REL-MECH | P-003 | Camille Villalobos | 2026-04-25 | 2026-05-08 | 2.4 | 2.2 | Closed
WI-0512 | REQ-0263 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2026-05-08 | 2026-06-24 | 9.9 | 13 | Closed
WI-0513 | REQ-0263 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2026-01-17 | 2026-03-11 | 17.8 | 24.8 | Closed
WI-0514 | REQ-0263 | MustShip | COMM-LNK | P-013 | Mei Thackeray | 2025-03-27 | 2025-04-02 | 33.1 | 26.3 | Closed
WI-0515 | REQ-0264 | MustShip | STRUCT-I | P-008 | Hiroshi Ibarra | 2026-02-05 | 2026-02-24 | 34.4 | 32.9 | Closed
WI-0516 | REQ-0264 | MustShip | STRUCT-I | P-020 | Tomas Ustinov | 2025-06-10 | 2025-06-15 | 16.8 | 13.1 | Closed
WI-0517 | REQ-0264 | MustShip | STRUCT-I | P-001 | Aditi Halvorsen | 2026-02-14 | 2026-03-17 | 35.7 | 39.7 | Closed
WI-0518 | REQ-0265 | MustShip | NAV-SENS | P-003 | Camille Villalobos | 2026-04-19 | 2026-04-29 | 3.8 | 3.2 | Closed
WI-0519 | REQ-0265 | MustShip | NAV-SENS | P-006 | Farid Saltzman | 2025-02-28 | 2025-04-24 | 8 | 11.3 | Closed
WI-0520 | REQ-0266 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2025-04-15 | 2025-05-21 | 19.4 | 22.7 | Closed
WI-0521 | REQ-0266 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2025-11-05 | 2025-11-08 | 2.3 | 1.8 | Closed
WI-0522 | REQ-0267 | Nice | PWR-MGMT | P-013 | Mei Thackeray | 2026-04-27 | 2026-06-20 | 28.4 | 39.9 | Closed
WI-0523 | REQ-0267 | Nice | PWR-MGMT | P-013 | Mei Thackeray | 2025-10-24 | 2025-12-06 | 4.6 | 5.8 | Closed
WI-0524 | REQ-0267 | Nice | PWR-MGMT | P-003 | Camille Villalobos | 2025-06-26 | 2025-08-20 | 14.3 | 20.3 | Closed
WI-0525 | REQ-0268 | MustShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-05-09 | 2025-06-16 | 2.1 | 2.5 | Closed
WI-0526 | REQ-0268 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2025-12-02 |  | 18.9 |  | InProgress
WI-0527 | REQ-0269 | MustShip | REL-MECH | P-014 | Nils Castellan | 2026-05-02 | 2026-05-22 | 29.3 | 28.7 | Closed
WI-0528 | REQ-0269 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2026-03-31 | 2026-04-20 | 16.3 | 15.9 | Closed
WI-0529 | REQ-0269 | MustShip | REL-MECH | P-006 | Farid Saltzman | 2025-02-05 | 2025-03-17 | 15.7 | 19.4 | Closed
WI-0530 | REQ-0271 | MustShip | PWR-MGMT | P-003 | Camille Villalobos | 2025-11-22 | 2025-12-03 | 30.1 | 25.9 | Closed
WI-0531 | REQ-0271 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-04-30 | 2025-05-05 | 23 | 18.1 | Closed
WI-0532 | REQ-0272 | MustShip | PWR-MGMT | P-017 | Quentin Zielinski | 2025-07-30 | 2025-09-20 | 24.1 | 33.3 | Closed
WI-0533 | REQ-0272 | MustShip | PWR-MGMT | P-013 | Mei Thackeray | 2026-03-05 | 2026-04-13 | 5.7 | 6.9 | Closed
WI-0534 | REQ-0272 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-12-12 |  | 7.3 |  | InProgress
WI-0535 | REQ-0273 | ShouldShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-12-14 | 2025-12-22 | 21.2 | 17.4 | Closed
WI-0536 | REQ-0273 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2025-10-24 | 2025-10-29 | 14.1 | 11.1 | Closed
WI-0537 | REQ-0273 | ShouldShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-10-05 | 2025-11-18 | 24.7 | 31.7 | Closed
WI-0538 | REQ-0274 | ShouldShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-07-01 | 2025-08-14 | 18.5 | 23.5 | Closed
WI-0539 | REQ-0274 | ShouldShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-09-28 | 2025-11-17 | 13.7 | 18.5 | Closed
WI-0540 | REQ-0275 | Nice | REL-MECH | P-021 | Ulrike Dalgleish | 2025-09-30 | 2025-10-06 | 14.2 | 11.3 | Closed
WI-0541 | REQ-0275 | Nice | REL-MECH | P-008 | Hiroshi Ibarra | 2025-07-18 | 2025-08-31 | 25.3 | 32.4 | Closed
WI-0542 | REQ-0276 | ShouldShip | NAV-SENS | P-009 | Imani Petrovic | 2025-08-11 | 2025-10-05 | 20.8 | 29.5 | Closed
WI-0543 | REQ-0276 | ShouldShip | NAV-SENS | P-005 | Elena Lindqvist | 2026-06-18 | 2026-07-20 | 14.5 | 16.3 | Closed
WI-0544 | REQ-0276 | ShouldShip | NAV-SENS | P-019 | Sana Nakamura | 2025-03-23 | 2025-04-01 | 15.1 | 12.6 | Closed
WI-0545 | REQ-0277 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2026-04-06 | 2026-06-01 | 13.1 | 18.8 | Closed
WI-0546 | REQ-0277 | MustShip | PWR-MGMT | P-005 | Elena Lindqvist | 2025-01-20 | 2025-01-26 | 11.5 | 9.1 | Closed
WI-0547 | REQ-0278 | ShouldShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-10-23 | 2025-11-02 | 18.3 | 15.4 | Closed
WI-0548 | REQ-0278 | ShouldShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-05-27 | 2025-07-10 | 35.7 | 45.6 | Closed
WI-0549 | REQ-0278 | ShouldShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2026-06-24 | 2026-07-11 | 31.2 | 29.4 | Closed
WI-0550 | REQ-0279 | Nice | GND-CTRL | P-006 | Farid Saltzman | 2025-10-03 | 2025-10-27 | 19 | 19.6 | Closed
WI-0551 | REQ-0279 | Nice | GND-CTRL | P-020 | Tomas Ustinov | 2025-12-04 |  | 13.3 |  | Open
WI-0552 | REQ-0280 | MustShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2025-12-07 | 2026-01-13 | 16.9 | 20.1 | Closed
WI-0553 | REQ-0280 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-04-13 | 2025-04-07 | 27.3 | 31.9 | Closed
WI-0554 | REQ-0281 | Nice | NAV-SENS | P-015 | Olabisi Jindal | 2025-05-26 | 2025-06-03 | 22.1 | 18.1 | Closed
WI-0555 | REQ-0281 | Nice | NAV-SENS | P-010 | Jonas Weatherby | 2026-05-08 | 2026-06-25 | 10.1 | 13.4 | Closed
WI-0556 | REQ-0281 | Nice | NAV-SENS | P-020 | Tomas Ustinov | 2026-06-20 | 2026-07-22 | 8.9 | 10 | Closed
WI-0557 | REQ-0282 | MustShip | GND-CTRL | P-016 | Priya Quintana | 2025-07-08 | 2025-08-28 | 30.1 | 41.3 | Closed
WI-0558 | REQ-0282 | MustShip | GND-CTRL | P-004 | Dmitri Eriksen | 2025-10-01 | 2025-10-23 | 29.9 | 29.8 | Closed
WI-0559 | REQ-0282 | MustShip | GND-CTRL | P-014 | Nils Castellan | 2025-02-13 | 2025-03-31 | 22.3 | 29.2 | Closed
WI-0560 | REQ-0283 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-12-29 | 2026-01-22 | 21.3 | 21.7 | Closed
WI-0561 | REQ-0283 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2025-04-07 | 2025-04-17 | 8.9 | 7.6 | Closed
WI-0562 | REQ-0283 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-05-25 | 2025-06-21 | 10.3 | 11 | Closed
WI-0563 | REQ-0284 | Nice | REL-MECH | P-015 | Olabisi Jindal | 2025-12-22 | 2025-12-29 | 26.9 | 21.8 | Closed
WI-0564 | REQ-0284 | Nice | REL-MECH | P-018 | Rafael Grigorescu | 2026-05-23 | 2026-06-02 | 8.6 | 7.2 | Closed
WI-0565 | REQ-0284 | Nice | REL-MECH | P-014 | Nils Castellan | 2025-05-22 | 2025-06-18 | 29.4 | 31 | Closed
WI-0566 | REQ-0284 | Nice | REL-MECH | P-021 | Ulrike Dalgleish | 2025-09-24 | 2025-10-01 | 27.6 | 22.2 | Closed
WI-0567 | REQ-0285 | ShouldShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2025-01-31 | 2025-02-05 | 20 | 15.7 | Closed
WI-0568 | REQ-0285 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-09-27 | 2025-10-23 | 13.5 | 14.1 | Closed
WI-0569 | REQ-0285 | ShouldShip | PWR-MGMT | P-020 | Tomas Ustinov | 2026-02-13 | 2026-04-05 | 24.3 | 33.3 | Closed
WI-0570 | REQ-0286 | MustShip | NAV-SENS | P-002 | Bruno Oyelaran | 2025-04-23 | 2025-05-19 | 4.2 | 4.4 | Closed
WI-0571 | REQ-0286 | MustShip | NAV-SENS | P-004 | Dmitri Eriksen | 2025-07-25 | 2025-08-20 | 6 | 6.3 | Closed
WI-0572 | REQ-0286 | MustShip | NAV-SENS | P-012 | Liam Moreau | 2025-03-01 | 2025-03-22 | 27.8 | 27.5 | Closed
WI-0573 | REQ-0287 | MustShip | REL-MECH | P-009 | Imani Petrovic | 2025-07-15 | 2025-08-29 | 21.6 | 27.9 | Closed
WI-0574 | REQ-0288 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-05-04 | 2025-05-09 | 20.9 | 16.4 | Closed
WI-0575 | REQ-0288 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-08-06 | 2025-09-14 | 21.9 | 26.5 | Closed
WI-0576 | REQ-0289 | MustShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-08-02 | 2025-09-12 | 28.5 | 35.4 | Closed
WI-0577 | REQ-0290 | ShouldShip | STRUCT-I | P-019 | Sana Nakamura | 2026-03-14 | 2026-04-28 | 16.5 | 21.4 | Closed
WI-0578 | REQ-0291 | MustShip | STRUCT-I | P-005 | Elena Lindqvist | 2026-06-01 | 2026-06-12 | 26.2 | 22.6 | Closed
WI-0579 | REQ-0291 | MustShip | STRUCT-I | P-017 | Quentin Zielinski | 2025-02-24 | 2025-03-24 | 10.5 | 11.3 | Closed
WI-0580 | REQ-0291 | MustShip | STRUCT-I | P-021 | Ulrike Dalgleish | 2025-11-24 | 2026-01-10 | 33.6 | 44.1 | Closed
WI-0581 | REQ-0292 | MustShip | NAV-SENS | P-002 | Bruno Oyelaran | 2026-04-22 | 2026-05-17 | 26.1 | 26.9 | Closed
WI-0582 | REQ-0293 | MustShip | GND-CTRL | P-010 | Jonas Weatherby | 2026-02-18 |  | 5.3 |  | InProgress
WI-0583 | REQ-0293 | MustShip | GND-CTRL | P-013 | Mei Thackeray | 2025-10-14 | 2025-10-28 | 34.6 | 31 | Closed
WI-0584 | REQ-0294 | MustShip | FLT-CTRL | P-006 | Farid Saltzman | 2026-05-12 | 2026-05-18 | 16.2 | 12.9 | Closed
WI-0585 | REQ-0295 | MustShip | PWR-MGMT | P-017 | Quentin Zielinski | 2026-03-06 | 2026-03-27 | 13.9 | 13.8 | Closed
WI-0586 | REQ-0295 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2025-06-11 | 2025-07-25 | 22.5 | 28.8 | Closed
WI-0587 | REQ-0296 | MustShip | PWR-MGMT | P-010 | Jonas Weatherby | 2026-02-09 | 2026-03-02 | 2.8 | 2.7 | Closed
WI-0588 | REQ-0296 | MustShip | PWR-MGMT | P-003 | Camille Villalobos | 2026-02-22 | 2026-03-04 | 15.2 | 12.9 | Closed
WI-0589 | REQ-0296 | MustShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-04-16 | 2025-05-27 | 20.7 | 25.8 | Closed
WI-0590 | REQ-0297 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2025-07-06 | 2025-08-21 | 31 | 40.4 | Closed
WI-0591 | REQ-0297 | ShouldShip | NAV-SENS | P-018 | Rafael Grigorescu | 2025-11-15 | 2025-12-08 | 30.7 | 31.1 | Closed
WI-0592 | REQ-0297 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2025-05-19 | 2025-06-10 | 17.3 | 17.3 | Closed
WI-0593 | REQ-0298 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-04-30 | 2025-05-30 | 29.3 | 32.3 | Closed
WI-0594 | REQ-0299 | ShouldShip | GND-CTRL | P-010 | Jonas Weatherby | 2026-05-11 | 2026-06-08 | 16.7 | 18.1 | Closed
WI-0595 | REQ-0299 | ShouldShip | GND-CTRL | P-019 | Sana Nakamura | 2025-05-13 | 2025-06-12 | 29 | 32.1 | Closed
WI-0596 | REQ-0299 | ShouldShip | GND-CTRL | P-013 | Mei Thackeray | 2025-02-25 | 2025-04-23 | 5 | 7.2 | Closed
WI-0597 | REQ-0300 | MustShip | FLT-CTRL | P-016 | Priya Quintana | 2025-04-22 | 2025-06-14 | 28.9 | 40.2 | Closed
WI-0598 | REQ-0300 | MustShip | FLT-CTRL | P-016 | Priya Quintana | 2025-10-25 | 2025-11-14 | 9 | 8.9 | Closed
WI-0599 | REQ-0301 | MustShip | STRUCT-I | P-010 | Jonas Weatherby | 2025-04-03 | 2025-05-25 | 2.1 | 2.9 | Closed
WI-0600 | REQ-0301 | MustShip | STRUCT-I | P-015 | Olabisi Jindal | 2026-06-23 |  | 29.8 |  | InProgress
WI-0601 | REQ-0301 | MustShip | STRUCT-I | P-020 | Tomas Ustinov | 2026-01-10 | 2026-03-06 | 28.5 | 40.4 | Closed
WI-0602 | REQ-0302 | Nice | PWR-MGMT | P-012 | Liam Moreau | 2025-04-29 | 2025-06-08 | 17.8 | 21.9 | Closed
WI-0603 | REQ-0303 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2026-01-10 |  | 31.4 |  | Open
WI-0604 | REQ-0303 | MustShip | COMM-LNK | P-005 | Elena Lindqvist | 2026-03-24 | 2026-04-03 | 7.7 | 6.5 | Closed
WI-0605 | REQ-0303 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2026-01-21 |  | 27.4 |  | Open
WI-0606 | REQ-0304 | ShouldShip | NAV-SENS | P-019 | Sana Nakamura | 2025-11-24 | 2025-12-04 | 21 | 17.7 | Closed
WI-0607 | REQ-0304 | ShouldShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-06-13 | 2025-07-19 | 22.5 | 26.5 | Closed
WI-0608 | REQ-0304 | ShouldShip | NAV-SENS | P-002 | Bruno Oyelaran | 2025-05-18 | 2025-06-11 | 20.3 | 20.8 | Closed
WI-0609 | REQ-0305 | Nice | DIAG-LOG | P-012 | Liam Moreau | 2025-01-24 | 2025-03-11 | 28 | 36.5 | Closed
WI-0610 | REQ-0305 | Nice | DIAG-LOG | P-002 | Bruno Oyelaran | 2025-05-15 | 2025-05-26 | 11.1 | 9.5 | Closed
WI-0611 | REQ-0306 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-06-28 | 2026-08-21 | 31.1 | 43.6 | Closed
WI-0612 | REQ-0307 | Nice | PWR-MGMT | P-019 | Sana Nakamura | 2026-02-25 | 2026-03-16 | 16.1 | 15.5 | Closed
WI-0613 | REQ-0307 | Nice | PWR-MGMT | P-009 | Imani Petrovic | 2025-08-12 | 2025-09-22 | 34.6 | 43.1 | Closed
WI-0614 | REQ-0307 | Nice | PWR-MGMT | P-020 | Tomas Ustinov | 2025-07-14 | 2025-09-01 | 27.9 | 37.4 | Closed
WI-0615 | REQ-0308 | MustShip | FLT-CTRL | P-005 | Elena Lindqvist | 2025-06-22 | 2025-07-28 | 35.9 | 42.3 | Closed
WI-0616 | REQ-0308 | MustShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-05-31 | 2025-06-27 | 14.3 | 15.1 | Closed
WI-0617 | REQ-0309 | MustShip | FLT-CTRL | P-009 | Imani Petrovic | 2025-12-29 | 2026-01-31 | 29.8 | 33.9 | Closed
WI-0618 | REQ-0309 | MustShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-08-28 | 2025-10-07 | 4.8 | 5.8 | Closed
WI-0619 | REQ-0310 | Nice | PWR-MGMT | P-015 | Olabisi Jindal | 2025-02-24 | 2025-04-17 | 33.8 | 46.5 | Closed
WI-0620 | REQ-0310 | Nice | PWR-MGMT | P-019 | Sana Nakamura | 2025-09-13 | 2025-11-01 | 34.9 | 46.6 | Closed
WI-0621 | REQ-0311 | ShouldShip | GND-CTRL | P-021 | Ulrike Dalgleish | 2025-11-02 | 2025-11-16 | 25 | 22.4 | Closed
WI-0622 | REQ-0311 | ShouldShip | GND-CTRL | P-020 | Tomas Ustinov | 2025-11-30 | 2025-12-05 | 18.7 | 14.6 | Closed
WI-0623 | REQ-0312 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-10-25 | 2025-10-28 | 10.9 | 8.2 | Closed
WI-0624 | REQ-0313 | Nice | DIAG-LOG | P-014 | Nils Castellan | 2025-11-26 | 2026-01-21 | 26.4 | 37.9 | Closed
WI-0625 | REQ-0313 | Nice | DIAG-LOG | P-021 | Ulrike Dalgleish | 2025-04-10 |  | 23.6 |  | Open
WI-0626 | REQ-0313 | Nice | DIAG-LOG | P-011 | Katya Fairweather | 2025-06-30 | 2025-08-06 | 18.8 | 22.3 | Closed
WI-0627 | REQ-0314 | ShouldShip | COMM-LNK | P-017 | Quentin Zielinski | 2025-01-31 | 2025-02-11 | 15.7 | 13.5 | Closed
WI-0628 | REQ-0314 | ShouldShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-11-02 | 2025-12-20 | 25.8 | 34.3 | Closed
WI-0629 | REQ-0314 | ShouldShip | COMM-LNK | P-006 | Farid Saltzman | 2025-07-06 | 2025-08-20 | 9.9 | 12.9 | Closed
WI-0630 | REQ-0315 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-06-28 | 2025-07-09 | 16.4 | 14 | Closed
WI-0631 | REQ-0316 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-04-26 | 2025-06-19 | 34.9 | 49.1 | Closed
WI-0632 | REQ-0317 | ShouldShip | DIAG-LOG | P-009 | Imani Petrovic | 2025-08-30 |  | 4.1 |  | InProgress
WI-0633 | REQ-0317 | ShouldShip | DIAG-LOG | P-005 | Elena Lindqvist | 2025-05-10 | 2025-06-22 | 19.8 | 25 | Closed
WI-0634 | REQ-0318 | Nice | NAV-SENS | P-009 | Imani Petrovic | 2026-04-06 | 2026-04-27 | 7 | 7 | Closed
WI-0635 | REQ-0318 | Nice | NAV-SENS | P-019 | Sana Nakamura | 2025-12-31 | 2026-01-23 | 27.3 | 27.4 | Closed
WI-0636 | REQ-0319 | MustShip | GND-CTRL | P-020 | Tomas Ustinov | 2025-01-29 | 2025-03-03 | 3.8 | 4.3 | Closed
WI-0637 | REQ-0320 | ShouldShip | FLT-CTRL | P-003 | Camille Villalobos | 2026-05-26 | 2026-07-03 | 22.3 | 26.7 | Closed
WI-0638 | REQ-0320 | ShouldShip | FLT-CTRL | P-014 | Nils Castellan | 2025-09-23 | 2025-10-22 | 29.5 | 32.1 | Closed
WI-0639 | REQ-0320 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-04-27 | 2025-06-18 | 32 | 44.2 | Closed
WI-0640 | REQ-0321 | MustShip | STRUCT-I | P-007 | Grace Baptiste | 2025-07-08 | 2025-09-01 | 18.8 | 26.6 | Closed
WI-0641 | REQ-0321 | MustShip | STRUCT-I | P-018 | Rafael Grigorescu | 2026-06-18 | 2026-07-14 | 2.6 | 2.7 | Closed
WI-0642 | REQ-0322 | Nice | STRUCT-I | P-006 | Farid Saltzman | 2025-06-11 | 2025-07-13 | 2.3 | 2.5 | Closed
WI-0643 | REQ-0322 | Nice | STRUCT-I | P-002 | Bruno Oyelaran | 2025-04-10 | 2025-05-29 | 33.2 | 44.3 | Closed
WI-0644 | REQ-0322 | Nice | STRUCT-I | P-019 | Sana Nakamura | 2025-09-17 | 2025-11-02 | 8.3 | 10.9 | Closed
WI-0645 | REQ-0323 | Nice | GND-CTRL | P-005 | Elena Lindqvist | 2026-03-19 | 2026-05-13 | 14.4 | 20.5 | Closed
WI-0646 | REQ-0323 | Nice | GND-CTRL | P-017 | Quentin Zielinski | 2025-12-09 | 2026-01-29 | 6.3 | 8.6 | Closed
WI-0647 | REQ-0324 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2026-06-16 | 2026-07-25 | 34.1 | 41.2 | Closed
WI-0648 | REQ-0324 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2025-12-06 | 2026-01-31 | 12.7 | 18.2 | Closed
WI-0649 | REQ-0324 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2026-03-05 | 2026-03-16 | 3.1 | 2.7 | Closed
WI-0650 | REQ-0325 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2025-08-17 | 2025-10-08 | 4.7 | 6.5 | Closed
WI-0651 | REQ-0325 | MustShip | NAV-SENS | P-020 | Tomas Ustinov | 2025-12-31 | 2026-02-03 | 13.9 | 15.9 | Closed
WI-0652 | REQ-0325 | MustShip | NAV-SENS | P-012 | Liam Moreau | 2025-10-10 | 2025-10-18 | 6.9 | 5.7 | Closed
WI-0653 | REQ-0325 | MustShip | NAV-SENS | P-001 | Aditi Halvorsen | 2025-09-09 | 2025-09-14 | 35.9 | 27.9 | Closed
WI-0654 | REQ-0326 | ShouldShip | NAV-SENS | P-012 | Liam Moreau | 2025-02-26 | 2025-04-01 | 21 | 24.3 | Closed
WI-0655 | REQ-0327 | ShouldShip | DIAG-LOG | P-010 | Jonas Weatherby | 2025-10-20 |  | 16.2 |  | InProgress
WI-0656 | REQ-0328 | Nice | GND-CTRL | P-006 | Farid Saltzman | 2026-04-20 | 2026-05-27 | 27.9 | 33.4 | Closed
WI-0657 | REQ-0329 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2026-04-07 | 2026-05-26 | 12.7 | 16.9 | Closed
WI-0658 | REQ-0329 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2025-06-21 |  | 8.8 |  | InProgress
WI-0659 | REQ-0331 | MustShip | GND-CTRL | P-005 | Elena Lindqvist | 2025-06-16 | 2025-07-07 | 7.4 | 7.3 | Closed
WI-0660 | REQ-0332 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2025-01-13 | 2025-03-06 | 5.3 | 7.4 | Closed
WI-0661 | REQ-0332 | MustShip | NAV-SENS | P-007 | Grace Baptiste | 2025-09-19 | 2025-10-02 | 23.2 | 20.5 | Closed
WI-0662 | REQ-0333 | MustShip | NAV-SENS | P-010 | Jonas Weatherby | 2026-05-28 | 2026-06-15 | 3.4 | 3.2 | Closed
WI-0663 | REQ-0334 | MustShip | DIAG-LOG | P-014 | Nils Castellan | 2025-10-05 | 2025-11-17 | 11.4 | 14.5 | Closed
WI-0664 | REQ-0334 | MustShip | DIAG-LOG | P-018 | Rafael Grigorescu | 2026-05-20 | 2026-06-09 | 26.6 | 26 | Closed
WI-0665 | REQ-0334 | MustShip | DIAG-LOG | P-020 | Tomas Ustinov | 2026-04-15 | 2026-05-24 | 4.2 | 5.1 | Closed
WI-0666 | REQ-0335 | ShouldShip | DIAG-LOG | P-006 | Farid Saltzman | 2026-04-21 | 2026-05-15 | 4 | 4.1 | Closed
WI-0667 | REQ-0335 | ShouldShip | DIAG-LOG | P-004 | Dmitri Eriksen | 2026-02-27 | 2026-04-06 | 22.3 | 26.7 | Closed
WI-0668 | REQ-0335 | ShouldShip | DIAG-LOG | P-006 | Farid Saltzman | 2026-01-19 | 2026-02-07 | 2.2 | 2.1 | Closed
WI-0669 | REQ-0336 | MustShip | REL-MECH | P-014 | Nils Castellan | 2025-03-19 | 2025-04-10 | 6.2 | 6.2 | Closed
WI-0670 | REQ-0336 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-12-08 | 2026-01-08 | 18.9 | 21 | Closed
WI-0671 | REQ-0337 | ShouldShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-09-02 | 2025-10-01 | 13.5 | 14.6 | Closed
WI-0672 | REQ-0337 | ShouldShip | FLT-CTRL | P-008 | Hiroshi Ibarra | 2026-06-20 | 2026-08-12 | 12.2 | 17 | Closed
WI-0673 | REQ-0338 | MustShip | REL-MECH | P-015 | Olabisi Jindal | 2025-09-16 | 2025-10-03 | 27.5 | 25.6 | Closed
WI-0674 | REQ-0339 | MustShip | COMM-LNK | P-007 | Grace Baptiste | 2025-07-04 | 2025-08-08 | 33.8 | 39.2 | Closed
WI-0675 | REQ-0339 | MustShip | COMM-LNK | P-005 | Elena Lindqvist | 2026-06-07 | 2026-06-27 | 29.3 | 28.3 | Closed
WI-0676 | REQ-0340 | MustShip | FLT-CTRL | P-012 | Liam Moreau | 2026-01-27 | 2026-02-22 | 27.6 | 28.8 | Closed
WI-0677 | REQ-0341 | MustShip | NAV-SENS | P-004 | Dmitri Eriksen | 2026-06-23 | 2026-07-22 | 13.5 | 14.6 | Closed
WI-0678 | REQ-0341 | MustShip | NAV-SENS | P-018 | Rafael Grigorescu | 2026-03-13 | 2026-04-14 | 13.1 | 14.7 | Closed
WI-0679 | REQ-0342 | ShouldShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-10-16 | 2025-11-27 | 16.4 | 20.5 | Closed
WI-0680 | REQ-0342 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-09-16 | 2025-10-25 | 32.2 | 39.1 | Closed
WI-0681 | REQ-0343 | MustShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-10-26 | 2025-11-27 | 8.3 | 9.4 | Closed
WI-0682 | REQ-0343 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-08-27 | 2025-10-09 | 13 | 16.6 | Closed
WI-0683 | REQ-0344 | ShouldShip | GND-CTRL | P-001 | Aditi Halvorsen | 2025-03-16 | 2025-05-04 | 23.7 | 31.9 | Closed
WI-0684 | REQ-0344 | ShouldShip | GND-CTRL | P-002 | Bruno Oyelaran | 2025-03-29 | 2025-04-18 | 4.2 | 4.1 | Closed
WI-0685 | REQ-0344 | ShouldShip | GND-CTRL | P-017 | Quentin Zielinski | 2025-08-13 | 2025-09-18 | 17 | 20.1 | Closed
WI-0686 | REQ-0345 | ShouldShip | REL-MECH | P-014 | Nils Castellan | 2025-10-04 | 2025-11-25 | 10.4 | 14.3 | Closed
WI-0687 | REQ-0345 | ShouldShip | REL-MECH | P-018 | Rafael Grigorescu | 2025-09-21 | 2025-11-09 | 9.6 | 13 | Closed
WI-0688 | REQ-0346 | MustShip | GND-CTRL | P-015 | Olabisi Jindal | 2025-09-09 | 2025-09-29 | 25.8 | 25.3 | Closed
WI-0689 | REQ-0346 | MustShip | GND-CTRL | P-005 | Elena Lindqvist | 2025-03-08 | 2025-04-02 | 33.1 | 34.3 | Closed
WI-0690 | REQ-0346 | MustShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2025-03-23 | 2025-04-07 | 3.4 | 3.1 | Closed
WI-0691 | REQ-0347 | Nice | GND-CTRL | P-020 | Tomas Ustinov | 2026-05-02 | 2026-06-03 | 35 | 39.3 | Closed
WI-0692 | REQ-0347 | Nice | GND-CTRL | P-020 | Tomas Ustinov | 2025-09-16 | 2025-11-11 | 29.8 | 42.6 | Closed
WI-0693 | REQ-0347 | Nice | GND-CTRL | P-001 | Aditi Halvorsen | 2025-03-19 | 2025-05-01 | 4.2 | 5.3 | Closed
WI-0694 | REQ-0348 | ShouldShip | REL-MECH | P-011 | Katya Fairweather | 2025-04-17 |  | 8.6 |  | InProgress
WI-0695 | REQ-0348 | ShouldShip | REL-MECH | P-015 | Olabisi Jindal | 2025-06-24 | 2025-08-18 | 22 | 31.4 | Closed
WI-0696 | REQ-0349 | MustShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-11-09 | 2026-01-02 | 32.9 | 46.4 | Closed
WI-0697 | REQ-0349 | MustShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2025-01-17 | 2025-01-25 | 32.2 | 26.4 | Closed
WI-0698 | REQ-0349 | MustShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-11-03 | 2025-12-17 | 34.3 | 44 | Closed
WI-0699 | REQ-0350 | MustShip | FLT-CTRL | P-003 | Camille Villalobos | 2026-04-11 | 2026-05-13 | 27.1 | 30.4 | Closed
WI-0700 | REQ-0350 | MustShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2026-04-07 | 2026-05-15 | 33 | 39.7 | Closed
WI-0701 | REQ-0350 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-05-07 | 2025-05-17 | 13.9 | 11.7 | Closed
WI-0702 | REQ-0351 | MustShip | GND-CTRL | P-011 | Katya Fairweather | 2026-02-20 | 2026-03-08 | 16.2 | 15 | Closed
WI-0703 | REQ-0351 | MustShip | GND-CTRL | P-013 | Mei Thackeray | 2025-01-13 | 2025-02-26 | 18.8 | 24.1 | Closed
WI-0704 | REQ-0351 | MustShip | GND-CTRL | P-018 | Rafael Grigorescu | 2025-03-24 | 2025-04-15 | 27.2 | 27.2 | Closed
WI-0705 | REQ-0352 | MustShip | NAV-SENS | P-003 | Camille Villalobos | 2026-02-02 | 2026-03-24 | 8 | 10.8 | Closed
WI-0706 | REQ-0352 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2025-03-05 | 2025-03-22 | 17.8 | 16.6 | Closed
WI-0707 | REQ-0352 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-10-31 | 2025-12-08 | 19.6 | 23.4 | Closed
WI-0708 | REQ-0353 | ShouldShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-03-23 | 2026-04-19 | 32 | 33.9 | Closed
WI-0709 | REQ-0353 | ShouldShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-09-09 | 2025-11-03 | 27.7 | 39.3 | Closed
WI-0710 | REQ-0353 | ShouldShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-08-03 |  | 23.1 |  | InProgress
WI-0711 | REQ-0354 | MustShip | GND-CTRL | P-001 | Aditi Halvorsen | 2026-06-04 |  | 3.6 |  | InProgress
WI-0712 | REQ-0354 | MustShip | GND-CTRL | P-019 | Sana Nakamura | 2025-09-13 | 2025-10-11 | 34.7 | 37.3 | Closed
WI-0713 | REQ-0355 | ShouldShip | DIAG-LOG | P-019 | Sana Nakamura | 2025-07-05 | 2025-07-13 | 6.1 | 5 | Closed
WI-0714 | REQ-0355 | ShouldShip | DIAG-LOG | P-001 | Aditi Halvorsen | 2026-06-19 | 2026-07-23 | 27.8 | 32.1 | Closed
WI-0715 | REQ-0355 | ShouldShip | DIAG-LOG | P-011 | Katya Fairweather | 2025-09-04 | 2025-09-23 | 2.3 | 2.2 | Closed
WI-0716 | REQ-0356 | MustShip | STRUCT-I | P-013 | Mei Thackeray | 2025-02-10 | 2025-02-15 | 32.5 | 25.2 | Closed
WI-0717 | REQ-0356 | MustShip | STRUCT-I | P-018 | Rafael Grigorescu | 2025-09-15 | 2025-10-01 | 14.9 | 13.7 | Closed
WI-0718 | REQ-0356 | MustShip | STRUCT-I | P-012 | Liam Moreau | 2026-05-21 | 2026-05-27 | 17.5 | 14 | Closed
WI-0719 | REQ-0357 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-05-28 | 2025-06-17 | 32.8 | 32 | Closed
WI-0720 | REQ-0357 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2026-02-03 | 2026-03-14 | 5.6 | 6.8 | Closed
WI-0721 | REQ-0358 | Nice | COMM-LNK | P-019 | Sana Nakamura | 2025-03-10 | 2025-03-13 | 6.2 | 4.6 | Closed
WI-0722 | REQ-0359 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2026-06-07 | 2026-07-05 | 7.4 | 8 | Closed
WI-0723 | REQ-0359 | MustShip | FLT-CTRL | P-006 | Farid Saltzman | 2026-06-02 | 2026-06-15 | 5 | 4.4 | Closed
WI-0724 | REQ-0360 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2026-06-18 |  | 30.2 |  | Open
WI-0725 | REQ-0360 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-04-09 | 2025-05-05 | 4.3 | 4.5 | Closed
WI-0726 | REQ-0360 | MustShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2025-12-20 | 2026-01-12 | 11.9 | 12.1 | Closed
WI-0727 | REQ-0361 | Nice | REL-MECH | P-005 | Elena Lindqvist | 2025-05-02 | 2025-05-19 | 27 | 25.1 | Closed
WI-0728 | REQ-0362 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2025-10-12 |  | 25.3 |  | InProgress
WI-0729 | REQ-0362 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-02-09 | 2025-03-06 | 16.8 | 17.4 | Closed
WI-0730 | REQ-0363 | ShouldShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-09-22 | 2025-10-29 | 25.3 | 30 | Closed
WI-0731 | REQ-0365 | ShouldShip | REL-MECH | P-019 | Sana Nakamura | 2025-01-27 | 2025-02-12 | 17.6 | 16.2 | Closed
WI-0732 | REQ-0366 | Nice | GND-CTRL | P-010 | Jonas Weatherby | 2025-05-18 | 2025-06-20 | 35.9 | 40.9 | Closed
WI-0733 | REQ-0367 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2025-05-01 |  | 8.4 |  | InProgress
WI-0734 | REQ-0367 | ShouldShip | NAV-SENS | P-019 | Sana Nakamura | 2026-06-04 | 2026-07-24 | 2.1 | 2.8 | Closed
WI-0735 | REQ-0368 | MustShip | FLT-CTRL | P-010 | Jonas Weatherby | 2025-02-21 | 2025-04-09 | 14.6 | 19.2 | Closed
WI-0736 | REQ-0368 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-06-02 | 2025-07-09 | 19.4 | 23.1 | Closed
WI-0737 | REQ-0368 | MustShip | FLT-CTRL | P-017 | Quentin Zielinski | 2025-11-10 | 2025-12-18 | 13 | 15.6 | Closed
WI-0738 | REQ-0368 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2026-03-01 | 2026-03-28 | 15.1 | 16 | Closed
WI-0739 | REQ-0369 | MustShip | FLT-CTRL | P-015 | Olabisi Jindal | 2025-11-03 | 2025-12-13 | 19 | 23.3 | Closed
WI-0740 | REQ-0370 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2025-07-12 | 2025-08-15 | 24.7 | 28.5 | Closed
WI-0741 | REQ-0370 | MustShip | COMM-LNK | P-009 | Imani Petrovic | 2025-06-28 | 2025-08-20 | 15.7 | 21.9 | Closed
WI-0742 | REQ-0370 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-01-21 | 2025-03-14 | 19.8 | 27.3 | Closed
WI-0743 | REQ-0371 | ShouldShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2026-01-31 | 2026-03-14 | 34.7 | 43.4 | Closed
WI-0744 | REQ-0371 | ShouldShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2026-02-12 | 2026-03-18 | 15.5 | 17.9 | Closed
WI-0745 | REQ-0371 | ShouldShip | COMM-LNK | P-015 | Olabisi Jindal | 2025-05-17 | 2025-07-08 | 17.6 | 24.3 | Closed
WI-0746 | REQ-0372 | MustShip | FLT-CTRL | P-014 | Nils Castellan | 2026-06-12 | 2026-07-31 | 22.8 | 30.5 | Closed
WI-0747 | REQ-0372 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-01-07 | 2025-01-20 | 4.5 | 4 | Closed
WI-0748 | REQ-0372 | MustShip | FLT-CTRL | P-013 | Mei Thackeray | 2025-03-31 |  | 8.3 |  | InProgress
WI-0749 | REQ-0373 | ShouldShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2025-11-13 | 2025-12-15 | 10.1 | 11.3 | Closed
WI-0750 | REQ-0373 | ShouldShip | COMM-LNK | P-007 | Grace Baptiste | 2026-01-18 | 2026-01-29 | 21.5 | 18.5 | Closed
WI-0751 | REQ-0373 | ShouldShip | COMM-LNK | P-012 | Liam Moreau | 2025-12-20 |  | 20.1 |  | InProgress
WI-0752 | REQ-0374 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2026-03-17 | 2026-04-17 | 23.6 | 26.3 | Closed
WI-0753 | REQ-0375 | MustShip | FLT-CTRL | P-001 | Aditi Halvorsen | 2026-01-24 | 2026-03-13 | 11.2 | 15 | Closed
WI-0754 | REQ-0376 | ShouldShip | REL-MECH | P-014 | Nils Castellan | 2026-03-13 | 2026-04-05 | 10.5 | 10.5 | Closed
WI-0755 | REQ-0376 | ShouldShip | REL-MECH | P-016 | Priya Quintana | 2025-08-15 | 2025-08-19 | 3.8 | 2.9 | Closed
WI-0756 | REQ-0376 | ShouldShip | REL-MECH | P-012 | Liam Moreau | 2026-06-14 | 2026-07-14 | 14 | 15.3 | Closed
WI-0757 | REQ-0377 | ShouldShip | FLT-CTRL | P-015 | Olabisi Jindal | 2025-01-08 | 2025-02-25 | 8.9 | 11.9 | Closed
WI-0758 | REQ-0377 | ShouldShip | FLT-CTRL | P-019 | Sana Nakamura | 2025-05-15 | 2025-05-26 | 33.3 | 28.6 | Closed
WI-0759 | REQ-0378 | MustShip | PWR-MGMT | P-014 | Nils Castellan | 2025-09-28 | 2025-10-28 | 8.9 | 9.9 | Closed
WI-0760 | REQ-0378 | MustShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2025-09-06 | 2025-09-11 | 12.7 | 9.9 | Closed
WI-0761 | REQ-0378 | MustShip | PWR-MGMT | P-016 | Priya Quintana | 2025-11-05 | 2025-11-10 | 24 | 18.8 | Closed
WI-0762 | REQ-0379 | ShouldShip | STRUCT-I | P-007 | Grace Baptiste | 2025-03-05 | 2025-03-26 | 30.4 | 30 | Closed
WI-0763 | REQ-0379 | ShouldShip | STRUCT-I | P-021 | Ulrike Dalgleish | 2025-05-23 | 2025-06-01 | 24.4 | 20.2 | Closed
WI-0764 | REQ-0380 | ShouldShip | REL-MECH | P-018 | Rafael Grigorescu | 2025-05-14 | 2025-05-20 | 7.4 | 5.9 | Closed
WI-0765 | REQ-0382 | MustShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-01-08 | 2025-03-03 | 33.5 | 47 | Closed
WI-0766 | REQ-0382 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-11-27 | 2026-01-01 | 8.9 | 10.4 | Closed
WI-0767 | REQ-0382 | MustShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2026-03-22 | 2026-05-05 | 12.5 | 16 | Closed
WI-0768 | REQ-0383 | ShouldShip | GND-CTRL | P-016 | Priya Quintana | 2025-06-21 | 2025-06-24 | 28.9 | 21.8 | Closed
WI-0769 | REQ-0385 | MustShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-02-22 |  | 11 |  | Open
WI-0770 | REQ-0385 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2026-01-03 | 2026-02-01 | 34.3 | 37.2 | Closed
WI-0771 | REQ-0385 | MustShip | COMM-LNK | P-009 | Imani Petrovic | 2026-05-08 | 2026-05-20 | 11 | 9.6 | Closed
WI-0772 | REQ-0386 | Nice | NAV-SENS | P-018 | Rafael Grigorescu | 2025-03-11 | 2025-04-22 | 11.6 | 14.6 | Closed
WI-0773 | REQ-0387 | Nice | NAV-SENS | P-006 | Farid Saltzman | 2025-08-06 | 2025-08-10 | 8.6 | 6.6 | Closed
WI-0774 | REQ-0387 | Nice | NAV-SENS | P-019 | Sana Nakamura | 2025-08-17 | 2025-09-30 | 29.1 | 37.4 | Closed
WI-0775 | REQ-0387 | Nice | NAV-SENS | P-001 | Aditi Halvorsen | 2025-10-10 |  | 35.1 |  | InProgress
WI-0776 | REQ-0388 | MustShip | DIAG-LOG | P-005 | Elena Lindqvist | 2026-04-25 | 2026-05-19 | 12 | 12.2 | Closed
WI-0777 | REQ-0389 | MustShip | GND-CTRL | P-011 | Katya Fairweather | 2025-03-15 | 2025-04-04 | 19 | 18.4 | Closed
WI-0778 | REQ-0390 | MustShip | COMM-LNK | P-019 | Sana Nakamura | 2025-01-10 | 2025-02-23 | 6.6 | 8.5 | Closed
WI-0779 | REQ-0390 | MustShip | COMM-LNK | P-004 | Dmitri Eriksen | 2026-01-11 | 2026-02-07 | 13.9 | 14.7 | Closed
WI-0780 | REQ-0391 | MustShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-03-28 | 2025-04-18 | 17.3 | 17.1 | Closed
WI-0781 | REQ-0391 | MustShip | PWR-MGMT | P-004 | Dmitri Eriksen | 2026-04-04 | 2026-05-09 | 15.3 | 17.7 | Closed
WI-0782 | REQ-0392 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2026-05-05 | 2026-06-22 | 13.1 | 17.4 | Closed
WI-0783 | REQ-0392 | MustShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2026-04-11 | 2026-05-12 | 24.1 | 26.8 | Closed
WI-0784 | REQ-0393 | Nice | REL-MECH | P-018 | Rafael Grigorescu | 2026-03-03 | 2026-03-20 | 21.3 | 19.8 | Closed
WI-0785 | REQ-0393 | Nice | REL-MECH | P-017 | Quentin Zielinski | 2025-02-16 | 2025-02-19 | 22.5 | 16.9 | Closed
WI-0786 | REQ-0394 | MustShip | NAV-SENS | P-010 | Jonas Weatherby | 2025-09-06 | 2025-10-04 | 19 | 20.5 | Closed
WI-0787 | REQ-0394 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2025-09-12 | 2025-10-28 | 29.1 | 38 | Closed
WI-0788 | REQ-0395 | ShouldShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2025-12-28 | 2026-02-01 | 32.9 | 38.2 | Closed
WI-0789 | REQ-0395 | ShouldShip | PWR-MGMT | P-005 | Elena Lindqvist | 2026-06-13 | 2026-07-13 | 15.2 | 16.8 | Closed
WI-0790 | REQ-0395 | ShouldShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2026-02-13 | 2026-02-16 | 17 | 12.8 | Closed
WI-0791 | REQ-0396 | Nice | REL-MECH | P-010 | Jonas Weatherby | 2025-01-21 | 2025-02-26 | 9.9 | 11.6 | Closed
WI-0792 | REQ-0396 | Nice | REL-MECH | P-013 | Mei Thackeray | 2025-07-16 | 2025-08-22 | 11.8 | 14 | Closed
WI-0793 | REQ-0396 | Nice | REL-MECH | P-005 | Elena Lindqvist | 2025-10-13 | 2025-10-27 | 4.6 | 4.1 | Closed
WI-0794 | REQ-0397 | MustShip | REL-MECH | P-015 | Olabisi Jindal | 2025-09-19 | 2025-10-25 | 24.8 | 29 | Closed
WI-0795 | REQ-0397 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2025-09-12 | 2025-09-20 | 13.9 | 11.4 | Closed
WI-0796 | REQ-0398 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-06-17 | 2025-07-23 | 30.9 | 36.5 | Closed
WI-0797 | REQ-0398 | MustShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-04-08 | 2025-05-21 | 28.9 | 36.7 | Closed
WI-0798 | REQ-0398 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-07-24 | 2025-09-11 | 27.9 | 37.2 | Closed
WI-0799 | REQ-0399 | Nice | DIAG-LOG | P-008 | Hiroshi Ibarra | 2025-04-01 | 2025-05-04 | 15.3 | 17.5 | Closed
WI-0800 | REQ-0399 | Nice | DIAG-LOG | P-015 | Olabisi Jindal | 2026-05-09 | 2026-06-01 | 7.2 | 7.4 | Closed
WI-0801 | REQ-0400 | Nice | PWR-MGMT | P-011 | Katya Fairweather | 2025-06-27 | 2025-08-18 | 14 | 19.3 | Closed
WI-0802 | REQ-0400 | Nice | PWR-MGMT | P-017 | Quentin Zielinski | 2026-06-02 | 2026-07-07 | 30.6 | 35.5 | Closed
WI-0803 | REQ-0400 | Nice | PWR-MGMT | P-001 | Aditi Halvorsen | 2025-10-29 | 2025-12-04 | 12.4 | 14.7 | Closed
WI-0804 | REQ-0401 | MustShip | REL-MECH | P-010 | Jonas Weatherby | 2026-05-20 | 2026-06-25 | 3.3 | 3.9 | Closed
WI-0805 | REQ-0401 | MustShip | REL-MECH | P-013 | Mei Thackeray | 2025-09-13 |  | 19.7 |  | InProgress
WI-0806 | REQ-0401 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-09-30 | 2025-11-13 | 30.9 | 39.4 | Closed
WI-0807 | REQ-0401 | MustShip | REL-MECH | P-014 | Nils Castellan | 2026-05-20 | 2026-07-12 | 2.6 | 3.7 | Closed
WI-0808 | REQ-0402 | MustShip | GND-CTRL | P-011 | Katya Fairweather | 2025-03-15 | 2025-04-15 | 17.1 | 19.1 | Closed
WI-0809 | REQ-0402 | MustShip | GND-CTRL | P-004 | Dmitri Eriksen | 2025-11-30 | 2025-12-22 | 18.7 | 18.7 | Closed
WI-0810 | REQ-0403 | Nice | DIAG-LOG | P-003 | Camille Villalobos | 2026-06-06 | 2026-06-29 | 13.6 | 13.7 | Closed
WI-0811 | REQ-0403 | Nice | DIAG-LOG | P-012 | Liam Moreau | 2025-05-27 | 2025-06-13 | 19.6 | 18.4 | Closed
WI-0812 | REQ-0404 | ShouldShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-01-11 | 2025-03-07 | 18.5 | 26.3 | Closed
WI-0813 | REQ-0405 | MustShip | DIAG-LOG | P-019 | Sana Nakamura | 2026-04-13 | 2026-05-21 | 27 | 32.4 | Closed
WI-0814 | REQ-0405 | MustShip | DIAG-LOG | P-015 | Olabisi Jindal | 2025-01-27 | 2025-03-23 | 17.8 | 25.2 | Closed
WI-0815 | REQ-0405 | MustShip | DIAG-LOG | P-008 | Hiroshi Ibarra | 2026-04-23 | 2026-05-31 | 28.2 | 33.7 | Closed
WI-0816 | REQ-0406 | ShouldShip | REL-MECH | P-009 | Imani Petrovic | 2026-06-29 | 2026-08-24 | 22.4 | 32.1 | Closed
WI-0817 | REQ-0406 | ShouldShip | REL-MECH | P-002 | Bruno Oyelaran | 2025-09-30 | 2025-10-16 | 30.9 | 28.5 | Closed
WI-0818 | REQ-0407 | ShouldShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-05-01 | 2025-05-19 | 11.7 | 11 | Closed
WI-0819 | REQ-0407 | ShouldShip | FLT-CTRL | P-009 | Imani Petrovic | 2026-01-17 | 2026-01-29 | 32 | 27.6 | Closed
WI-0820 | REQ-0408 | Nice | NAV-SENS | P-020 | Tomas Ustinov | 2025-09-25 | 2025-11-18 | 23.8 | 33.6 | Closed
WI-0821 | REQ-0408 | Nice | NAV-SENS | P-016 | Priya Quintana | 2025-07-22 | 2025-08-19 | 2.7 | 2.9 | Closed
WI-0822 | REQ-0408 | Nice | NAV-SENS | P-020 | Tomas Ustinov | 2026-06-08 | 2026-07-13 | 26.7 | 31.1 | Closed
WI-0823 | REQ-0409 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2025-04-23 | 2025-05-23 | 35 | 38.4 | Closed
WI-0824 | REQ-0409 | MustShip | COMM-LNK | P-015 | Olabisi Jindal | 2026-06-02 |  | 9.6 |  | Open
WI-0825 | REQ-0410 | MustShip | COMM-LNK | P-017 | Quentin Zielinski | 2026-06-20 | 2026-07-28 | 26 | 31.2 | Closed
WI-0826 | REQ-0411 | MustShip | COMM-LNK | P-018 | Rafael Grigorescu | 2025-02-13 | 2025-04-02 | 28.5 | 37.8 | Closed
WI-0827 | REQ-0411 | MustShip | COMM-LNK | P-017 | Quentin Zielinski | 2025-03-11 | 2025-04-27 | 20.4 | 26.8 | Closed
WI-0828 | REQ-0411 | MustShip | COMM-LNK | P-020 | Tomas Ustinov | 2025-12-19 | 2026-02-11 | 12.3 | 17.3 | Closed
WI-0829 | REQ-0412 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-01-22 | 2025-02-07 | 32.7 | 30 | Closed
WI-0830 | REQ-0412 | MustShip | REL-MECH | P-004 | Dmitri Eriksen | 2026-06-23 | 2026-08-10 | 8.3 | 11.1 | Closed
WI-0831 | REQ-0412 | MustShip | REL-MECH | P-011 | Katya Fairweather | 2025-07-10 | 2025-07-31 | 3.4 | 3.3 | Closed
WI-0832 | REQ-0413 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2025-07-13 | 2025-08-02 | 22.5 | 22 | Closed
WI-0833 | REQ-0413 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2025-06-24 | 2025-08-05 | 12.7 | 15.9 | Closed
WI-0834 | REQ-0413 | MustShip | COMM-LNK | P-009 | Imani Petrovic | 2025-05-27 | 2025-07-11 | 33.9 | 43.6 | Closed
WI-0835 | REQ-0414 | Nice | COMM-LNK | P-005 | Elena Lindqvist | 2025-05-14 | 2025-05-20 | 35.8 | 28.4 | Closed
WI-0836 | REQ-0414 | Nice | COMM-LNK | P-004 | Dmitri Eriksen | 2026-04-14 | 2026-06-08 | 27.7 | 39.1 | Closed
WI-0837 | REQ-0415 | MustShip | STRUCT-I | P-015 | Olabisi Jindal | 2026-05-29 | 2026-06-02 | 4.2 | 3.2 | Closed
WI-0838 | REQ-0416 | MustShip | COMM-LNK | P-009 | Imani Petrovic | 2026-05-03 | 2026-05-13 | 23.3 | 19.7 | Closed
WI-0839 | REQ-0416 | MustShip | COMM-LNK | P-002 | Bruno Oyelaran | 2026-06-13 | 2026-06-18 | 26.6 | 21 | Closed
WI-0840 | REQ-0417 | MustShip | FLT-CTRL | P-014 | Nils Castellan | 2025-07-25 | 2025-09-01 | 8.9 | 10.7 | Closed
WI-0841 | REQ-0418 | ShouldShip | DIAG-LOG | P-006 | Farid Saltzman | 2025-03-20 | 2025-05-12 | 16.7 | 23.4 | Closed
WI-0842 | REQ-0418 | ShouldShip | DIAG-LOG | P-015 | Olabisi Jindal | 2025-06-05 | 2025-08-01 | 29.4 | 42.5 | Closed
WI-0843 | REQ-0419 | MustShip | DIAG-LOG | P-016 | Priya Quintana | 2025-03-09 | 2025-04-10 | 33.4 | 37.8 | Closed
WI-0844 | REQ-0419 | MustShip | DIAG-LOG | P-011 | Katya Fairweather | 2025-02-25 | 2025-03-19 | 19.9 | 19.8 | Closed
WI-0845 | REQ-0419 | MustShip | DIAG-LOG | P-002 | Bruno Oyelaran | 2025-01-22 | 2025-01-27 | 25.6 | 20.1 | Closed
WI-0846 | REQ-0420 | MustShip | PWR-MGMT | P-014 | Nils Castellan | 2025-06-04 | 2025-07-20 | 9.7 | 12.7 | Closed
WI-0847 | REQ-0420 | MustShip | PWR-MGMT | P-018 | Rafael Grigorescu | 2026-01-26 | 2026-02-19 | 35.3 | 36 | Closed
WI-0848 | REQ-0421 | MustShip | NAV-SENS | P-017 | Quentin Zielinski | 2025-10-11 | 2025-10-15 | 16.3 | 12.6 | Closed
WI-0849 | REQ-0423 | MustShip | FLT-CTRL | P-008 | Hiroshi Ibarra | 2025-11-24 |  | 4.8 |  | InProgress
WI-0850 | REQ-0423 | MustShip | FLT-CTRL | P-014 | Nils Castellan | 2025-12-16 | 2026-01-15 | 25.1 | 27.5 | Closed
WI-0851 | REQ-0424 | MustShip | STRUCT-I | P-002 | Bruno Oyelaran | 2025-08-29 | 2025-09-07 | 15.6 | 13 | Closed
WI-0852 | REQ-0424 | MustShip | STRUCT-I | P-004 | Dmitri Eriksen | 2026-02-14 | 2026-03-02 | 18 | 16.6 | Closed
WI-0853 | REQ-0425 | MustShip | COMM-LNK | P-002 | Bruno Oyelaran | 2025-04-24 | 2025-05-18 | 34.8 | 35.6 | Closed
WI-0854 | REQ-0425 | MustShip | COMM-LNK | P-010 | Jonas Weatherby | 2026-01-26 | 2026-02-01 | 6.6 | 5.3 | Closed
WI-0855 | REQ-0426 | MustShip | STRUCT-I | P-008 | Hiroshi Ibarra | 2026-06-23 | 2026-08-09 | 7.6 | 10.1 | Closed
WI-0856 | REQ-0427 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2025-06-09 | 2025-07-26 | 22.8 | 30.1 | Closed
WI-0857 | REQ-0428 | MustShip | GND-CTRL | P-010 | Jonas Weatherby | 2026-01-20 | 2026-03-09 | 17.3 | 23 | Closed
WI-0858 | REQ-0429 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2025-12-03 | 2025-12-18 | 24.5 | 22.2 | Closed
WI-0859 | REQ-0429 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2026-04-14 | 2026-05-18 | 32 | 36.8 | Closed
WI-0860 | REQ-0429 | MustShip | REL-MECH | P-016 | Priya Quintana | 2026-01-09 | 2026-02-02 | 31.3 | 31.9 | Closed
WI-0861 | REQ-0431 | ShouldShip | COMM-LNK | P-004 | Dmitri Eriksen | 2026-03-21 | 2026-03-26 | 5.4 | 4.2 | Closed
WI-0862 | REQ-0432 | ShouldShip | DIAG-LOG | P-011 | Katya Fairweather | 2026-02-04 | 2026-03-12 | 21.8 | 25.6 | Closed
WI-0863 | REQ-0433 | MustShip | PWR-MGMT | P-003 | Camille Villalobos | 2025-10-10 | 2025-10-15 | 9.7 | 7.5 | Closed
WI-0864 | REQ-0433 | MustShip | PWR-MGMT | P-017 | Quentin Zielinski | 2025-06-16 | 2025-06-25 | 28.9 | 24.2 | Closed
WI-0865 | REQ-0434 | MustShip | STRUCT-I | P-019 | Sana Nakamura | 2025-12-22 | 2026-01-07 | 16.2 | 15.1 | Closed
WI-0866 | REQ-0434 | MustShip | STRUCT-I | P-017 | Quentin Zielinski | 2025-06-03 | 2025-07-27 | 24.8 | 34.7 | Closed
WI-0867 | REQ-0435 | MustShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2026-05-09 | 2026-05-15 | 28 | 22.4 | Closed
WI-0868 | REQ-0436 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2025-05-13 | 2025-06-24 | 25.6 | 32 | Closed
WI-0869 | REQ-0436 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2026-06-23 | 2026-08-05 | 34 | 42.9 | Closed
WI-0870 | REQ-0436 | ShouldShip | PWR-MGMT | P-009 | Imani Petrovic | 2026-06-18 | 2026-08-10 | 10.9 | 15.2 | Closed
WI-0871 | REQ-0437 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-09-16 | 2025-10-31 | 27.6 | 35.6 | Closed
WI-0872 | REQ-0437 | ShouldShip | PWR-MGMT | P-009 | Imani Petrovic | 2025-09-29 | 2025-11-14 | 33.9 | 44.4 | Closed
WI-0873 | REQ-0437 | ShouldShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-12-24 | 2026-02-12 | 34.4 | 46.6 | Closed
WI-0874 | REQ-0438 | MustShip | FLT-CTRL | P-009 | Imani Petrovic | 2025-09-11 | 2025-10-18 | 29.5 | 35.1 | Closed
WI-0875 | REQ-0438 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-06-05 | 2026-07-22 | 11.8 | 15.5 | Closed
WI-0876 | REQ-0438 | MustShip | FLT-CTRL | P-003 | Camille Villalobos | 2025-07-16 | 2025-08-17 | 3.8 | 4.3 | Closed
WI-0877 | REQ-0439 | MustShip | REL-MECH | P-017 | Quentin Zielinski | 2025-05-08 | 2025-06-13 | 16.3 | 19.1 | Closed
WI-0878 | REQ-0439 | MustShip | REL-MECH | P-004 | Dmitri Eriksen | 2026-01-09 | 2026-02-08 | 24.3 | 26.8 | Closed
WI-0879 | REQ-0440 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2025-02-17 | 2025-02-23 | 16.8 | 13.3 | Closed
WI-0880 | REQ-0440 | MustShip | NAV-SENS | P-015 | Olabisi Jindal | 2025-08-23 | 2025-10-01 | 10.1 | 12.3 | Closed
WI-0881 | REQ-0441 | MustShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-06-16 | 2025-06-26 | 27.2 | 23.1 | Closed
WI-0882 | REQ-0441 | MustShip | PWR-MGMT | P-012 | Liam Moreau | 2025-09-07 | 2025-09-15 | 15.8 | 12.9 | Closed
WI-0883 | REQ-0441 | MustShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2025-05-04 | 2025-04-28 | 13.2 | 12.8 | Closed
WI-0884 | REQ-0442 | ShouldShip | REL-MECH | P-017 | Quentin Zielinski | 2026-04-09 | 2026-06-01 | 23.4 | 32.6 | Closed
WI-0885 | REQ-0442 | ShouldShip | REL-MECH | P-004 | Dmitri Eriksen | 2026-02-18 | 2026-02-22 | 21.6 | 16.7 | Closed
WI-0886 | REQ-0443 | MustShip | COMM-LNK | P-010 | Jonas Weatherby | 2026-03-15 | 2026-03-27 | 10.1 | 8.8 | Closed
WI-0887 | REQ-0443 | MustShip | COMM-LNK | P-006 | Farid Saltzman | 2025-05-30 | 2025-07-12 | 21.2 | 26.7 | Closed
WI-0888 | REQ-0443 | MustShip | COMM-LNK | P-013 | Mei Thackeray | 2026-01-16 | 2026-03-11 | 23.5 | 33 | Closed
WI-0889 | REQ-0444 | MustShip | NAV-SENS | P-016 | Priya Quintana | 2026-05-21 | 2026-07-01 | 13.5 | 16.8 | Closed
WI-0890 | REQ-0444 | MustShip | NAV-SENS | P-003 | Camille Villalobos | 2026-06-10 | 2026-06-17 | 31.3 | 25.3 | Closed
WI-0891 | REQ-0445 | MustShip | PWR-MGMT | P-003 | Camille Villalobos | 2025-07-13 | 2025-08-25 | 6.4 | 8 | Closed
WI-0892 | REQ-0445 | MustShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-05-20 | 2025-06-04 | 26.5 | 24.2 | Closed
WI-0893 | REQ-0445 | MustShip | PWR-MGMT | P-013 | Mei Thackeray | 2026-03-19 | 2026-05-11 | 27.9 | 39 | Closed
WI-0894 | REQ-0446 | ShouldShip | REL-MECH | P-005 | Elena Lindqvist | 2025-08-20 | 2025-09-08 | 20.2 | 19.5 | Closed
WI-0895 | REQ-0446 | ShouldShip | REL-MECH | P-018 | Rafael Grigorescu | 2025-03-05 |  | 22.1 |  | InProgress
WI-0896 | REQ-0447 | ShouldShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2025-10-03 | 2025-10-06 | 30.5 | 23.1 | Closed
WI-0897 | REQ-0447 | ShouldShip | NAV-SENS | P-009 | Imani Petrovic | 2026-05-27 | 2026-06-12 | 31.3 | 28.9 | Closed
WI-0898 | REQ-0448 | Nice | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-09-07 | 2025-10-31 | 24.2 | 34 | Closed
WI-0899 | REQ-0448 | Nice | PWR-MGMT | P-005 | Elena Lindqvist | 2025-05-01 | 2025-06-06 | 22.7 | 26.6 | Closed
WI-0900 | REQ-0449 | MustShip | REL-MECH | P-006 | Farid Saltzman | 2026-04-09 | 2026-05-10 | 24.5 | 27.3 | Closed
WI-0901 | REQ-0449 | MustShip | REL-MECH | P-016 | Priya Quintana | 2026-04-02 | 2026-05-08 | 29.6 | 34.8 | Closed
WI-0902 | REQ-0450 | Nice | DIAG-LOG | P-001 | Aditi Halvorsen | 2026-01-29 | 2026-02-13 | 5.1 | 4.6 | Closed
WI-0903 | REQ-0450 | Nice | DIAG-LOG | P-021 | Ulrike Dalgleish | 2025-09-23 | 2025-10-31 | 19.3 | 23.2 | Closed
WI-0904 | REQ-0450 | Nice | DIAG-LOG | P-009 | Imani Petrovic | 2026-04-20 | 2026-05-20 | 23.1 | 25.4 | Closed
WI-0905 | REQ-0450 | Nice | DIAG-LOG | P-021 | Ulrike Dalgleish | 2026-02-12 |  | 14.3 |  | InProgress
WI-0906 | REQ-0451 | MustShip | DIAG-LOG | P-011 | Katya Fairweather | 2025-11-25 | 2026-01-04 | 14.8 | 18.1 | Closed
WI-0907 | REQ-0451 | MustShip | DIAG-LOG | P-013 | Mei Thackeray | 2025-03-05 | 2025-03-10 | 16.7 | 13.1 | Closed
WI-0908 | REQ-0451 | MustShip | DIAG-LOG | P-017 | Quentin Zielinski | 2025-05-08 | 2025-05-19 | 12.6 | 10.8 | Closed
WI-0909 | REQ-0452 | MustShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-10-01 | 2025-11-17 | 19 | 25.1 | Closed
WI-0910 | REQ-0452 | MustShip | PWR-MGMT | P-019 | Sana Nakamura | 2025-08-02 | 2025-09-20 | 16.1 | 21.6 | Closed
WI-0911 | REQ-0452 | MustShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-10-22 | 2025-12-10 | 35.4 | 47.5 | Closed
WI-0912 | REQ-0453 | ShouldShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-08-20 | 2025-10-13 | 19.9 | 27.9 | Closed
WI-0913 | REQ-0453 | ShouldShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2025-08-25 | 2025-09-25 | 8.9 | 9.9 | Closed
WI-0914 | REQ-0453 | ShouldShip | PWR-MGMT | P-013 | Mei Thackeray | 2025-02-09 | 2025-04-05 | 10.5 | 14.8 | Closed
WI-0915 | REQ-0454 | Nice | REL-MECH | P-014 | Nils Castellan | 2026-01-24 | 2026-03-07 | 30.2 | 38 | Closed
WI-0916 | REQ-0455 | MustShip | COMM-LNK | P-010 | Jonas Weatherby | 2025-07-17 | 2025-08-24 | 17.6 | 21.3 | Closed
WI-0917 | REQ-0455 | MustShip | COMM-LNK | P-012 | Liam Moreau | 2025-12-04 | 2026-01-21 | 24.3 | 32.3 | Closed
WI-0918 | REQ-0455 | MustShip | COMM-LNK | P-016 | Priya Quintana | 2026-05-31 | 2026-07-05 | 13.1 | 15.2 | Closed
WI-0919 | REQ-0456 | MustShip | COMM-LNK | P-011 | Katya Fairweather | 2025-01-08 | 2025-01-22 | 23.6 | 21.2 | Closed
WI-0920 | REQ-0456 | MustShip | COMM-LNK | P-008 | Hiroshi Ibarra | 2025-08-02 | 2025-08-11 | 16.9 | 14.1 | Closed
WI-0921 | REQ-0457 | MustShip | PWR-MGMT | P-021 | Ulrike Dalgleish | 2026-02-08 | 2026-03-03 | 9.7 | 9.8 | Closed
WI-0922 | REQ-0458 | MustShip | NAV-SENS | P-001 | Aditi Halvorsen | 2025-10-03 | 2025-11-13 | 18.6 | 23.2 | Closed
WI-0923 | REQ-0458 | MustShip | NAV-SENS | P-009 | Imani Petrovic | 2025-03-14 | 2025-04-08 | 29.6 | 30.8 | Closed
WI-0924 | REQ-0458 | MustShip | NAV-SENS | P-003 | Camille Villalobos | 2025-04-06 | 2025-04-29 | 12.3 | 12.4 | Closed
WI-0925 | REQ-0459 | MustShip | PWR-MGMT | P-010 | Jonas Weatherby | 2025-09-02 | 2025-09-06 | 20 | 15.4 | Closed
WI-0926 | REQ-0459 | MustShip | PWR-MGMT | P-020 | Tomas Ustinov | 2025-03-02 | 2025-03-10 | 3 | 2.4 | Closed
WI-0927 | REQ-0460 | MustShip | NAV-SENS | P-019 | Sana Nakamura | 2026-06-21 |  | 32.7 |  | Open
WI-0928 | REQ-0461 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-03-03 | 2025-03-08 | 12.7 | 10 | Closed
WI-0929 | REQ-0461 | ShouldShip | PWR-MGMT | P-012 | Liam Moreau | 2025-02-21 | 2025-03-25 | 18.6 | 20.8 | Closed
WI-0930 | REQ-0461 | ShouldShip | PWR-MGMT | P-018 | Rafael Grigorescu | 2025-04-19 | 2025-06-15 | 29.3 | 42.2 | Closed
WI-0931 | REQ-0462 | Nice | COMM-LNK | P-016 | Priya Quintana | 2026-04-17 | 2026-04-30 | 14.2 | 12.5 | Closed
WI-0932 | REQ-0463 | ShouldShip | FLT-CTRL | P-013 | Mei Thackeray | 2025-02-20 | 2025-03-11 | 25.9 | 25 | Closed
WI-0933 | REQ-0463 | ShouldShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2025-06-27 | 2025-07-30 | 13.8 | 15.7 | Closed
WI-0934 | REQ-0464 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2026-06-08 | 2026-07-29 | 6.3 | 8.6 | Closed
WI-0935 | REQ-0465 | MustShip | NAV-SENS | P-006 | Farid Saltzman | 2026-04-05 | 2026-05-12 | 14.1 | 16.7 | Closed
WI-0936 | REQ-0465 | MustShip | NAV-SENS | P-002 | Bruno Oyelaran | 2026-03-14 | 2026-04-21 | 16.4 | 19.8 | Closed
WI-0937 | REQ-0465 | MustShip | NAV-SENS | P-007 | Grace Baptiste | 2026-01-23 | 2026-02-15 | 23.7 | 23.9 | Closed
WI-0938 | REQ-0466 | ShouldShip | REL-MECH | P-016 | Priya Quintana | 2025-08-05 | 2025-08-23 | 21.7 | 20.5 | Closed
WI-0939 | REQ-0466 | ShouldShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-05-23 | 2025-06-23 | 31.6 | 35.3 | Closed
WI-0940 | REQ-0466 | ShouldShip | REL-MECH | P-014 | Nils Castellan | 2026-04-21 |  | 2.1 |  | InProgress
WI-0941 | REQ-0467 | MustShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2026-01-21 | 2026-03-07 | 28.3 | 36.8 | Closed
WI-0942 | REQ-0467 | MustShip | FLT-CTRL | P-008 | Hiroshi Ibarra | 2026-04-21 | 2026-06-10 | 6.3 | 8.5 | Closed
WI-0943 | REQ-0467 | MustShip | FLT-CTRL | P-020 | Tomas Ustinov | 2026-02-22 | 2026-04-05 | 35.4 | 44.3 | Closed
WI-0944 | REQ-0468 | MustShip | GND-CTRL | P-020 | Tomas Ustinov | 2025-11-05 | 2025-11-25 | 21.6 | 21.1 | Closed
WI-0945 | REQ-0468 | MustShip | GND-CTRL | P-013 | Mei Thackeray | 2025-06-24 | 2025-08-11 | 14.1 | 18.6 | Closed
WI-0946 | REQ-0469 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2026-06-18 | 2026-07-10 | 34.5 | 34.4 | Closed
WI-0947 | REQ-0469 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2025-11-09 | 2025-11-30 | 3 | 3 | Closed
WI-0948 | REQ-0469 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2026-04-17 | 2026-06-05 | 30.5 | 41 | Closed
WI-0949 | REQ-0470 | Nice | PWR-MGMT | P-017 | Quentin Zielinski | 2025-02-15 | 2025-02-22 | 11.8 | 9.5 | Closed
WI-0950 | REQ-0471 | MustShip | COMM-LNK | P-007 | Grace Baptiste | 2025-07-11 | 2025-09-06 | 23.1 | 33.3 | Closed
WI-0951 | REQ-0472 | MustShip | FLT-CTRL | P-016 | Priya Quintana | 2026-04-07 | 2026-05-26 | 20.6 | 27.5 | Closed
WI-0952 | REQ-0472 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2026-01-11 | 2026-01-24 | 29.2 | 25.7 | Closed
WI-0953 | REQ-0472 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2025-10-02 | 2025-10-08 | 27.1 | 21.6 | Closed
WI-0954 | REQ-0473 | MustShip | REL-MECH | P-020 | Tomas Ustinov | 2026-05-06 | 2026-05-14 | 26.6 | 21.8 | Closed
WI-0955 | REQ-0473 | MustShip | REL-MECH | P-001 | Aditi Halvorsen | 2025-11-05 | 2025-11-18 | 13.2 | 11.7 | Closed
WI-0956 | REQ-0473 | MustShip | REL-MECH | P-021 | Ulrike Dalgleish | 2025-08-07 | 2025-09-09 | 31 | 35.3 | Closed
WI-0957 | REQ-0474 | MustShip | DIAG-LOG | P-003 | Camille Villalobos | 2026-06-17 | 2026-07-11 | 35 | 36 | Closed
WI-0958 | REQ-0474 | MustShip | DIAG-LOG | P-015 | Olabisi Jindal | 2025-12-03 | 2026-01-19 | 22.6 | 29.7 | Closed
WI-0959 | REQ-0475 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-11-09 | 2026-01-01 | 2.5 | 3.5 | Closed
WI-0960 | REQ-0475 | MustShip | REL-MECH | P-015 | Olabisi Jindal | 2025-08-19 | 2025-09-11 | 26.2 | 26.3 | Closed
WI-0961 | REQ-0475 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-06-28 | 2025-07-27 | 6.8 | 7.4 | Closed
WI-0962 | REQ-0476 | ShouldShip | PWR-MGMT | P-015 | Olabisi Jindal | 2025-11-24 | 2025-12-07 | 8.2 | 7.2 | Closed
WI-0963 | REQ-0476 | ShouldShip | PWR-MGMT | P-008 | Hiroshi Ibarra | 2026-03-13 | 2026-03-26 | 18.8 | 16.7 | Closed
WI-0964 | REQ-0476 | ShouldShip | PWR-MGMT | P-001 | Aditi Halvorsen | 2025-02-17 | 2025-03-06 | 3.8 | 3.5 | Closed
WI-0965 | REQ-0477 | Nice | GND-CTRL | P-018 | Rafael Grigorescu | 2025-06-14 | 2025-08-02 | 23.2 | 31.1 | Closed
WI-0966 | REQ-0477 | Nice | GND-CTRL | P-017 | Quentin Zielinski | 2025-08-27 | 2025-10-10 | 6.5 | 8.3 | Closed
WI-0967 | REQ-0477 | Nice | GND-CTRL | P-013 | Mei Thackeray | 2025-11-13 | 2025-12-27 | 34.7 | 44.1 | Closed
WI-0968 | REQ-0478 | MustShip | FLT-CTRL | P-004 | Dmitri Eriksen | 2026-02-05 | 2026-03-11 | 34.3 | 39.7 | Closed
WI-0969 | REQ-0478 | MustShip | FLT-CTRL | P-015 | Olabisi Jindal | 2025-06-08 | 2025-07-10 | 28.1 | 31.8 | Closed
WI-0970 | REQ-0478 | MustShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2025-06-24 | 2025-06-29 | 16.3 | 12.8 | Closed
WI-0971 | REQ-0479 | MustShip | COMM-LNK | P-015 | Olabisi Jindal | 2025-01-07 | 2025-01-16 | 14 | 11.6 | Closed
WI-0972 | REQ-0480 | ShouldShip | PWR-MGMT | P-017 | Quentin Zielinski | 2026-02-24 | 2026-03-28 | 21.4 | 24.1 | Closed
WI-0973 | REQ-0480 | ShouldShip | PWR-MGMT | P-014 | Nils Castellan | 2026-04-16 | 2026-05-24 | 34.5 | 41.7 | Closed
WI-0974 | REQ-0480 | ShouldShip | PWR-MGMT | P-013 | Mei Thackeray | 2025-10-10 | 2025-11-02 | 29.8 | 30.2 | Closed
WI-0975 | REQ-0481 | MustShip | REL-MECH | P-021 | Ulrike Dalgleish | 2025-12-26 | 2026-01-20 | 32.4 | 33.5 | Closed
WI-0976 | REQ-0481 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-05-17 | 2025-06-15 | 24.4 | 26.5 | Closed
WI-0977 | REQ-0482 | MustShip | GND-CTRL | P-003 | Camille Villalobos | 2025-12-18 | 2025-12-30 | 17.8 | 15.4 | Closed
WI-0978 | REQ-0483 | ShouldShip | COMM-LNK | P-005 | Elena Lindqvist | 2025-10-22 | 2025-12-13 | 28.6 | 39.5 | Closed
WI-0979 | REQ-0483 | ShouldShip | COMM-LNK | P-009 | Imani Petrovic | 2026-02-12 | 2026-02-25 | 29.7 | 26.3 | Closed
WI-0980 | REQ-0484 | Nice | DIAG-LOG | P-010 | Jonas Weatherby | 2026-05-02 | 2026-05-21 | 8.1 | 7.8 | Closed
WI-0981 | REQ-0485 | ShouldShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2026-01-11 | 2026-01-15 | 29.9 | 23.1 | Closed
WI-0982 | REQ-0485 | ShouldShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-01-16 | 2025-03-10 | 29.2 | 40.8 | Closed
WI-0983 | REQ-0486 | MustShip | PWR-MGMT | P-002 | Bruno Oyelaran | 2025-07-02 | 2025-08-21 | 20.8 | 28.2 | Closed
WI-0984 | REQ-0487 | ShouldShip | GND-CTRL | P-014 | Nils Castellan | 2025-10-25 | 2025-11-01 | 29.5 | 23.9 | Closed
WI-0985 | REQ-0488 | MustShip | REL-MECH | P-012 | Liam Moreau | 2025-12-21 | 2025-12-29 | 15 | 12.4 | Closed
WI-0986 | REQ-0489 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2025-03-28 | 2025-05-17 | 29.5 | 39.9 | Closed
WI-0987 | REQ-0489 | ShouldShip | NAV-SENS | P-015 | Olabisi Jindal | 2025-09-29 | 2025-10-18 | 11.1 | 10.7 | Closed
WI-0988 | REQ-0489 | ShouldShip | NAV-SENS | P-015 | Olabisi Jindal | 2025-04-14 | 2025-05-14 | 3.5 | 3.8 | Closed
WI-0989 | REQ-0489 | ShouldShip | NAV-SENS | P-019 | Sana Nakamura | 2026-02-03 | 2026-03-20 | 11.6 | 15 | Closed
WI-0990 | REQ-0490 | ShouldShip | NAV-SENS | P-011 | Katya Fairweather | 2026-02-05 | 2026-03-10 | 32 | 36.4 | Closed
WI-0991 | REQ-0490 | ShouldShip | NAV-SENS | P-006 | Farid Saltzman | 2026-02-09 | 2026-02-26 | 14.9 | 14 | Closed
WI-0992 | REQ-0491 | ShouldShip | DIAG-LOG | P-016 | Priya Quintana | 2025-07-03 | 2025-06-27 | 6.7 | 5.5 | Closed
WI-0993 | REQ-0492 | ShouldShip | GND-CTRL | P-007 | Grace Baptiste | 2025-07-01 | 2025-07-15 | 2.2 | 2 | Closed
WI-0994 | REQ-0493 | MustShip | REL-MECH | P-016 | Priya Quintana | 2025-06-11 | 2025-07-18 | 18.1 | 21.6 | Closed
WI-0995 | REQ-0493 | MustShip | REL-MECH | P-007 | Grace Baptiste | 2025-02-01 | 2025-03-05 | 16.8 | 19 | Closed
WI-0996 | REQ-0493 | MustShip | REL-MECH | P-005 | Elena Lindqvist | 2026-03-24 | 2026-05-01 | 16.8 | 20.2 | Closed
WI-0997 | REQ-0493 | MustShip | REL-MECH | P-016 | Priya Quintana | 2025-07-25 | 2025-08-02 | 2.4 | 1.9 | Closed
WI-0998 | REQ-0494 | MustShip | PWR-MGMT | P-015 | Olabisi Jindal | 2026-05-29 | 2026-06-20 | 27.4 | 27.5 | Closed
WI-0999 | REQ-0494 | MustShip | PWR-MGMT | P-006 | Farid Saltzman | 2025-02-19 | 2025-04-03 | 5.2 | 6.6 | Closed
WI-1000 | REQ-0495 | ShouldShip | REL-MECH | P-003 | Camille Villalobos | 2025-06-26 | 2025-07-09 | 10.4 | 9.2 | Closed
WI-1001 | REQ-0495 | ShouldShip | REL-MECH | P-018 | Rafael Grigorescu | 2025-10-08 | 2025-10-11 | 5.3 | 4 | Closed
WI-1002 | REQ-0495 | ShouldShip | REL-MECH | P-003 | Camille Villalobos | 2025-10-09 | 2025-10-24 | 15.6 | 14.2 | Closed
WI-1003 | REQ-0496 | MustShip | NAV-SENS | P-007 | Grace Baptiste | 2026-04-05 | 2026-05-02 | 10.6 | 11.3 | Closed
WI-1004 | REQ-0496 | MustShip | NAV-SENS | P-005 | Elena Lindqvist | 2025-08-04 | 2025-09-20 | 26.7 | 35.2 | Closed
WI-1005 | REQ-0496 | MustShip | NAV-SENS | P-014 | Nils Castellan | 2026-04-21 | 2026-05-21 | 29.1 | 32 | Closed
WI-1006 | REQ-0497 | MustShip | REL-MECH | P-014 | Nils Castellan | 2025-11-27 |  | 20.4 |  | InProgress
WI-1007 | REQ-0497 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2025-07-03 | 2025-08-03 | 12.9 | 14.4 | Closed
WI-1008 | REQ-0498 | MustShip | COMM-LNK | P-017 | Quentin Zielinski | 2025-08-12 | 2025-09-13 | 6.7 | 7.6 | Closed
WI-1009 | REQ-0498 | MustShip | COMM-LNK | P-001 | Aditi Halvorsen | 2026-01-27 | 2026-03-21 | 35 | 48.7 | Closed
WI-1010 | REQ-0499 | MustShip | REL-MECH | P-003 | Camille Villalobos | 2025-07-29 | 2025-09-01 | 8 | 9.2 | Closed
WI-1011 | REQ-0500 | ShouldShip | NAV-SENS | P-003 | Camille Villalobos | 2025-05-27 | 2025-07-11 | 11.5 | 14.8 | Closed
WI-1012 | REQ-0501 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2025-07-16 | 2025-09-05 | 10.2 | 13.8 | Closed
WI-1013 | REQ-0502 | Nice | REL-MECH | P-010 | Jonas Weatherby | 2025-09-22 | 2025-11-15 | 16.5 | 23.2 | Closed
WI-1014 | REQ-0503 | MustShip | STRUCT-I | P-008 | Hiroshi Ibarra | 2026-03-03 | 2026-04-17 | 30 | 38.6 | Closed
WI-1015 | REQ-0503 | MustShip | STRUCT-I | P-002 | Bruno Oyelaran | 2026-01-20 | 2026-01-27 | 17.5 | 14.2 | Closed
WI-1016 | REQ-0504 | ShouldShip | COMM-LNK | P-007 | Grace Baptiste | 2025-03-28 | 2025-04-10 | 33.6 | 29.7 | Closed
WI-1017 | REQ-0504 | ShouldShip | COMM-LNK | P-015 | Olabisi Jindal | 2026-05-23 | 2026-07-05 | 15.6 | 19.8 | Closed
WI-1018 | REQ-0504 | ShouldShip | COMM-LNK | P-002 | Bruno Oyelaran | 2026-01-22 |  | 22.7 |  | Open
WI-1019 | REQ-0505 | ShouldShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-01-17 | 2026-02-19 | 7 | 8 | Closed
WI-1020 | REQ-0505 | ShouldShip | FLT-CTRL | P-012 | Liam Moreau | 2025-06-29 | 2025-08-07 | 21.1 | 25.7 | Closed
WI-1021 | REQ-0505 | ShouldShip | FLT-CTRL | P-011 | Katya Fairweather | 2026-03-08 |  | 29.5 |  | InProgress
WI-1022 | REQ-0506 | ShouldShip | COMM-LNK | P-021 | Ulrike Dalgleish | 2025-11-03 | 2025-11-12 | 29.2 | 24.2 | Closed
WI-1023 | REQ-0506 | ShouldShip | COMM-LNK | P-005 | Elena Lindqvist | 2026-05-26 | 2026-07-22 | 31.5 | 45.5 | Closed
WI-1024 | REQ-0506 | ShouldShip | COMM-LNK | P-001 | Aditi Halvorsen | 2025-08-01 | 2025-09-19 | 20.9 | 28.2 | Closed
WI-1025 | REQ-0507 | MustShip | GND-CTRL | P-003 | Camille Villalobos | 2025-11-03 | 2025-12-20 | 34.4 | 45.3 | Closed
WI-1026 | REQ-0507 | MustShip | GND-CTRL | P-015 | Olabisi Jindal | 2025-01-15 | 2025-02-08 | 20.3 | 20.7 | Closed
WI-1027 | REQ-0508 | ShouldShip | DIAG-LOG | P-015 | Olabisi Jindal | 2025-11-13 | 2025-12-19 | 7.6 | 9 | Closed
WI-1028 | REQ-0508 | ShouldShip | DIAG-LOG | P-011 | Katya Fairweather | 2025-04-02 | 2025-05-29 | 2 | 2.9 | Closed
WI-1029 | REQ-0508 | ShouldShip | DIAG-LOG | P-006 | Farid Saltzman | 2025-04-18 | 2025-04-28 | 20.7 | 17.4 | Closed
WI-1030 | REQ-0509 | Nice | PWR-MGMT | P-007 | Grace Baptiste | 2025-03-16 | 2025-04-25 | 19.8 | 24.2 | Closed
WI-1031 | REQ-0509 | Nice | PWR-MGMT | P-011 | Katya Fairweather | 2025-01-21 | 2025-02-08 | 32.5 | 31 | Closed
WI-1032 | REQ-0509 | Nice | PWR-MGMT | P-013 | Mei Thackeray | 2025-12-14 | 2026-01-10 | 27.8 | 29.7 | Closed
WI-1033 | REQ-0510 | MustShip | GND-CTRL | P-014 | Nils Castellan | 2025-11-05 | 2025-12-23 | 21.2 | 28.1 | Closed
WI-1034 | REQ-0511 | ShouldShip | PWR-MGMT | P-012 | Liam Moreau | 2026-05-24 | 2026-05-27 | 26.9 | 20.3 | Closed
WI-1035 | REQ-0512 | Nice | DIAG-LOG | P-017 | Quentin Zielinski | 2026-05-01 | 2026-05-28 | 21.9 | 23.1 | Closed
WI-1036 | REQ-0514 | MustShip | FLT-CTRL | P-002 | Bruno Oyelaran | 2026-04-17 | 2026-04-26 | 21.1 | 17.7 | Closed
WI-1037 | REQ-0514 | MustShip | FLT-CTRL | P-017 | Quentin Zielinski | 2026-01-17 | 2026-03-13 | 28.5 | 40.6 | Closed
WI-1038 | REQ-0514 | MustShip | FLT-CTRL | P-021 | Ulrike Dalgleish | 2026-04-18 | 2026-06-01 | 23.7 | 30.2 | Closed
WI-1039 | REQ-0515 | MustShip | REL-MECH | P-018 | Rafael Grigorescu | 2026-03-16 | 2026-04-09 | 9.8 | 10 | Closed
WI-1040 | REQ-0516 | ShouldShip | GND-CTRL | P-006 | Farid Saltzman | 2025-11-07 | 2025-12-18 | 18.1 | 22.3 | Closed
WI-1041 | REQ-0516 | ShouldShip | GND-CTRL | P-005 | Elena Lindqvist | 2026-03-31 | 2026-04-22 | 22.4 | 22.4 | Closed
WI-1042 | REQ-0516 | ShouldShip | GND-CTRL | P-005 | Elena Lindqvist | 2026-04-15 | 2026-05-07 | 4.1 | 4.1 | Closed
WI-1043 | REQ-0517 | Nice | REL-MECH | P-011 | Katya Fairweather | 2025-11-25 | 2026-01-21 | 18.5 | 26.6 | Closed
WI-1044 | REQ-0517 | Nice | REL-MECH | P-019 | Sana Nakamura | 2025-11-26 | 2025-12-15 | 19 | 18.3 | Closed
WI-1045 | REQ-0517 | Nice | REL-MECH | P-010 | Jonas Weatherby | 2026-01-21 | 2026-02-18 | 6.9 | 7.4 | Closed
WI-1046 | REQ-0517 | Nice | REL-MECH | P-003 | Camille Villalobos | 2025-08-27 | 2025-10-19 | 30.8 | 43 | Closed
WI-1047 | REQ-0518 | Nice | REL-MECH | P-019 | Sana Nakamura | 2025-03-09 | 2025-04-23 | 20 | 25.7 | Closed
WI-1048 | REQ-0518 | Nice | REL-MECH | P-010 | Jonas Weatherby | 2025-07-21 | 2025-09-04 | 24.9 | 32 | Closed
WI-1049 | REQ-0518 | Nice | REL-MECH | P-003 | Camille Villalobos | 2026-02-27 | 2026-03-04 | 23.3 | 18.2 | Closed
WI-1050 | REQ-0519 | ShouldShip | GND-CTRL | P-004 | Dmitri Eriksen | 2025-11-29 | 2026-01-23 | 33.4 | 47.5 | Closed
WI-1051 | REQ-0519 | ShouldShip | GND-CTRL | P-018 | Rafael Grigorescu | 2025-10-20 |  | 32 |  | InProgress
WI-1052 | REQ-0519 | ShouldShip | GND-CTRL | P-015 | Olabisi Jindal | 2026-01-12 | 2026-01-24 | 26.5 | 23 | Closed
WI-1053 | REQ-0520 | ShouldShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2026-03-03 | 2026-04-09 | 17.6 | 20.9 | Closed
WI-1054 | REQ-0520 | ShouldShip | NAV-SENS | P-013 | Mei Thackeray | 2025-04-29 | 2025-06-05 | 24.9 | 29.7 | Closed
WI-1055 | REQ-0520 | ShouldShip | NAV-SENS | P-007 | Grace Baptiste | 2025-01-20 | 2025-02-15 | 9.8 | 10.3 | Closed
WI-1056 | REQ-0521 | MustShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-04-15 | 2025-05-02 | 20.5 | 19.2 | Closed
WI-1057 | REQ-0522 | ShouldShip | FLT-CTRL | P-009 | Imani Petrovic | 2026-03-05 | 2026-04-05 | 10.8 | 12 | Closed
WI-1058 | REQ-0523 | MustShip | REL-MECH | P-008 | Hiroshi Ibarra | 2025-10-03 | 2025-10-21 | 30.1 | 28.6 | Closed
WI-1059 | REQ-0523 | MustShip | REL-MECH | P-019 | Sana Nakamura | 2026-03-02 | 2026-03-27 | 11.7 | 12.1 | Closed
WI-1060 | REQ-0524 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2026-05-27 | 2026-07-15 | 5.6 | 7.5 | Closed
WI-1061 | REQ-0524 | MustShip | NAV-SENS | P-008 | Hiroshi Ibarra | 2026-03-17 | 2026-05-10 | 28.8 | 40.5 | Closed
WI-1062 | REQ-0525 | Nice | COMM-LNK | P-018 | Rafael Grigorescu | 2025-04-18 | 2025-04-29 | 7.8 | 6.7 | Closed
WI-1063 | REQ-0526 | ShouldShip | DIAG-LOG | P-008 | Hiroshi Ibarra | 2026-05-05 | 2026-05-25 | 11.1 | 10.8 | Closed
WI-1064 | REQ-0526 | ShouldShip | DIAG-LOG | P-017 | Quentin Zielinski | 2025-07-15 | 2025-07-24 | 31.2 | 25.9 | Closed
WI-1065 | REQ-0527 | ShouldShip | GND-CTRL | P-003 | Camille Villalobos | 2025-01-08 | 2025-02-05 | 29.1 | 31.2 | Closed
WI-1066 | REQ-0527 | ShouldShip | GND-CTRL | P-017 | Quentin Zielinski | 2026-04-09 | 2026-05-30 | 18.4 | 25.1 | Closed
WI-1067 | REQ-0528 | MustShip | FLT-CTRL | P-011 | Katya Fairweather | 2025-06-13 | 2025-07-12 | 8.6 | 9.4 | Closed
WI-1068 | REQ-0529 | MustShip | NAV-SENS | P-010 | Jonas Weatherby | 2025-04-19 | 2025-06-14 | 12.8 | 18.3 | Closed
WI-1069 | REQ-0529 | MustShip | NAV-SENS | P-001 | Aditi Halvorsen | 2025-01-09 | 2025-01-27 | 2 | 1.9 | Closed
WI-1070 | REQ-0530 | MustShip | DIAG-LOG | P-011 | Katya Fairweather | 2026-06-18 | 2026-08-12 | 31.9 | 45.4 | Closed
WI-1071 | REQ-0530 | MustShip | DIAG-LOG | P-006 | Farid Saltzman | 2025-06-21 | 2025-07-16 | 14.1 | 14.7 | Closed
WI-1072 | REQ-0530 | MustShip | DIAG-LOG | P-001 | Aditi Halvorsen | 2026-06-23 | 2026-07-09 | 26.4 | 24.4 | Closed
WI-1073 | REQ-0531 | ShouldShip | FLT-CTRL | P-006 | Farid Saltzman | 2026-02-23 | 2026-03-13 | 18.5 | 17.5 | Closed
WI-1074 | REQ-0531 | ShouldShip | FLT-CTRL | P-011 | Katya Fairweather | 2026-04-11 | 2026-05-07 | 12.6 | 13.3 | Closed
WI-1075 | REQ-0531 | ShouldShip | FLT-CTRL | P-018 | Rafael Grigorescu | 2025-10-02 |  | 2.5 |  | InProgress
WI-1076 | REQ-0532 | ShouldShip | NAV-SENS | P-021 | Ulrike Dalgleish | 2026-06-02 | 2026-07-17 | 6.3 | 8 | Closed
WI-1077 | REQ-0533 | MustShip | NAV-SENS | P-004 | Dmitri Eriksen | 2026-04-25 | 2026-05-16 | 23.9 | 23.5 | Closed
WI-1078 | REQ-0533 | MustShip | NAV-SENS | P-007 | Grace Baptiste | 2025-06-23 | 2025-08-03 | 12.8 | 15.9 | Closed
WI-1079 | REQ-0533 | MustShip | NAV-SENS | P-003 | Camille Villalobos | 2025-05-21 | 2025-07-16 | 9.7 | 13.8 | Closed
WI-1080 | REQ-0534 | ShouldShip | PWR-MGMT | P-011 | Katya Fairweather | 2025-09-13 | 2025-11-05 | 20 | 27.9 | Closed
WI-1081 | REQ-0534 | ShouldShip | PWR-MGMT | P-016 | Priya Quintana | 2026-06-03 | 2026-06-07 | 26.5 | 20.2 | Closed
WI-1082 | REQ-0534 | ShouldShip | PWR-MGMT | P-007 | Grace Baptiste | 2025-05-07 | 2025-06-23 | 30.3 | 40 | Closed
WI-1083 | REQ-0534 | ShouldShip | PWR-MGMT | P-012 | Liam Moreau | 2025-07-25 | 2025-09-20 | 22.1 | 32 | Closed
WI-1084 | REQ-0537 | MustShip | COMM-LNK | P-017 | Quentin Zielinski | 2026-03-18 | 2026-04-22 | 33.1 | 38.4 | Closed
WI-1085 | REQ-0537 | MustShip | COMM-LNK | P-015 | Olabisi Jindal | 2026-06-19 | 2026-07-05 | 29.8 | 27.4 | Closed
WI-1086 | REQ-0537 | MustShip | COMM-LNK | P-003 | Camille Villalobos | 2025-03-22 | 2025-03-28 | 2.3 | 1.8 | Closed
WI-1087 | REQ-0538 | MustShip | DIAG-LOG | P-013 | Mei Thackeray | 2025-08-18 | 2025-09-11 | 6.6 | 6.7 | Closed
WI-1088 | REQ-0538 | MustShip | DIAG-LOG | P-008 | Hiroshi Ibarra | 2025-07-19 | 2025-08-18 | 23.5 | 25.8 | Closed
WI-1089 | REQ-0539 | MustShip | GND-CTRL | P-008 | Hiroshi Ibarra | 2025-04-21 | 2025-06-13 | 5.9 | 8.2 | Closed
WI-1090 | REQ-0539 | MustShip | GND-CTRL | P-017 | Quentin Zielinski | 2025-03-12 | 2025-03-27 | 22.5 | 20.5 | Closed
WI-1091 | REQ-0540 | ShouldShip | FLT-CTRL | P-012 | Liam Moreau | 2025-10-22 | 2025-12-16 | 9.6 | 13.6 | Closed

## Data_DQ
AnomalyType | EntityType | Severity | ImpactClass | CountsTowardExposure | Anomalies | PopulationScanned | AnomalyRatePct | WhatItMeans
UNDER_LEVELLED_VERIFICATION | Requirement | High | Policy | 0 | 110 | 519 | 21.195 | A requirement with a passing run below the test level its type demands and no evidence that meets its policy -- a safety behaviour signed off by a unit test. Again accurate data recording an inadequate practice.
SELF_VERIFIED_SAFETY | Requirement | High | Policy | 0 | 20 | 519 | 3.854 | A Safety or Regulatory requirement with a passing run by its own owner and no evidence that meets its policy, which requires an independent tester. The record is accurate; the practice is not. Held to account by the KPI layer, not by the data-quality gate.
RUN_BEFORE_BUILD | TestRun | High | Timing | 1 | 14 | 3011 | 0.465 | A test run dated before the build it ran against existed. Either the date or the build is wrong, and which one decides whether the evidence is current -- so it can change a readiness answer.
WORKITEM_CLOSED_BEFORE_OPEN | WorkItem | High | Timing | 0 | 9 | 1091 | 0.825 | A work item closed before it was opened. Corrupts cycle-time and burn-down figures; does not touch verification evidence.
ORPHAN_DIMENSION_KEY | TestRun | High | Integrity | 1 | 0 | 3011 | 0 | A fact row pointing at a requirement, build, person or date that does not exist. Enforced structurally by foreign keys; checked anyway, because a check that never fires is how you find out the constraint was dropped.
REQ_WITHOUT_TESTCASE | Requirement | High | Coverage | 1 | 0 | 519 | 0 | A baselined requirement with no test case at all. It cannot be verified, so its readiness answer is not merely unknown -- it is unobtainable until somebody writes a test.
BLOCKED_AT_RELEASE_CANDIDATE | TestCase | Medium | Evidence | 0 | 45 | 1354 | 3.323 | A test case whose most recent run against the release candidate was Blocked. A blocked test is not evidence of anything, and a readiness metric that treats "could not run" as "did not fail" is how rig contention stays invisible until the ship date.
DUPLICATE_TEST_RUN | TestRun | Medium | Evidence | 0 | 22 | 3011 | 0.731 | The same test case recorded twice against the same build on the same day with the same result. Overstates how much testing was done; does not change any requirement's verification state, because a duplicate pass and a pass are the same evidence.
RUN_ON_WITHDRAWN_REQ | TestRun | Medium | Waste | 0 | 16 | 3011 | 0.531 | Test effort spent verifying a requirement the programme has already withdrawn. Costs rig time that the outstanding queue needs; does not affect readiness, because withdrawn requirements are out of scope by definition.
RAID_DUE_BEFORE_RAISED | RAID | Medium | Timing | 0 | 7 | 96 | 7.292 | A RAID item due before it was raised: overdue on the day it is created. IsOverdue excludes it, so it cannot inflate the overdue rate; while open it still sits in the rate's denominator, and it can never be reported overdue until its dates are corrected.
TESTCASE_NEVER_RUN | TestCase | Medium | Coverage | 0 | 0 | 1354 | 0 | A test case that exists but has never been executed. Counted separately from REQ_WITHOUT_TESTCASE so that "nobody wrote a test" and "nobody ran the test" are not reported as the same failure.

## Data_Policy
ReqType | MinTestLevel | MinTestLevelRank | RequiresIndependentTester | PolicyNote
Regulatory | Field | 4 | 1 | Certification evidence must come from the airframe, independently witnessed. Rig data is not accepted by the authority.
Performance | HIL | 3 | 0 | Timing and power figures measured in software are estimates. Performance is verified on the rig or not at all.
Safety | HIL | 3 | 1 | Safety requirements are verified on hardware and by someone other than the author. Both halves are the rule; either alone has failed before.
Functional | Integration | 2 | 0 | Interfaces must be exercised against real neighbours. A unit test proves the author's intent, not the behaviour.
Interface | Integration | 2 | 0 | An interface is verified when both sides run together. A mock agrees with whatever it was written to agree with.

## Data_Matrix
Probability | Impact | ExposureScore | ExposureBand
1 | 1 | 1 | Low
1 | 2 | 2 | Low
1 | 3 | 3 | Low
1 | 4 | 8 | Medium
1 | 5 | 10 | High
2 | 1 | 2 | Low
2 | 2 | 4 | Low
2 | 3 | 6 | Medium
2 | 4 | 10 | Medium
2 | 5 | 15 | High
3 | 1 | 3 | Low
3 | 2 | 6 | Medium
3 | 3 | 9 | Medium
3 | 4 | 14 | High
3 | 5 | 20 | Critical
4 | 1 | 4 | Low
4 | 2 | 8 | Medium
4 | 3 | 14 | High
4 | 4 | 18 | High
4 | 5 | 24 | Critical
5 | 1 | 5 | Medium
5 | 2 | 10 | Medium
5 | 3 | 17 | High
5 | 4 | 22 | Critical
5 | 5 | 25 | Critical

## Data_Targets
MetricName | TargetValue | WarningValue | Direction | Unit | Description
BlockedTestPct | 5 | 12 | LowerBetter | Percent | Test cases whose most recent run against the release candidate was Blocked rather than Pass or Fail.
CriticalRAIDOpen | 0 | 2 | LowerBetter | Count | Open or mitigating RAID items in the Critical exposure band.
OverdueRAIDPct | 10 | 25 | LowerBetter | Percent | Open RAID items past their due date, as a share of all open items, excluding items due before they were raised (a data defect).
PolicyCompliancePct | 100 | 95 | HigherBetter | Percent | Verifications meeting Ref_VerificationPolicy for their requirement type, including the independent-tester rule.
ShipReadinessPct | 100 | 95 | HigherBetter | Percent | MustShip requirements whose latest policy-compliant passing verification is still CURRENT. The ship gate; 100% is the only passing value, because a must-ship requirement is by definition one you cannot ship without.
StaleVerificationPct | 15 | 30 | LowerBetter | Percent | Of requirements whose evidence meets policy, the share whose latest policy-compliant pass predates a change to the same subsystem or a Modified change to the requirement itself. The gap between coverage and readiness.
VerificationCoveragePct | 95 | 85 | HigherBetter | Percent | Baselined requirements with any passing verification on any build. Says evidence exists; says nothing about whether it still applies.
WorkItemCompletionPct | 95 | 85 | HigherBetter | Percent | Closed work items over all work items. Reported because the programme reports it; it counts effort, not evidence.

## README
TALON ROBOTICS -- PAYLOAD DELIVERY READINESS CONTROL
THE QUESTION
Is the new payload ready to ship, and what is still open?
THE ANSWER THIS WORKBOOK GIVES
Work items are 93.9% closed. Ship readiness is 52.0%. Both are true; only one is about shipping.
WHY THEY DIFFER
A verification is evidence about ONE BUILD. If a requirement passed on build 62 and its subsystem
changed in build 71, the green tick is describing software that no longer exists. Readiness counts
only must-ship requirements whose evidence is still current AND meets the verification policy for
their type -- a safety behaviour is not verified by a unit test, and not by its own author.
WHAT IS NOT A STALENESS RULE
Age. A verification from fourteen months ago is fine if nothing underneath it has moved; one from
last Tuesday is worthless if the subsystem was rewritten on Wednesday. Intervening change is the
question, and it is why the model needs build history rather than timestamps.
SHEETS
Control Parameters. Change the rig capacity and the queue re-bounds itself.
Dashboard The contrast, the scorecard, where the gap is, and the schedule answer.
Verification Queue What to do next, ranked, bounded by one week of rig time.
Subsystem Readiness Readiness against the churn behind it.
RAID Register Exposure read from the matrix, open items first.
Validation Every Excel figure against the one SQL produced independently.
Calc Helper block for the queue. Not a reporting sheet.
Data_* The loaded extracts. Data > Refresh All re-reads them from disk.
HOW TO USE IT
Change Rig hours per week on the Control sheet and the queue re-bounds itself: that is the
"what if we add a rig" question answered without editing anything. Every threshold lives in
readiness_targets.csv, so a target the programme disagrees with can be argued with.
DATA DISCLOSURE
Talon Robotics is a fictional mechatronics company. All data in this workbook is synthetic and
generated by the scripts in the sql\ folder. No confidential data is used and no claim is made
about any production system.

## Dashboard
PAYLOAD DELIVERY -- READINESS AT THE RELEASE CANDIDATE
Assessed against build 88 ¦ as of 30 September 2026 ¦ every figure below is a formula over the extracts, not a pasted value
THE QUESTION ON THE AGENDA
MEASURE | VALUE | WHAT IT ACTUALLY MEANS
Work items closed | 93.8588 | What the programme reports. Counts effort.
Requirements with evidence | 96.5318 | Has a passing test ever run? Deliberately generous.
SHIP READINESS | 51.9573 | Must-ship requirements with CURRENT, policy-compliant evidence. The gate.
The gap | 41.9015 | Between what is reported and what can ship.
READINESS SCORECARD
METRIC | VALUE | TARGET | WARN | STATUS
Ship readiness | 51.9573 | 100 | 95 | Red
Verification coverage | 96.5318 | 95 | 85 | Green
Stale verification | 24.4845 | 15 | 30 | Amber
Policy compliance | 77.4451 | 100 | 95 | Red
Work-item completion | 93.8588 | 95 | 85 | Amber
Critical RAID open | 9 | 0 | 2 | Red
Overdue RAID | 57.7778 | 10 | 25 | Red
WHERE THE GAP IS -- readiness by subsystem, worst first
Subsystem | Criticality | Must-ship | Current | Readiness % | Builds changed
Flight Control Interface | Safety | 47 | 11 | 23.4043 | 45
Payload Release Mechanism | Safety | 62 | 20 | 32.2581 | 42
Power Management | Mission | 37 | 22 | 59.4595 | 15
Command & Telemetry Link | Mission | 43 | 26 | 60.4651 | 23
Structural Interface | Safety | 19 | 13 | 68.4211 | 15
Ground Control Software | Support | 28 | 20 | 71.4286 | 21
Navigation & Sensor Fusion | Mission | 33 | 24 | 72.7273 | 17
Diagnostics & Logging | Support | 12 | 10 | 83.3333 | 18
THE SCHEDULE ANSWER
Requirements outstanding | 226
Rig hours to clear them | 425
Rig weeks at current capacity | 2.3611 | This is the honest schedule answer: it is the only figure here a programme board can act on without a further study.
Schedulable this week | 69
Airframe hours to clear them | 272 | Field evidence needs the airframe, not a rig. Never divided by rig capacity; the data holds no airframe capacity, so it is not turned into weeks.

## Verification Queue
VERIFICATION QUEUE -- what to do next, bounded by rig capacity
Ranked by priority score. The first 69 rows fit inside 180 rig hours -- one week. A list of everything outstanding is not a plan.
Rank | Requirement | Subsystem | Type | Priority | Owner | Action | Rig hrs | Airframe hrs | Cumulative rig | This week | What to do
1 | REQ-0287 | REL-MECH | Interface | MustShip | Imani Petrovic | REVIEW_THEN_RERUN | 2.5 | 0 | 2.5 | 1 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
2 | REQ-0397 | REL-MECH | Functional | MustShip | Grace Baptiste | REVIEW_THEN_RERUN | 2.5 | 0 | 5 | 1 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
3 | REQ-0253 | FLT-CTRL | Regulatory | MustShip | Sana Nakamura | REVIEW_THEN_RERUN | 0 | 24 | 5 | 0 | The requirement itself was modified after it was verified. Confirm the test still checks the right thing, then re-run -- re-running first risks certifying against the old wording.
4 | REQ-0211 | REL-MECH | Interface | MustShip | Ulrike Dalgleish | VERIFY | 0 | 0 | 5 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
5 | REQ-0266 | REL-MECH | Interface | MustShip | Aditi Halvorsen | VERIFY | 0 | 0 | 5 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
6 | REQ-0449 | REL-MECH | Safety | MustShip | Katya Fairweather | VERIFY | 5 | 0 | 10 | 1 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
7 | REQ-0176 | REL-MECH | Regulatory | MustShip | Hiroshi Ibarra | VERIFY | 0 | 8 | 10 | 0 | No passing evidence exists. Write and run the test before the gate review; this is not a re-run, it is first-time verification.
8 | REQ-0085 | REL-MECH | Interface | MustShip | Imani Petrovic | RERUN | 0 | 0 | 10 | 1 | Evidence was valid at build 59 but the subsystem has changed in 21 builds since. Re-run on the release candidate.
9 | REQ-0260 | REL-MECH | Interface | MustShip | Quentin Zielinski | RERUN | 0 | 0 | 10 | 1 | Evidence was valid at build 55 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
10 | REQ-0338 | REL-MECH | Functional | MustShip | Elena Lindqvist | RERUN | 0 | 0 | 10 | 1 | Evidence was valid at build 67 but the subsystem has changed in 15 builds since. Re-run on the release candidate.
11 | REQ-0340 | FLT-CTRL | Functional | MustShip | Farid Saltzman | RERUN | 0 | 0 | 10 | 1 | Evidence was valid at build 42 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
12 | REQ-0401 | REL-MECH | Interface | MustShip | Priya Quintana | RERUN | 0 | 0 | 10 | 1 | Evidence was valid at build 41 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
13 | REQ-0036 | FLT-CTRL | Functional | MustShip | Elena Lindqvist | RERUN | 2.5 | 0 | 12.5 | 1 | Evidence was valid at build 66 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
14 | REQ-0157 | REL-MECH | Safety | MustShip | Aditi Halvorsen | RERUN | 2.5 | 0 | 15 | 1 | Evidence was valid at build 68 but the subsystem has changed in 14 builds since. Re-run on the release candidate.
15 | REQ-0217 | REL-MECH | Safety | MustShip | Camille Villalobos | RERUN | 2.5 | 0 | 17.5 | 1 | Evidence was valid at build 40 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
16 | REQ-0225 | FLT-CTRL | Safety | MustShip | Aditi Halvorsen | RERUN | 2.5 | 0 | 20 | 1 | Evidence was valid at build 51 but the subsystem has changed in 23 builds since. Re-run on the release candidate.
17 | REQ-0252 | REL-MECH | Safety | MustShip | Dmitri Eriksen | RERUN | 2.5 | 0 | 22.5 | 1 | Evidence was valid at build 49 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
18 | REQ-0350 | FLT-CTRL | Safety | MustShip | Dmitri Eriksen | RERUN | 2.5 | 0 | 25 | 1 | Evidence was valid at build 30 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
19 | REQ-0359 | FLT-CTRL | Safety | MustShip | Elena Lindqvist | RERUN | 2.5 | 0 | 27.5 | 1 | Evidence was valid at build 54 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
20 | REQ-0372 | FLT-CTRL | Safety | MustShip | Jonas Weatherby | RERUN | 2.5 | 0 | 30 | 1 | Evidence was valid at build 29 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
21 | REQ-0429 | REL-MECH | Safety | MustShip | Sana Nakamura | RERUN | 2.5 | 0 | 32.5 | 1 | Evidence was valid at build 41 but the subsystem has changed in 25 builds since. Re-run on the release candidate.
22 | REQ-0472 | FLT-CTRL | Safety | MustShip | Priya Quintana | RERUN | 2.5 | 0 | 35 | 1 | Evidence was valid at build 32 but the subsystem has changed in 33 builds since. Re-run on the release candidate.
23 | REQ-0478 | FLT-CTRL | Performance | MustShip | Nils Castellan | RERUN | 2.5 | 0 | 37.5 | 1 | Evidence was valid at build 64 but the subsystem has changed in 18 builds since. Re-run on the release candidate.
24 | REQ-0060 | FLT-CTRL | Safety | MustShip | Rafael Grigorescu | RERUN | 5 | 0 | 42.5 | 1 | Evidence was valid at build 53 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
25 | REQ-0069 | FLT-CTRL | Safety | MustShip | Jonas Weatherby | RERUN | 5 | 0 | 47.5 | 1 | Evidence was valid at build 59 but the subsystem has changed in 21 builds since. Re-run on the release candidate.
26 | REQ-0106 | FLT-CTRL | Safety | MustShip | Dmitri Eriksen | RERUN | 5 | 0 | 52.5 | 1 | Evidence was valid at build 42 but the subsystem has changed in 27 builds since. Re-run on the release candidate.
27 | REQ-0165 | REL-MECH | Functional | MustShip | Rafael Grigorescu | RERUN | 5 | 0 | 57.5 | 1 | Evidence was valid at build 71 but the subsystem has changed in 12 builds since. Re-run on the release candidate.
28 | REQ-0166 | REL-MECH | Safety | MustShip | Elena Lindqvist | RERUN | 5 | 0 | 62.5 | 1 | Evidence was valid at build 54 but the subsystem has changed in 22 builds since. Re-run on the release candidate.
29 | REQ-0167 | REL-MECH | Safety | MustShip | Katya Fairweather | RERUN | 5 | 0 | 67.5 | 1 | Evidence was valid at build 65 but the subsystem has changed in 16 builds since. Re-run on the release candidate.
30 | REQ-0191 | REL-MECH | Safety | MustShip | Mei Thackeray | RERUN | 5 | 0 | 72.5 | 1 | Evidence was valid at build 65 but the subsystem has changed in 16 builds since. Re-run on the release candidate.

## Subsystem Readiness
SUBSYSTEM READINESS -- and the churn behind it
A subsystem that changed forty times and is a quarter ready is not behind on testing -- it is still being designed. That is a different conversation with a different owner.
Subsystem | Criticality | Reqs | Must-ship | Current | Readiness % | No evidence | Insufficient | Stale (code) | Stale (req) | Builds changed | Rig hrs
Flight Control Interface | Safety | 79 | 47 | 11 | 23.4043 | 0 | 22 | 31 | 3 | 45 | 120
Payload Release Mechanism | Safety | 93 | 62 | 20 | 32.2581 | 6 | 25 | 30 | 3 | 42 | 132.5
Power Management | Mission | 78 | 37 | 22 | 59.4595 | 4 | 20 | 5 | 0 | 15 | 32.5
Command & Telemetry Link | Mission | 73 | 43 | 26 | 60.4651 | 5 | 15 | 5 | 0 | 23 | 52.5
Structural Interface | Safety | 29 | 19 | 13 | 68.4211 | 0 | 4 | 4 | 0 | 15 | 15
Ground Control Software | Support | 61 | 28 | 20 | 71.4286 | 2 | 12 | 4 | 1 | 21 | 25
Navigation & Sensor Fusion | Mission | 66 | 33 | 24 | 72.7273 | 1 | 10 | 5 | 0 | 17 | 30
Diagnostics & Logging | Support | 40 | 12 | 10 | 83.3333 | 0 | 5 | 4 | 0 | 18 | 17.5

## RAID Register
RAID REGISTER -- scored against the matrix, open items first
Exposure is read from Ref_RAIDMatrix, not computed as probability x impact. A board treats "unlikely but catastrophic" differently from "certain but trivial" even though the product is the same.
Open items | 45
Critical band, open | 9
Overdue, open | 26
Total open exposure | 466
RAID | Type | Subsystem | Owner | Prob | Impact | Exposure | Band | Status | Overdue days | Mitigation
RAID-041 | Issue | PWR-MGMT | Camille Villalobos | 5 | 5 | 25 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-045 | Issue | REL-MECH | Dmitri Eriksen | 5 | 5 | 25 | Critical | Open | 54 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-055 | Risk | REL-MECH | Nils Castellan | 5 | 5 | 25 | Critical | Open | 239 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-061 | Issue | COMM-LNK | Sana Nakamura | 5 | 5 | 25 | Critical | Open | 102 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-083 | Dependency | PWR-MGMT | Hiroshi Ibarra | 5 | 5 | 25 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-091 | Risk | PWR-MGMT | Aditi Halvorsen | 5 | 5 | 25 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-032 | Risk | DIAG-LOG | Mei Thackeray | 4 | 5 | 24 | Critical | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-075 | Assumption | COMM-LNK | Ulrike Dalgleish | 4 | 5 | 24 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-086 | Dependency | STRUCT-I | Hiroshi Ibarra | 4 | 5 | 24 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-051 | Risk | FLT-CTRL | Jonas Weatherby | 5 | 4 | 22 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-090 | Issue | FLT-CTRL | Tomas Ustinov | 5 | 4 | 22 | Critical | Open | 0 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-004 | Issue | COMM-LNK | Tomas Ustinov | 3 | 5 | 20 | Critical | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-015 | Issue | FLT-CTRL | Aditi Halvorsen | 3 | 5 | 20 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-018 | Dependency | REL-MECH | Bruno Oyelaran | 3 | 5 | 20 | Critical | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-033 | Risk | GND-CTRL | Liam Moreau | 3 | 5 | 20 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-042 | Risk | PWR-MGMT | Aditi Halvorsen | 3 | 5 | 20 | Critical | Open | 71 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-072 | Issue | REL-MECH | Ulrike Dalgleish | 3 | 5 | 20 | Critical | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-073 | Risk | FLT-CTRL | Sana Nakamura | 3 | 5 | 20 | Critical | Open | 355 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-043 | Risk | REL-MECH | Camille Villalobos | 4 | 4 | 18 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-048 | Issue | PWR-MGMT | Farid Saltzman | 4 | 4 | 18 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-005 | Assumption | STRUCT-I | Nils Castellan | 5 | 3 | 17 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-009 | Issue | FLT-CTRL | Jonas Weatherby | 5 | 3 | 17 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-027 | Risk | STRUCT-I | Rafael Grigorescu | 5 | 3 | 17 | High | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-068 | Risk | NAV-SENS | Nils Castellan | 5 | 3 | 17 | High | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-017 | Assumption | FLT-CTRL | Aditi Halvorsen | 2 | 5 | 15 | High | Open | 0 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-021 | Issue | NAV-SENS | Mei Thackeray | 3 | 4 | 14 | High | Mitigating | 230 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-028 | Risk | GND-CTRL | Mei Thackeray | 3 | 4 | 14 | High | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-030 | Assumption | DIAG-LOG | Elena Lindqvist | 4 | 3 | 14 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-036 | Risk | FLT-CTRL | Jonas Weatherby | 3 | 4 | 14 | High | Open | 243 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-039 | Risk | REL-MECH | Olabisi Jindal | 3 | 4 | 14 | High | Open | 236 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-053 | Assumption | NAV-SENS | Priya Quintana | 3 | 4 | 14 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-059 | Dependency | FLT-CTRL | Mei Thackeray | 3 | 4 | 14 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-080 | Issue | GND-CTRL | Nils Castellan | 3 | 4 | 14 | High | Mitigating | 0 | Mitigation in progress; owner reporting weekly to the programme board.
RAID-084 | Dependency | REL-MECH | Mei Thackeray | 4 | 3 | 14 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-001 | Issue | REL-MECH | Olabisi Jindal | 5 | 2 | 10 | Medium | Open | 14 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-011 | Dependency | NAV-SENS | Priya Quintana | 5 | 2 | 10 | Medium | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-014 | Assumption | COMM-LNK | Hiroshi Ibarra | 2 | 4 | 10 | Medium | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-016 | Issue | FLT-CTRL | Aditi Halvorsen | 1 | 5 | 10 | High | Closed | 0 | Closed: mitigation completed and evidence attached to the verification record.
RAID-031 | Risk | FLT-CTRL | Aditi Halvorsen | 1 | 5 | 10 | High | Open | 0 | Open: no mitigation started. Requires a decision at the next programme board.
RAID-034 | Risk | REL-MECH | Camille Villalobos | 5 | 2 | 10 | Medium | Open | 0 | Open: no mitigation started. Requires a decision at the next programme board.

## Validation
VALIDATION -- every Excel figure against the one SQL produced independently
Each row recomputes a figure with Excel formulas over the extracts, then compares it with the value SQL published in readiness_kpi.csv. Agreement is necessary, not sufficient -- both could be derived from the same flawed definition -- but disagreement is decisive.
# | Figure | Excel | SQL | Difference | Result
1 | Requirements (baselined) | 519 | 519 | 0 | MATCH
2 | Must-ship requirements | 281 | 281 | 0 | MATCH
3 | Ship readiness % | 51.9573 | 51.96 | 0.0027046 | MATCH
4 | Verification coverage % | 96.5318 | 96.53 | 0.0017919 | MATCH
5 | Stale verification % | 24.4845 | 24.48 | 0.0045361 | MATCH
6 | Policy compliance % | 77.4451 | 77.45 | 0.0048902 | MATCH
7 | Work-item completion % | 93.8588 | 93.86 | 0.0011549 | MATCH
8 | No evidence (count) | 18 | 18 | 0 | MATCH
9 | Insufficient (count) | 113 | 113 | 0 | MATCH
10 | Current (count) | 293 | 293 | 0 | MATCH
11 | Queue size | 226 | 226 | 0 | MATCH
12 | Rig hours outstanding | 425 | 425 | 0 | MATCH
13 | Airframe hours outstanding | 272 | 272 | 0 | MATCH
14 | Critical RAID open | 9 | 9 | 0 | MATCH
15 | Overdue RAID % | 57.7778 | 57.78 | 0.0022222 | MATCH
16 | Must-ship, subsystem sum | 281 | 281 | 0 | MATCH
17 | Current, subsystem sum | 146 | 146 | 0 | MATCH
| Checks reconciling: | 17 of 17

## Calc
CALC -- helper block for the Verification Queue ranking. Not a reporting sheet.
Rank | RequirementID | RigHours | Cumulative rig hours (Excel, independent of SQL) | Airframe hours (never in the rig week) | Within the week
1 | REQ-0287 | 2.5 | 2.5 | 0 | 1
2 | REQ-0397 | 2.5 | 5 | 0 | 1
3 | REQ-0253 | 0 | 5 | 24 | 0
4 | REQ-0211 | 0 | 5 | 0 | 1
5 | REQ-0266 | 0 | 5 | 0 | 1
6 | REQ-0449 | 5 | 10 | 0 | 1
7 | REQ-0176 | 0 | 10 | 8 | 0
8 | REQ-0085 | 0 | 10 | 0 | 1
9 | REQ-0260 | 0 | 10 | 0 | 1
10 | REQ-0338 | 0 | 10 | 0 | 1
11 | REQ-0340 | 0 | 10 | 0 | 1
12 | REQ-0401 | 0 | 10 | 0 | 1
13 | REQ-0036 | 2.5 | 12.5 | 0 | 1
14 | REQ-0157 | 2.5 | 15 | 0 | 1
15 | REQ-0217 | 2.5 | 17.5 | 0 | 1
16 | REQ-0225 | 2.5 | 20 | 0 | 1
17 | REQ-0252 | 2.5 | 22.5 | 0 | 1
18 | REQ-0350 | 2.5 | 25 | 0 | 1
19 | REQ-0359 | 2.5 | 27.5 | 0 | 1
20 | REQ-0372 | 2.5 | 30 | 0 | 1
21 | REQ-0429 | 2.5 | 32.5 | 0 | 1
22 | REQ-0472 | 2.5 | 35 | 0 | 1
23 | REQ-0478 | 2.5 | 37.5 | 0 | 1
24 | REQ-0060 | 5 | 42.5 | 0 | 1
25 | REQ-0069 | 5 | 47.5 | 0 | 1
26 | REQ-0106 | 5 | 52.5 | 0 | 1
27 | REQ-0165 | 5 | 57.5 | 0 | 1
28 | REQ-0166 | 5 | 62.5 | 0 | 1
29 | REQ-0167 | 5 | 67.5 | 0 | 1
30 | REQ-0191 | 5 | 72.5 | 0 | 1
31 | REQ-0258 | 5 | 77.5 | 0 | 1
32 | REQ-0269 | 5 | 82.5 | 0 | 1
33 | REQ-0300 | 5 | 87.5 | 0 | 1
34 | REQ-0439 | 5 | 92.5 | 0 | 1
35 | REQ-0528 | 5 | 97.5 | 0 | 1
36 | REQ-0280 | 7.5 | 105 | 0 | 1
37 | REQ-0349 | 7.5 | 112.5 | 0 | 1
38 | REQ-0515 | 7.5 | 120 | 0 | 1
39 | REQ-0034 | 0 | 120 | 8 | 0
40 | REQ-0187 | 0 | 120 | 8 | 0
41 | REQ-0198 | 0 | 120 | 8 | 0
42 | REQ-0417 | 0 | 120 | 8 | 0
43 | REQ-0467 | 0 | 120 | 8 | 0
44 | REQ-0113 | 0 | 120 | 16 | 0
45 | REQ-0154 | 0 | 120 | 16 | 0
46 | REQ-0235 | 0 | 120 | 16 | 0
47 | REQ-0308 | 0 | 120 | 16 | 0
48 | REQ-0118 | 0 | 120 | 0 | 1
49 | REQ-0137 | 0 | 120 | 0 | 1
50 | REQ-0141 | 0 | 120 | 0 | 1
51 | REQ-0178 | 0 | 120 | 0 | 1
52 | REQ-0208 | 0 | 120 | 0 | 1
53 | REQ-0306 | 0 | 120 | 0 | 1
54 | REQ-0324 | 0 | 120 | 0 | 1
55 | REQ-0438 | 0 | 120 | 0 | 1
56 | REQ-0473 | 0 | 120 | 0 | 1
57 | REQ-0026 | 2.5 | 122.5 | 0 | 1
58 | REQ-0035 | 2.5 | 125 | 0 | 1
59 | REQ-0043 | 2.5 | 127.5 | 0 | 1
60 | REQ-0053 | 2.5 | 130 | 0 | 1
61 | REQ-0080 | 2.5 | 132.5 | 0 | 1
62 | REQ-0109 | 2.5 | 135 | 0 | 1
63 | REQ-0149 | 2.5 | 137.5 | 0 | 1
64 | REQ-0169 | 2.5 | 140 | 0 | 1
65 | REQ-0181 | 2.5 | 142.5 | 0 | 1
66 | REQ-0189 | 2.5 | 145 | 0 | 1
67 | REQ-0301 | 2.5 | 147.5 | 0 | 1
68 | REQ-0336 | 2.5 | 150 | 0 | 1
69 | REQ-0382 | 2.5 | 152.5 | 0 | 1
70 | REQ-0427 | 2.5 | 155 | 0 | 1
71 | REQ-0469 | 2.5 | 157.5 | 0 | 1
72 | REQ-0475 | 2.5 | 160 | 0 | 1
73 | REQ-0488 | 2.5 | 162.5 | 0 | 1
74 | REQ-0493 | 2.5 | 165 | 0 | 1
75 | REQ-0514 | 2.5 | 167.5 | 0 | 1
76 | REQ-0521 | 2.5 | 170 | 0 | 1
77 | REQ-0089 | 0 | 170 | 8 | 0
78 | REQ-0368 | 0 | 170 | 8 | 0
79 | REQ-0392 | 0 | 170 | 8 | 0
80 | REQ-0412 | 0 | 170 | 8 | 0
81 | REQ-0503 | 0 | 170 | 8 | 0
82 | REQ-0014 | 2.5 | 172.5 | 0 | 1
83 | REQ-0092 | 5 | 177.5 | 0 | 1
84 | REQ-0434 | 2.5 | 180 | 0 | 1
85 | REQ-0099 | 0 | 180 | 0 | 1
86 | REQ-0249 | 2.5 | 182.5 | 0 | 0
87 | REQ-0398 | 2.5 | 185 | 0 | 0
88 | REQ-0444 | 2.5 | 187.5 | 0 | 0
89 | REQ-0027 | 2.5 | 190 | 0 | 0
90 | REQ-0416 | 5 | 195 | 0 | 0
91 | REQ-0496 | 5 | 200 | 0 | 0
92 | REQ-0008 | 0 | 200 | 0 | 0
93 | REQ-0124 | 0 | 200 | 0 | 0
94 | REQ-0155 | 0 | 200 | 0 | 0
95 | REQ-0218 | 0 | 200 | 0 | 0
96 | REQ-0433 | 0 | 200 | 0 | 0
97 | REQ-0459 | 0 | 200 | 0 | 0
98 | REQ-0486 | 0 | 200 | 0 | 0
99 | REQ-0028 | 2.5 | 202.5 | 0 | 0
100 | REQ-0049 | 2.5 | 205 | 0 | 0
101 | REQ-0122 | 2.5 | 207.5 | 0 | 0
102 | REQ-0172 | 2.5 | 210 | 0 | 0
103 | REQ-0196 | 2.5 | 212.5 | 0 | 0
104 | REQ-0197 | 2.5 | 215 | 0 | 0
105 | REQ-0233 | 2.5 | 217.5 | 0 | 0
106 | REQ-0247 | 2.5 | 220 | 0 | 0
107 | REQ-0272 | 2.5 | 222.5 | 0 | 0
108 | REQ-0286 | 2.5 | 225 | 0 | 0
109 | REQ-0316 | 2.5 | 227.5 | 0 | 0
110 | REQ-0378 | 2.5 | 230 | 0 | 0
111 | REQ-0529 | 2.5 | 232.5 | 0 | 0
112 | REQ-0537 | 2.5 | 235 | 0 | 0
113 | REQ-0116 | 5 | 240 | 0 | 0
114 | REQ-0224 | 5 | 245 | 0 | 0
115 | REQ-0042 | 0 | 245 | 8 | 0
116 | REQ-0161 | 0 | 245 | 8 | 0
117 | REQ-0194 | 0 | 245 | 8 | 0
118 | REQ-0228 | 0 | 245 | 8 | 0
119 | REQ-0394 | 0 | 245 | 8 | 0
120 | REQ-0457 | 0 | 245 | 8 | 0
121 | REQ-0464 | 0 | 245 | 8 | 0
122 | REQ-0443 | 0 | 245 | 0 | 0
123 | REQ-0045 | 2.5 | 247.5 | 0 | 0
124 | REQ-0093 | 5 | 252.5 | 0 | 0
125 | REQ-0435 | 0 | 252.5 | 8 | 0
126 | REQ-0346 | 0 | 252.5 | 0 | 0
127 | REQ-0354 | 0 | 252.5 | 0 | 0
128 | REQ-0402 | 0 | 252.5 | 0 | 0
129 | REQ-0428 | 0 | 252.5 | 0 | 0
130 | REQ-0199 | 2.5 | 255 | 0 | 0
131 | REQ-0223 | 2.5 | 257.5 | 0 | 0
132 | REQ-0274 | 2.5 | 260 | 0 | 0
133 | REQ-0540 | 2.5 | 262.5 | 0 | 0
134 | REQ-0539 | 0 | 262.5 | 0 | 0
135 | REQ-0012 | 2.5 | 265 | 0 | 0
136 | REQ-0293 | 2.5 | 267.5 | 0 | 0
137 | REQ-0482 | 2.5 | 270 | 0 | 0
138 | REQ-0057 | 0 | 270 | 0 | 0
139 | REQ-0077 | 0 | 270 | 0 | 0
140 | REQ-0320 | 0 | 270 | 0 | 0
141 | REQ-0348 | 0 | 270 | 0 | 0
142 | REQ-0505 | 0 | 270 | 0 | 0
143 | REQ-0037 | 2.5 | 272.5 | 0 | 0
144 | REQ-0147 | 2.5 | 275 | 0 | 0
145 | REQ-0148 | 2.5 | 277.5 | 0 | 0
146 | REQ-0406 | 2.5 | 280 | 0 | 0
147 | REQ-0407 | 2.5 | 282.5 | 0 | 0
148 | REQ-0495 | 2.5 | 285 | 0 | 0
149 | REQ-0501 | 2.5 | 287.5 | 0 | 0
150 | REQ-0262 | 5 | 292.5 | 0 | 0
151 | REQ-0377 | 7.5 | 300 | 0 | 0
152 | REQ-0376 | 0 | 300 | 8 | 0
153 | REQ-0278 | 0 | 300 | 16 | 0
154 | REQ-0002 | 0 | 300 | 0 | 0
155 | REQ-0222 | 0 | 300 | 0 | 0
156 | REQ-0446 | 0 | 300 | 0 | 0
157 | REQ-0132 | 2.5 | 302.5 | 0 | 0
158 | REQ-0243 | 2.5 | 305 | 0 | 0
159 | REQ-0245 | 2.5 | 307.5 | 0 | 0
160 | REQ-0337 | 2.5 | 310 | 0 | 0
161 | REQ-0342 | 2.5 | 312.5 | 0 | 0
162 | REQ-0345 | 2.5 | 315 | 0 | 0
163 | REQ-0363 | 2.5 | 317.5 | 0 | 0
164 | REQ-0380 | 2.5 | 320 | 0 | 0
165 | REQ-0290 | 0 | 320 | 8 | 0
166 | REQ-0239 | 0 | 320 | 0 | 0
167 | REQ-0480 | 0 | 320 | 0 | 0
168 | REQ-0005 | 2.5 | 322.5 | 0 | 0
169 | REQ-0329 | 2.5 | 325 | 0 | 0
170 | REQ-0362 | 2.5 | 327.5 | 0 | 0
171 | REQ-0502 | 2.5 | 330 | 0 | 0
172 | REQ-0297 | 0 | 330 | 0 | 0
173 | REQ-0518 | 0 | 330 | 0 | 0
174 | REQ-0517 | 2.5 | 332.5 | 0 | 0
175 | REQ-0004 | 0 | 332.5 | 0 | 0
176 | REQ-0110 | 0 | 332.5 | 0 | 0
177 | REQ-0326 | 0 | 332.5 | 0 | 0
178 | REQ-0373 | 0 | 332.5 | 0 | 0
179 | REQ-0256 | 2.5 | 335 | 0 | 0
180 | REQ-0437 | 2.5 | 337.5 | 0 | 0
181 | REQ-0532 | 5 | 342.5 | 0 | 0
182 | REQ-0128 | 0 | 342.5 | 0 | 0
183 | REQ-0138 | 2.5 | 345 | 0 | 0
184 | REQ-0454 | 2.5 | 347.5 | 0 | 0
185 | REQ-0120 | 5 | 352.5 | 0 | 0
186 | REQ-0396 | 5 | 357.5 | 0 | 0
187 | REQ-0064 | 0 | 357.5 | 0 | 0
188 | REQ-0031 | 2.5 | 360 | 0 | 0
189 | REQ-0058 | 2.5 | 362.5 | 0 | 0
190 | REQ-0108 | 2.5 | 365 | 0 | 0
191 | REQ-0284 | 2.5 | 367.5 | 0 | 0
192 | REQ-0361 | 2.5 | 370 | 0 | 0
193 | REQ-0160 | 0 | 370 | 0 | 0
194 | REQ-0311 | 0 | 370 | 0 | 0
195 | REQ-0367 | 0 | 370 | 0 | 0
196 | REQ-0453 | 0 | 370 | 0 | 0
197 | REQ-0383 | 2.5 | 372.5 | 0 | 0
198 | REQ-0299 | 0 | 372.5 | 0 | 0
199 | REQ-0335 | 0 | 372.5 | 0 | 0
200 | REQ-0508 | 0 | 372.5 | 0 | 0
201 | REQ-0516 | 0 | 372.5 | 0 | 0
202 | REQ-0007 | 2.5 | 375 | 0 | 0
203 | REQ-0117 | 2.5 | 377.5 | 0 | 0
204 | REQ-0212 | 2.5 | 380 | 0 | 0
205 | REQ-0448 | 2.5 | 382.5 | 0 | 0
206 | REQ-0095 | 0 | 382.5 | 0 | 0
207 | REQ-0151 | 0 | 382.5 | 0 | 0
208 | REQ-0310 | 0 | 382.5 | 0 | 0
209 | REQ-0048 | 2.5 | 385 | 0 | 0
210 | REQ-0066 | 2.5 | 387.5 | 0 | 0
211 | REQ-0152 | 2.5 | 390 | 0 | 0
212 | REQ-0220 | 2.5 | 392.5 | 0 | 0
213 | REQ-0307 | 2.5 | 395 | 0 | 0
214 | REQ-0462 | 2.5 | 397.5 | 0 | 0
215 | REQ-0355 | 5 | 402.5 | 0 | 0
216 | REQ-0107 | 7.5 | 410 | 0 | 0
217 | REQ-0216 | 5 | 415 | 0 | 0
218 | REQ-0114 | 0 | 415 | 0 | 0
219 | REQ-0241 | 0 | 415 | 0 | 0
220 | REQ-0131 | 2.5 | 417.5 | 0 | 0
221 | REQ-0184 | 2.5 | 420 | 0 | 0
222 | REQ-0313 | 0 | 420 | 0 | 0
223 | REQ-0323 | 0 | 420 | 0 | 0
224 | REQ-0366 | 0 | 420 | 0 | 0
225 | REQ-0076 | 2.5 | 422.5 | 0 | 0
226 | REQ-0079 | 2.5 | 425 | 0 | 0